## DataBase
275 | 275 | 275 | 275 | 275 | 275 | 0 | 0 | 0 | 275 | 275 | 275 | 36 | 18 | 275 | 275 | 0 | 275 | 275 | 275 | 211 | 275 | 275 | 268 | 0 | 0 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 3 | 0 | 2 | 2 | 269 | 180 | 0 | 272 | 272 | 270 | 74 | 5 | 151 | 272 | 272 | 275
275 | 275 | 275 | 275 | 275 | 275 | 210 | 275 | 275 | 275 | 275 | 275 | 221 | 18 | 275 | 275 | 0 | 275 | 275 | 275 | 218 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 268 | 268 | 268 | 268 | 268 | 274 | 274 | 267 | 264 | 250 | 275 | 275 | 275 | 275 | 275 | 275 | 185 | 268 | 275 | 275 | 275 | 184 | 232 | 267 | 275 | 275 | 275
Site ID | Macro/Small | Project | SAQ Status | SAQ Stage | District | Priority | SSO Latitude | SSO Longitude | Vendor | Scope Type | Same/New Location | Hajj/Ramadan | Old Site ID | Site type | Doable/Not Doable | Reason for Non Doable | SSO GAT Status | ISR GAT Status | IGATE/Non IGATE | Submitted in IGATE | Request Number in IGATE | Request Status | Owner in IGATE | ISS Date | ISR Submitted to RF | ISR Document (STC) | ISR Document (SAQ) | OA Submitted to TTC | OA Approved by TTC | IBP Submit | IBP | Baladiya Contract Issued | Baladiya Contract Submitted to Tawal | Baladiya Contract Signed By Tawal | Non Private Contract Signed By Non Private | Private Contract Sign Date (Tawal) | Private Contract Sign Date (Owner) | Application Number | FBP Submit date | FBP Issue date | FSSR Date | FSSR Lat. | FSSR Long. | SAF Date | TCC Date | Tower Type | Area dimension | HOC date | Private/Non-Private | Owner's Type (Gov/Amanah/Private) | Owner's Name | Owner Contract Information | Rent Value | Area | Site Type (GF/RT) | Nokia TL Name | 2021-11-15
PMD889 | Macro | Aspiration | HOC | HO to CW Done | Madinah | 2020 | 24.505 | 39.5451 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 01/05/2019 15:46:10 | SNR1010016 | NOBODY | ACCEPTED | 2019-03-21 | 2019-03-24 | 2019-03-24 | 2019-03-26 | NA | NA | 2019-10-15 | 2019-10-15 | 2019-10-15 | 2019-10-15 | 2019-10-15 | 2019-10-15 | NA | NA | NI-35/331 | 2019-10-15 | 2019-10-15 | 2019-08-23 | 24.505 | 39.5451 | 2019-08-29 | 2019-09-01 | 11.5m Concealed Pole |  | 2019-10-15 | Non-Private | GOV | المراسم الملكيه | NA | Free | 1M | GF | Fahad Aljohany | HOC
PMD890 | Macro | Aspiration | HOC | HO to CW Done | Madinah | 2020 | 24.5048 | 39.5418 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 14/05/2019 21:43:01 | SNR1010248 | NOBODY | ACCEPTED | 2019-03-21 | 2019-03-24 | 2019-03-24 | 2019-03-26 | NA | NA | 2019-10-15 | 2019-10-15 | 2019-10-15 | 2019-10-15 | 2019-10-15 | 2019-10-15 | NA | NA | NI-35/331 | 2019-10-15 | 2019-10-15 | 2019-08-23 | 24.5048 | 39.5418 | 2019-08-29 | 2019-09-01 | 11.5m Concealed Pole |  | 2019-10-15 | Non-Private | GOV | المراسم الملكيه | NA | Free | 1M | GF | Fahad Aljohany | HOC
ZAB379 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2020 | 18.1992 | 42.5103 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 27/04/2019 17:14:37 | SNR1009737 | NOBODY | ACCEPTED | 2019-03-12 | 2019-03-15 | 2019-03-15 | 2019-03-17 | NA | NA | 2019-05-02 | 2019-05-16 | 2019-05-16 | 2019-05-16 | 2019-06-13 | 2019-06-13 | NA | NA | 0 | 2019-08-06 | 2019-08-27 | 2019-06-16 | 18.1992 | 42.5103 | 2019-05-22 | 2019-05-22 | 35M-LP-GF | 20X20 | 2019-08-27 | Non-Private | Baladiya | Asir Municipality | 4000111 | 50000 | 400 | GF | Mohammed elshehry | HOC
ZAB381 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2019 | 18.2195 | 42.5906 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 27/04/2019 17:20:29 | SNR1009738 | NOBODY | ACCEPTED | 2019-03-13 | 2019-03-16 | 2019-03-16 | 2019-03-18 | NA | NA | 2019-05-02 | 2019-05-16 | 2019-05-16 | 2019-05-16 | 2019-06-13 | 2019-06-13 | NA | NA | 0 | 2019-08-06 | 2019-08-27 | 2019-06-16 | 18.2196 | 42.5906 | 2019-05-22 | 2019-05-22 | 35M-LP-GF | 20X20 | 2019-08-27 | Non-Private | Baladiya | Asir Municipality | 4000105 | 30000 | 400 | GF | Mohammed elshehry | HOC
ZAB382 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2020 | 18.2411 | 42.4732 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 24/04/2019 10:05:53 | SNR1009695 | NOBODY | ACCEPTED | 2019-03-19 | 2019-03-22 | 2019-03-22 | 2019-03-24 | 16/10/2019 14:37:39 | 17/10/2019 17:03:30 | NA | NA | NA | NA | NA | NA | 2019-11-21 | 2019-11-24 | 0 | 2019-10-30 | 2019-11-20 | 2019-09-26 | 18.2411 | 42.4732 | 2019-09-22 | 2019-09-22 | 36m-E4-GF | 20X20 | 2019-11-10 | Private | Private | محمد حمدان مداوي | 555757979 | 30000 | 400M | GF | Mohammed elshehry | HOC
ZAB383 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2019 | 18.2749 | 42.6122 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 27/04/2019 17:25:34 | SNR1009739 | NOBODY | ACCEPTED | 2019-03-13 | 2019-03-16 | 2019-03-16 | 2019-03-18 | NA | NA | 2019-05-02 | 2019-05-16 | 2019-05-16 | 2019-05-16 | 2019-06-13 | 2019-06-13 | NA | NA | 0 | 2019-07-15 | 2019-08-05 | 2019-05-29 | 18.275 | 42.6122 | 2019-05-22 | 2019-05-22 | 35M-LP-GF |  | 2019-08-19 | Non-Private | Baladiya | Asir Municipality | 4000104 | 30000 | 400 | GF | Mohammed elshehry | HOC
ZAB384 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2020 | 18.2389 | 42.5332 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 27/04/2019 17:34:16 | SNR1009740 | NOBODY | ACCEPTED | 2019-03-11 | 2019-03-14 | 2019-03-14 | 2019-03-16 | NA | NA | 2019-05-02 | 2019-05-16 | 2019-05-16 | 2019-05-16 | 2019-06-13 | 2019-06-13 | NA | NA | 0 | 2019-09-24 | 2019-10-15 | 2019-09-26 | 18.2389 | 42.5332 | 2019-05-22 | 2019-05-22 | 35m-MP-GF | 18X18 | 2019-10-15 | Non-Private | Baladiya | Asir Municipality | 4000112 | 30000 | 400 | GF | Mohammed elshehry | HOC
ZAB386 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2020 | 18.2488 | 42.5838 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 25/04/2019 16:09:31 | SNR1009725 | SNR_I | District Support | 2019-03-24 | 2019-03-27 | 2019-03-27 | 2019-03-29 | NA | NA | 2019-10-24 | 2020-12-17 | 2020-12-17 | 2020-12-17 | 2021-03-09 | 2021-03-09 | NA | NA | 0 | 2020-06-25 | 2020-06-25 | 2020-02-23 | 18.2488 | 42.5838 | 2020-02-26 | 2020-03-03 | 40m-PT-GF | 7X7 | 2020-06-25 | Non-Private | GOV | شركة الكهرباء عسير |  | Free | 7X7 | GF | Mohammed elshehry | HOC
ZAB388 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2020 | 18.2243 | 42.6417 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 24/04/2019 10:20:21 | SNR1009696 | NOBODY | ACCEPTED | 2019-03-17 | 2019-03-20 | 2019-03-20 | 2019-03-22 | 02/05/2019 13:39:43 | 14/05/2019 15:34:20 | NA | NA | NA | NA | NA | NA | 2019-05-01 | 2019-05-09 | 0 | 2019-06-11 | 2019-07-02 | 2019-04-28 | 18.2243 | 42.6417 | 2019-04-24 | 2019-04-24 | 35m-MP-GF |  | 2019-07-03 | Private | Private | زينة عبد الله لاحق | 555752290 | 35000 | 624M | GF | Mohammed elshehry | HOC
ZAB393 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2020 | 18.2524 | 42.4703 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 27/04/2019 17:40:05 | SNR1009741 | NOBODY | ACCEPTED | 2019-03-17 | 2019-03-14 | 2019-03-14 | 2019-03-16 | NA | NA | 2019-05-02 | 2019-05-16 | 2019-05-16 | 2019-05-16 | 2019-06-13 | 2019-06-13 | NA | NA | 0 | 2019-10-17 | 2019-11-07 | 2019-07-09 | 18.2524 | 42.4703 | 2019-05-22 | 2019-05-22 | 45M-E4-GF |  | 2019-11-06 | Non-Private | Baladiya | امانة عسير | 4000113 | 30000 | 400 | GF | Mohammed elshehry | HOC
ZAB417 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2019 | 18.2168 | 42.5399 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 30/04/2019 12:59:03 | SNR1009919 | NOBODY | ACCEPTED | 2019-03-17 | 2019-03-20 | 2019-03-20 | 2019-03-22 | NA | NA | 2019-05-02 | 2019-05-16 | 2019-05-16 | 2019-05-16 | 2019-06-13 | 2019-06-13 | NA | NA | 0 | 2019-08-06 | 2019-08-27 | 2019-06-16 | 18.2168 | 42.5399 | 2019-05-22 | 2019-05-22 | 35M-LP-GF | 20X20 | 2019-08-27 | Non-Private | Baladiya | Asir Municipality | 4000109 | 30000 | 400 | GF | Mohammed elshehry | HOC
ZAB426 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2019 | 18.2838 | 42.6003 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 27/04/2019 17:55:52 | SNR1009742 | NOBODY | ACCEPTED | 2019-03-18 | 2019-03-21 | 2019-03-21 | 2019-03-23 | NA | NA | 2019-05-02 | 2019-05-16 | 2019-05-16 | 2019-05-16 | 2019-06-13 | 2019-06-13 | NA | NA | 0 | 2019-08-06 | 2019-08-27 | 2019-05-29 | 18.2838 | 42.6003 | 2019-05-22 | 2019-05-22 | 45M-E4-GF | 20X20 | 2019-08-27 | Non-Private | Baladiya | Asir Municipality | 4000106 | 30000 | 400 | GF | Mohammed elshehry | HOC
ZAB416 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2019 | 18.2301 | 42.599 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 19/05/2019 14:51:18 | SNR1010296 | NOBODY | ACCEPTED | 2019-04-21 | 2019-04-24 | 2019-04-24 | 2019-04-26 | NA | NA | 2019-05-02 | 2019-05-16 | 2019-05-16 | 2019-05-16 | 2019-06-19 | 2019-06-19 | NA | NA | 0 | 2019-08-06 | 2019-08-27 | 2019-08-19 | 18.2301 | 42.5991 | 2019-07-11 | 2019-07-11 | 35M-LP-GF | 20X20 | 2019-08-27 | Non-Private | Baladiya | Asir Municipality | 4000116 | 30000 | 400 | GF | Mohammed elshehry | HOC
ZAB430 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2019 | 18.2345 | 42.4935 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 27/04/2019 18:00:02 | SNR1009743 | NOBODY | ACCEPTED | 2019-03-10 | 2019-03-13 | 2019-03-13 | 2019-03-15 | NA | NA | 2019-05-02 | 2019-05-16 | 2019-05-16 | 2019-05-16 | 2019-06-13 | 2019-06-13 | NA | NA | 0 | 2019-09-17 | 2019-10-08 | 2019-05-29 | 18.2345 | 42.4935 | 2019-05-22 | 2019-05-22 | 35m-LP-GF | 20X20 | 2019-10-15 | Non-Private | Baladiya | Asir Municipality | 4000103 | 30000 | 400 | GF | Mohammed elshehry | HOC
ZAB673 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2019 | 18.2039 | 42.5065 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 17/06/2019 18:30:05 | SNR1010634 | NOBODY | ACCEPTED | 2019-06-14 | 2019-06-17 | 2019-06-17 | 2019-06-19 | NA | NA | 2019-10-10 | 2019-10-20 | 2019-10-20 | 2019-10-20 | 2019-11-20 | 2019-11-20 | NA | NA | 0 | 2019-11-24 | 2019-12-30 | 2019-11-21 | 18.2036 | 42.5073 | 2019-11-11 | 2019-12-09 | 35m-PT-Sharable | 400M | 2019-11-24 | Non-Private | Baladiya | امانة عسير | 4100107 | 50000 | 400 | GF | Mohammed elshehry | HOC
ZAB437 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2019 | 18.2511 | 42.6239 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 27/04/2019 18:04:58 | SNR1009744 | NOBODY | ACCEPTED | 2019-03-18 | 2019-03-21 | 2019-03-21 | 2019-03-23 | NA | NA | 2019-05-02 | 2019-05-16 | 2019-05-16 | 2019-05-16 | 2019-06-13 | 2019-06-13 | NA | NA | 0 | 2019-07-09 | 2019-07-30 | 2019-07-07 | 18.2511 | 42.6239 | 2020-02-03 | 2019-05-22 | 35m-Holly Name |  | 2019-07-31 | Non-Private | Baladiya | Asir Municipality | 4000107 | 30000 | 400 | GF | Mohammed elshehry | HOC
ZAB691 | Macro | Aspiration | Pending FBP | FBP Not Issued | Assir | 2019 | 18.2054 | 42.5177 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 17/06/2019 18:24:47 | SNR1010633 | NOBODY | ACCEPTED | 2019-07-22 | 2019-07-25 | 2019-07-25 | 2019-07-27 | NA | NA | 2019-11-01 | 2019-12-09 | 2019-12-12 | 2019-12-12 | 2019-12-22 | 2019-12-24 | NA | NA | 0 | 2019-12-24 |  | 2019-11-02 | 18.2056 | 42.5177 | 2019-09-29 | 2019-09-29 | 35m-Holly Name | 9X9 | 2020-01-21 | Non-Private | Baladiya | امانة عسير | 4100112 | 50000 | 81M | GF | Mohammed elshehry | HOC
ZAB438 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2019 | 18.2403 | 42.5589 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 27/04/2019 18:09:56 | SNR1009745 | NOBODY | ACCEPTED | 2019-03-19 | 2019-03-22 | 2019-03-22 | 2019-03-24 | NA | NA | 2019-05-02 | 2019-05-16 | 2019-05-16 | 2019-05-16 | 2019-06-13 | 2019-06-13 | NA | NA | 0 | 2019-09-17 | 2019-10-08 | 2019-05-29 | 18.2403 | 42.5589 | 2019-05-22 | 2019-05-22 | 36m-E4-GF | 18x18 | 2019-10-13 | Non-Private | Baladiya | Asir Municipality | 4000108 | 30000 | 400 | GF | Mohammed elshehry | HOC
ZAB481 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2020 | 18.2836 | 42.589 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 27/04/2019 18:15:07 | SNR1009746 | NOBODY | ACCEPTED | 2019-03-19 | 2019-03-22 | 2019-03-22 | 2019-03-24 | NA | NA | 2019-05-02 | 2019-05-16 | 2019-05-16 | 2019-05-16 | 2019-06-13 | 2019-06-13 | NA | NA | 0 | 2019-07-15 | 2019-08-05 | 2019-05-29 | 18.2837 | 42.5891 | 2019-05-22 | 2019-05-22 | 45M-E4-GF | 20x20 | 2019-08-05 | Non-Private | Baladiya | Asir Municipality | 4000114 | 30000 | 400 | GF | Mohammed elshehry | HOC
ZAB634 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2020 | 18.2731 | 42.5478 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 27/04/2019 18:21:39 | SNR1009747 | NOBODY | ACCEPTED | 2019-03-19 | 2019-03-22 | 2019-03-22 | 2019-03-24 | NA | NA | 2019-05-02 | 2019-05-16 | 2019-05-16 | 2019-05-16 | 2019-06-13 | 2019-06-13 | NA | NA | 0 | 2019-09-17 | 2019-10-08 | 2019-05-29 | 18.2731 | 42.5478 | 2019-05-22 | 2019-05-22 | 60m-E4-GF | 20X20 | 2019-10-14 | Non-Private | Baladiya | Asir Municipality | 4000115 | 30000 | 400 | GF | Mohammed elshehry | HOC
ZAB754 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2020 | 18.2346 | 42.6178 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 25/04/2019 16:43:10 | SNR1009726 | NOBODY | ACCEPTED | 2019-03-20 | 2019-03-23 | 2019-03-23 | 2019-03-25 | 22/05/2019 00:39:10 | 24/06/2019 11:03:26 | NA | NA | NA | NA | NA | NA | 2019-07-07 | 2019-07-07 | 0 | 2019-09-23 | 2019-10-14 | 2019-07-14 | 18.2346 | 42.6179 | 2019-07-07 | 2019-07-07 | 45M-E4-GF | 20X20 | 2019-10-14 | Private | Private | فيصل القحطاني | 558299288 | 30000 | 400M | GF | Mohammed elshehry | HOC
ZBA987 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2020 | 18.7349 | 42.2612 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 25/04/2019 16:58:24 | SNR1009727 | NOBODY | ACCEPTED | 2019-03-23 | 2019-03-26 | 2019-03-26 | 2019-03-28 | NA | NA | 2019-06-23 | 2019-07-07 | 2019-07-07 | 2019-07-07 | 2019-08-16 | 2019-08-16 | NA | NA | 0 | 2019-10-02 | 2019-10-23 | 2019-08-22 | 18.7349 | 42.2612 | 2019-07-08 | 2019-07-08 | 45M-E4-GF | 20X20 | 2019-10-23 | Non-Private | Baladiya | Billsmar Municipality | 2\20 | 30000 | 400 | GF | Mohammed elshehry | HOC
ZBH589 | Macro | Aspiration | Pending FBP | FBP Not Issued | Baha | 2019 | 20.0147 | 41.4763 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 27/04/2019 18:27:36 | SNR1009748 | SNR_I | District Support | 2019-04-27 | 2019-04-27 | 2019-04-27 | 2019-04-27 | NA | NA | 2020-01-09 | 2020-07-07 | 2020-07-07 | 2020-07-09 | 2020-07-16 | 2020-08-19 | NA | NA | 0 | 2020-08-19 |  | 2020-08-18 | 20.0156 | 41.4753 | 2020-08-18 | 2020-08-18 | 45m-E4-GF |  | 2020-08-18 | Non-Private | Baladiya | امانة الباحة |  |  | 15x15 | GF | Fahad Alrogy | HOC
ZKH549 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2020 | 18.2358 | 42.7731 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 30/04/2019 14:45:34 | SNR1009953 | NOBODY | ACCEPTED | 2019-03-12 | 2019-03-15 | 2019-03-15 | 2019-03-17 | 06/10/2019 09:51:23 | 13/10/2019 13:45:41 | NA | NA | NA | NA | NA | NA | 2019-10-20 | 2019-10-26 | 0 | 2019-10-26 | 2019-12-16 | 2019-07-09 | 18.2358 | 42.7731 | 2019-07-08 | 2019-07-08 | 45m-E4-GF | 400M | 2019-11-17 | Private | Private | سعيد حسين مليح | 504736684 | 30000 | 400M | GF | Mohammed elshehry | HOC
ZKH692 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2020 | 18.2167 | 42.8917 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 01/05/2019 15:17:10 | SNR1010012 | NOBODY | ACCEPTED | 2019-03-21 | 2019-03-24 | 2019-03-24 | 2019-03-26 | 14/07/2019 12:29:21 | 14/07/2019 14:03:02 | NA | NA | NA | NA | NA | NA | 2019-08-01 | 2019-08-05 | 0 | 2019-08-05 | 2019-12-16 | 2019-09-05 | 18.2167 | 42.8917 | 2019-07-22 | 2019-07-22 | 60m-E4-GF |  | 2019-11-10 | Private | Private | سالم ناصر القحطاني | 555848814 | 26000 | 400M | GF | Mohammed elshehry | HOC
ZBS327 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2020 | 20.0118 | 42.5961 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 28/04/2019 14:42:33 | SNR1009765 | NOBODY | ACCEPTED | 2019-03-19 | 2019-03-22 | 2019-03-22 | 2019-03-24 | 26/05/2019 13:41:49 | 22/06/2019 18:50:23 | NA | NA | NA | NA | NA | NA | 2019-05-22 | 2019-07-07 | 0 | 2019-06-26 | 2019-07-17 | 2019-07-09 | 20.0118 | 42.5961 | 2019-07-07 | 2019-07-07 | 45M-E4-GF |  | 2019-07-21 | Private | Private | عامرعبالله محمد كركمان | 557669090 | 20000 | 400M | GF | Mohammed elshehry | HOC
ZKH661 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2020 | 18.3749 | 42.8238 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 31/10/2019 09:22:11 | SNR1012276 | NOBODY | ACCEPTED | 2019-03-16 | 2019-03-19 | 2019-03-19 | 2019-03-21 | 06/05/2019 11:29:05 | 12/05/2019 12:36:34 | NA | NA | NA | NA | NA | NA | 2019-08-12 | 2019-08-19 | 0 | 2019-08-19 | 2019-12-16 | 2019-11-02 | 18.375 | 42.8239 | 2019-10-14 | 2019-10-14 | 60m-E4-GF | 20X20 | 2019-11-17 | Private | Private | عون عبدالله الشهراني | 555238505 | 28000 | 400M | GF | Mohammed elshehry | HOC
ZBS344 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2020 | 19.9349 | 42.5996 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 01/05/2019 16:11:23 | SNR1010017 | SNR_I | District Support | 2019-03-19 | 2019-03-22 | 2019-03-22 | 2019-03-24 | NA | NA | 2019-04-25 | 2019-05-09 | 2020-05-03 | 2020-05-03 | 2020-06-15 | 2020-06-29 | NA | NA | 0 | 2020-06-29 | 2020-07-06 | 2019-06-16 | 19.9349 | 42.5996 | 2020-02-26 | 2020-02-27 | 45m-E4-GF | 20X20 | 2020-07-02 | Non-Private | Baladiya | بلدية بيشة | 535 | 50000 | 20X20 | GF | Mohammed elshehry | HOC
ZDJ974 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2020 | 17.6711 | 43.5044 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 24/04/2019 15:43:30 | SNR1009699 | NOBODY | ACCEPTED | 2019-03-17 | 2019-03-20 | 2019-03-20 | 2019-03-22 | NA | NA | 2019-04-14 | 2020-01-12 | 2020-01-12 | 2020-01-19 | 2020-02-12 | 2020-02-19 | NA | NA | 0 | 2020-03-01 | 2020-04-06 | 2020-04-07 | 17.6711 | 43.5044 | 2020-04-08 | 2020-04-07 | 60m-E4-GF | 20X20 | 2020-04-08 | Non-Private | Baladiya | بلدية ظهران الجنوب | 550 | 30000 | 400M | GF | Mohammed elshehry | HOC
ZBS346 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2019 | 20.0241 | 42.6076 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 30/04/2019 14:38:53 | SNR1009952 | NOBODY | ACCEPTED | 2019-03-19 | 2019-03-22 | 2019-03-22 | 2019-03-24 | 16/10/2019 14:41:24 | 17/10/2019 12:02:07 | NA | NA | NA | NA | NA | NA | 2019-10-24 | 2019-10-30 | 0 | 2019-04-24 | 2019-11-26 | 2019-10-23 | 20.0241 | 42.6076 | 2019-09-29 | 2019-09-29 | 45M-E4-GF | 20X20 | 2019-11-10 | Private | Private | عمير شاراع ظافر الشهراني | 503667036 | 20000 | 400M | GF | Mohammed elshehry | HOC
ZKH547 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2020 | 18.2989 | 42.6322 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 19/05/2019 15:23:28 | SNR1010297 | NOBODY | ACCEPTED | 2019-03-25 | 2019-03-28 | 2019-03-28 | 2019-03-30 | NA | NA | 2019-07-24 | 2019-08-07 | 2019-08-07 | 2019-08-07 | 2019-09-18 | 2019-09-18 | NA | NA | 0 | 2019-10-13 | 2019-11-03 | 2019-10-23 | 18.2989 | 42.6322 | 2019-09-29 | 2019-09-07 | 45m-E4-GF | 20X20 | 2019-11-03 | Non-Private | Baladiya | بلدية خميس مشيط | 4000124 | 30000 | 400 | GF | Mohammed elshehry | HOC
ZKH551 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2019 | 18.2051 | 42.8045 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 17/06/2019 18:22:15 | SNR1010632 | NOBODY | ACCEPTED | 2019-06-14 | 2019-06-17 | 2019-06-17 | 2019-06-19 | NA | NA | 2019-11-11 | 2019-11-10 | 2019-11-10 | 2019-11-20 | 2019-11-20 | 2019-11-28 | NA | NA | 0 | 2019-12-01 | 2019-12-01 | 2019-11-03 | 18.2051 | 42.8045 | 2019-11-03 | 2019-11-03 | 40m-PT-Sharable | 400M | 2019-12-01 | Non-Private | GOV | قاعدة الملك فيصل الجويه | 1441 | 40000 | 400 | GF | Mohammed elshehry | HOC
ZKH560 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2020 | 18.185 | 42.8763 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 25/04/2019 17:43:37 | SNR1009729 | NOBODY | ACCEPTED | 2019-03-03 | 2019-03-06 | 2019-03-06 | 2019-03-08 | NA | NA | 2019-11-13 | 2019-12-10 | 2019-12-26 | 2020-02-05 | 2020-02-12 | 2020-02-19 | NA | NA | 0 | 2020-02-19 | 2020-03-12 | 2020-01-09 | 18.185 | 42.8763 | 2020-01-13 | 2020-02-18 | 45m-E4-GF |  | 2020-03-26 | Non-Private | Baladiya | بلدية احد رفيده | NA | 33750 | 225 | GF | Mohammed elshehry | HOC
ZKH553 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2019 | 18.177 | 42.8211 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 07/05/2019 13:53:00 | SNR1010143 | NOBODY | ACCEPTED | 2019-03-03 | 2019-03-06 | 2019-03-06 | 2019-03-08 | 26/05/2019 16:07:33 | 28/05/2019 15:08:13 | [6 empty] | 2019-07-07 | 2019-07-07 | 0 | 2019-07-03 | 2019-07-24 | 2019-07-09 | 18.177 | 42.8211 | 2019-07-07 | 2019-07-07 | 45M-E4-GF | 20X20 | 2019-07-25 | Private | Private | مبارك علي الشهري | 503758846 | 30000 | 400M | GF | Mohammed elshehry | HOC | bar: 2019-11-13 to 2020-02-19
ZKH556 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2020 | 18.3371 | 42.7662 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 28/04/2019 16:01:29 | SNR1009773 | NOBODY | ACCEPTED | 2019-03-17 | 2019-03-20 | 2019-03-20 | 2019-03-22 | NA | NA | 2019-04-10 | 2019-04-24 | 2019-04-24 | 2019-04-24 | 2019-06-13 | 2019-06-13 | NA | NA | 0 | 2019-07-01 | 2019-07-22 | 2019-05-13 | 18.3371 | 42.7662 | 2019-05-01 | 2019-05-01 | 45M-E4-GF | 20X20 | 2019-07-23 | Non-Private | Baladiya | Khamis Moshit Municipality | STC-ZKH-556 | 40000 | 400 | GF | Mohammed elshehry | HOC
ZKH564 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2019 | 18.3282 | 42.7762 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 29/04/2019 16:06:42 | SNR1009817 | NOBODY | ACCEPTED | 2019-03-09 | 2019-03-12 | 2019-03-12 | 2019-03-14 | 18/06/2019 17:28:33 | 19/06/2019 12:01:08 | [6 empty] | 2019-05-22 | 2019-05-22 | 0 | 2019-06-11 | 2019-07-02 | 2019-05-02 | 18.3281 | 42.7763 | 2019-05-01 | 2019-05-01 | 45M-E4-GF | 20X20 | 2019-07-03 | Private | Private | صالح العمري | NA | 37000 | 400 | GF | Mohammed elshehry | HOC | bar: 2019-11-13 to 2020-02-19
ZKH585 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2020 | 18.32 | 42.6857 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 01/05/2019 09:40:38 | SNR1009986 | NOBODY | ACCEPTED | 2019-03-19 | 2019-03-22 | 2019-03-22 | 2019-03-24 | NA | NA | 2019-04-10 | 2019-04-24 | 2019-04-24 | 2019-04-24 | 2019-06-13 | 2019-06-13 | NA | NA | 0 | 2019-07-01 | 2019-07-22 | 2019-07-14 | 18.32 | 42.6857 | 2019-07-02 | 2019-07-02 | 45M-E4-GF | 20X20 | 2019-07-23 | Non-Private | Baladiya | Khamis Moshit Municipality | STC-ZKH-585 | 40000 | 400 | GF | Mohammed elshehry | HOC
ZKH610 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2020 | 18.3182 | 42.6574 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 19/05/2019 15:42:36 | SNR1010299 | NOBODY | ACCEPTED | 2019-04-11 | 2019-04-14 | 2019-04-14 | 2019-04-16 | NA | NA | 2019-06-18 | 2019-07-02 | 2019-07-02 | 2019-07-02 | 2019-06-10 | 2019-06-10 | NA | NA | 0 | 2019-06-10 | 2019-11-26 | 2019-09-17 | 18.3182 | 42.6574 | 2019-07-08 | 2019-07-08 | 60m-E4-GF | 20X20 | 2019-11-10 | Non-Private | Baladiya | بلدية خميس مشيط | ZKH610 | 40000 | 400 | GF | Mohammed elshehry | HOC
ZKH576 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2020 | 18.1292 | 42.786 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 01/05/2019 15:00:00 | SNR1010010 | NOBODY | ACCEPTED | 2019-03-03 | 2019-03-06 | 2019-03-06 | 2019-03-08 | NA | NA | 2019-08-25 | 2019-09-08 | 2019-09-08 | 2019-09-08 | 2019-09-16 | 2019-09-16 | NA | NA | 0 | 2019-10-03 | 2019-10-24 | 2019-10-02 | 18.1292 | 42.786 | 2019-09-29 | 2019-09-29 | 60m-E4-GF | 18x18 | 2019-10-27 | Non-Private | Baladiya | Al Wadeen Municipality | 576 - أج | 30132 | 324 | GF | Mohammed elshehry | HOC
ZKH578 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2020 | 18.3712 | 42.7028 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 24/04/2019 15:15:25 | SNR1009698 | NOBODY | ACCEPTED | 2019-03-04 | 2019-03-07 | 2019-03-07 | 2019-03-09 | 02/05/2019 13:45:33 | 12/05/2019 13:31:31 | [6 empty] | 2019-05-02 | 2019-05-09 | 0 | 2019-05-19 | 2019-06-09 | 2019-05-22 | 18.3712 | 42.7028 | 2019-05-20 | 2019-05-20 | 45M-E4-GF | 20X20 | 2019-06-10 | Private | Private | يحى مفرح معض الكاسئ | 503732421 | 29000 | 400M | GF | Mohammed elshehry | HOC | bar: 2019-11-13 to 2020-02-19
ZKH616 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2019 | 18.2694 | 42.764 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 19/05/2019 17:07:29 | SNR1010302 | NOBODY | ACCEPTED | 2019-04-30 | 2019-05-03 | 2019-05-03 | 2019-05-05 | 21/07/2019 14:08:47 | 28/07/2019 11:59:28 | [6 empty] | 2019-08-09 | 2019-08-18 | 0 | 2019-11-10 | 2019-11-24 | 2019-07-01 | 18.2695 | 42.764 | 2019-05-28 | 2019-05-28 | 45M-E4-GF | 20X20 | 2019-11-17 | Private | Private | ناصر سفر الشهراني | 557733522 | 30000 | 400M | GF | Mohammed elshehry | HOC | bar: 2019-11-13 to 2020-02-19
ZJZ071 | Macro | Aspiration | Pending FBP | FBP Not Issued | Makkah | 2019 | 19.146 | 41.0733 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 05/05/2019 16:38:53 | SNR1010076 | NOBODY | ACCEPTED | 2019-03-19 | 2019-03-19 | 2019-12-15 | 2019-12-15 | NA | NA | 2019-12-15 | 2020-12-31 | 2020-12-31 | 2020-02-05 | 2020-02-19 | 2020-03-12 | NA | NA | 1969 | 2020-03-12 |  | 2020-01-02 | 19.1447 | 41.0738 | 2020-02-11 | 2020-01-23 | 45m-E4-GF |  | 2020-07-02 | Non-Private | Baladiya | بلدية القنفذه | 07\41 | 40000 | 15x15 | GF | Adnan Alqorashy | HOC
ZKH618 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2019 | 18.246 | 42.743 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 17/06/2019 18:19:02 | SNR1010631 | NOBODY | ACCEPTED | 2019-11-26 | 2019-11-26 | 2019-11-26 | 2019-11-26 | 2019-11-27 | 2019-11-27 | [6 empty] | 2019-12-16 | 2019-12-24 | 0 | 2019-12-24 | 2020-07-27 | 2020-01-02 | 18.246 | 42.7431 | 2020-01-01 | 2020-01-06 | 45m-E4-GF | 20X20 | 2020-01-21 | Private | Private | حميدي محمد سعد شلوان | 555741331 | 30000 | 400M | GF | Mohammed elshehry | HOC | bar: 2019-11-13 to 2020-02-19
ZKH581 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2020 | 18.3515 | 42.7092 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 24/04/2019 10:34:51 | SNR1009697 | NOBODY | ACCEPTED | 2019-03-19 | 2019-03-22 | 2019-03-22 | 2019-03-24 | NA | NA | 2019-04-10 | 2019-04-24 | 2019-04-24 | 2019-04-24 | 2019-06-13 | 2019-06-13 | NA | NA | 0 | 2019-07-01 | 2019-07-22 | 2019-05-02 | 18.3514 | 42.7093 | 2019-05-01 | 2019-05-01 | 45M-E4-GF | 20X20 | 2019-07-23 | Non-Private | Baladiya | Khamis Moshit Municipality | STC-ZKH-581 | 40000 | 400 | GF | Mohammed elshehry | HOC
ZKH691 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2020 | 18.1018 | 42.8108 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 21/05/2019 01:18:41 | SNR1010306 | NOBODY | ACCEPTED | 2019-04-23 | 2019-04-26 | 2019-04-26 | 2019-04-28 | NA | NA | 2019-08-25 | 2019-09-08 | 2019-09-08 | 2019-09-08 | 2019-09-16 | 2019-09-16 | NA | NA | 0 | 2019-10-03 | 2019-10-24 | 2019-07-14 | 18.1018 | 42.8108 | 2019-07-08 | 2019-07-08 | 60m-E4-GF | 18x18 | 2019-10-21 | Non-Private | Baladiya | بلدية خميس مشيط | 691-2 | 30132 | 324 | GF | Mohammed elshehry | HOC
ZMC086 | Macro | Aspiration | HOC | HO to CW Done | Makkah | 2019 | 22.6319 | 39.0479 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 17/06/2019 12:34:02 | SNR1010578 | NOBODY | ACCEPTED | 2019-06-14 | 2019-06-17 | 2019-06-17 | 2019-06-19 | NA | NA | 2019-06-26 | 2020-03-08 | 2020-03-08 | 2020-03-08 | 2020-03-12 | 2020-03-08 | NA | NA | 0 | 2020-03-12 | 2020-03-12 | 2020-01-02 | 22.6319 | 39.0479 | 2020-01-19 | 2020-02-23 | 60m-E4-GF |  | 2020-03-12 | Non-Private | GOV | شركة كهرباء رابغ | NA | 40000 | 20X20 | GF | Adnan Alqorashy | HOC
ZKH609 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2020 | 18.3318 | 42.6877 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 05/05/2019 18:09:07 | SNR1010081 | NOBODY | ACCEPTED | 2019-03-04 | 2019-03-07 | 2019-03-07 | 2019-03-09 | NA | NA | 2019-05-02 | 2019-05-16 | 2019-05-16 | 2019-05-16 | 2019-06-13 | 2019-06-13 | NA | NA | 0 | 2019-07-01 | 2019-07-22 | 2019-06-11 | 18.3318 | 42.6877 | 2019-05-28 | 2019-05-28 | 45M-E4-GF | 20X20 | 2019-07-23 | Non-Private | Baladiya | Assir Municipality | STC-ZKH609 | 40000 | 400 | GF | Mohammed elshehry | HOC
ZMH228 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2019 | 18.559 | 42.0747 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 30/01/2020 10:04:00 | SNR1012650 | NOBODY | ACCEPTED | 2019-03-30 | 2019-03-30 | 2019-03-30 | 2019-03-30 | 2019-03-30 | 2019-06-09 | [6 empty] | 2019-07-14 | 2019-07-18 | 0 | 2019-09-19 | 2019-10-10 | 2019-07-01 | 18.559 | 42.0747 | 2019-05-28 | 2019-05-28 | 60m-E4-GF | 20X20 | 2019-10-14 | Private | Private | حسن ابراهيم ال مفطر | 504541448 | 30000 | 400M | GF | Mohammed elshehry | HOC | bar: 2019-11-13 to 2020-02-19
ZKH612 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2019 | 18.2872 | 42.6962 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 25/04/2019 17:37:42 | SNR1009728 | NOBODY | ACCEPTED | 2019-03-14 | 2019-03-17 | 2019-03-17 | 2019-03-19 | NA | NA | 2019-06-13 | 2019-06-27 | 2019-06-27 | 2019-06-27 | 2019-07-23 | 2019-07-23 | NA | NA | 0 | 2019-10-07 | 2019-10-28 | 2019-05-02 | 18.2872 | 42.6962 | 2019-05-01 | 2019-05-01 | 45M-E4-GF | 20X20 | 2019-10-28 | Non-Private | Baladiya | Khamis Moshit Municipality | STC-ZKH-612 | 40000 | 400 | GF | Mohammed elshehry | HOC
ZKH555 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2020 | 18.1005 | 43.1305 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 05/05/2019 18:00:00 | SNR1010080 | NOBODY | ACCEPTED | 2019-03-28 | 2019-03-31 | 2019-04-02 | 2019-04-02 | 26/08/2019 09:56:47 | 08/09/2019 10:41:59 | [6 empty] | 2020-02-04 | 2020-02-20 | 0 | 2020-02-20 | 2020-03-05 | 2019-11-18 | 18.1005 | 43.1305 | 2020-02-10 | 2020-02-12 | 60m-E4-GF | 20X20 | 2020-03-08 | Private | Private | حسين القحطاني | 557170324 | 30000 | 400M | GF | Mohammed elshehry | HOC | bar: 2019-11-13 to 2020-02-19
ZKH614 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2020 | 18.306 | 42.7558 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 25/04/2019 17:56:56 | SNR1009731 | NOBODY | ACCEPTED | 2019-03-14 | 2019-03-17 | 2019-03-17 | 2019-03-19 | NA | NA | 2019-04-10 | 2019-04-24 | 2019-04-24 | 2019-04-24 | 2019-06-13 | 2019-06-13 | NA | NA | 0 | 2019-07-01 | 2019-07-22 | 2019-05-13 | 18.306 | 42.7558 | 2019-05-01 | 2019-05-01 | 35m-Camouflage/Palm tree | 20X20 | 2019-07-23 | Non-Private | Baladiya | Khamis Moshit Municipality | STC-ZKH-614 | 40000 | 400 | GF | Mohammed elshehry | HOC
ZMH231 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2019 | 18.5127 | 42.0385 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 17/06/2019 18:15:54 | SNR1010630 | SNR_I | District Support | 2019-06-13 | 2019-06-16 | 2019-06-16 | 2019-06-16 | 2020-08-10 | 2020-08-10 | [6 empty] | 2020-08-10 | 2020-08-10 | 0 | 2020-08-10 | 2020-10-19 | 2019-07-09 | 18.5112 | 42.038 | 2020-09-20 | 2020-09-20 | 45m-E4-GF | 20X20 | 2020-09-30 | Private | Private | محمد عسيري | 555996505 | 45000 | 400 | GF | Mohammed elshehry | HOC | bar: 2019-11-13 to 2020-02-19
ZKH619 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2019 | 18.238 | 42.8017 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 25/04/2019 18:04:20 | SNR1009732 | NOBODY | ACCEPTED | 2019-03-05 | 2019-03-08 | 2019-03-08 | 2019-03-10 | NA | NA | 2019-04-10 | 2019-04-24 | 2019-04-24 | 2019-04-24 | 2019-06-13 | 2019-06-13 | NA | NA | 0 | 2019-07-01 | 2019-07-22 | 2019-05-02 | 18.238 | 42.8017 | 2019-05-01 | 2019-05-01 | 45M-E4-GF | 20X20 | 2019-07-23 | Non-Private | Baladiya | Khamis Moshit Municipality | STC-ZKH-619 | 40000 | 400 | GF | Mohammed elshehry | HOC
ZTF319 | Macro | Aspiration | Pending FBP | FBP Not Issued | Taif | 2020 | 21.5248 | 40.5073 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 17/06/2019 18:05:50 | SNR1010628 | SNR_I | District Support | 2019-06-17 | 2019-06-17 | 2019-12-12 | 2019-12-12 | NA | NA | 2019-12-15 | 2020-06-18 | 2020-06-18 | 2020-06-24 | 2020-09-01 | 2020-09-06 | NA | NA | 0 | 2020-09-10 |  | 2020-02-17 | 21.5248 | 40.5073 | 2020-02-19 | 2020-02-17 | 60m-E4-GF |  | 2020-06-24 | Non-Private | Baladiya | امانة الطائف |  |  |  | GF | Fahad Alrogy | HOC
ZKH540 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2020 | 18.3435 | 42.7527 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 19/10/2019 12:57:15 | SNR1012144 | NOBODY | ACCEPTED | 2019-09-18 | 2019-09-21 | 2019-09-21 | 2019-09-23 | NA | NA | 2019-11-10 | 2019-11-17 | 2019-11-17 | 2019-11-17 | 2019-11-17 | 2019-11-20 | NA | NA | 0 | 2019-11-21 | 2019-12-09 | 2019-11-02 | 18.3435 | 42.7527 | 2019-10-14 | 2019-10-14 | 45M-E4-GF | 20X20 | 2019-11-17 | Non-Private | Baladiya | بلدية خميس مشيط | ZKH540 | 40000 | 400 | GF | Mohammed elshehry | HOC
ZKH654 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2020 | 18.3116 | 42.6883 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 28/04/2019 15:51:06 | SNR1009772 | NOBODY | ACCEPTED | 2019-03-04 | 2019-03-07 | 2019-03-07 | 2019-03-09 | NA | NA | 2019-04-10 | 2019-04-24 | 2019-04-24 | 2019-04-24 | 2019-06-13 | 2019-06-13 | NA | NA | 0 | 2019-07-01 | 2019-07-22 | 2019-05-13 | 18.3116 | 42.6883 | 2019-05-01 | 2019-05-01 | 35M-LP-GF | 20X20 | 2019-07-23 | Non-Private | Baladiya | Khamis Moshit Municipality | STC-ZKH-654 | 40000 | 400 | GF | Mohammed elshehry | HOC
ZKH707 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2020 | 18.3119 | 42.728 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 02/05/2019 17:52:01 | SNR1010030 | NOBODY | ACCEPTED | 2019-03-05 | 2019-03-08 | 2019-03-08 | 2019-03-10 | 22/05/2019 00:52:08 | 23/05/2019 16:32:56 | [6 empty] | 2019-07-07 | 2019-07-07 | 0 | 2019-10-07 | 2019-10-28 | 2019-07-08 | 18.3119 | 42.728 | 2019-05-28 | 2019-05-28 | 15m-RT-Tower | all roof | 2019-10-28 | Private | Private | مشبب عبدالله الحقباني | 505497834 | 34000 | 258M | RT | Mohammed elshehry | HOC | bar: 2019-11-13 to 2020-02-19
ZKH697 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2020 | 18.2313 | 42.8636 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 25/04/2019 18:19:16 | SNR1009733 | NOBODY | ACCEPTED | 2019-03-21 | 2019-03-24 | 2019-03-24 | 2019-03-26 | 02/05/2019 13:34:59 | 12/05/2019 13:27:11 | [6 empty] | 2019-05-02 | 2019-05-09 | 0 | 2019-05-07 | 2019-05-28 | 2019-05-28 | 18.2313 | 42.8636 | 2019-05-13 | 2019-05-13 | 60m-E4-GF |  | 2019-05-28 | Private | Private | علي سعيد علي | 505758360 | 27000 | 400M | GF | Mohammed elshehry | HOC | bar: 2019-11-13 to 2020-02-19
ZBH626 | Macro | Aspiration | HOC | HO to CW Done | Baha | 2019 | 20.3468 | 41.6447 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 28/04/2019 17:05:38 | SNR1009782 | NOBODY | ACCEPTED | 2019-03-20 | 2019-03-23 | 2019-03-23 | 2019-03-25 | NA | NA | 2019-08-18 | 2019-08-25 | 2019-08-25 | 2019-08-25 | 2019-09-08 | 2019-10-15 | NA | NA | 102097826 | 2019-10-15 | 2020-07-05 | 2019-09-08 | 20.3468 | 41.6447 | 2019-10-15 | 2019-10-15 | 60m-E4-GF |  | 2019-10-15 | Non-Private | GOV | Saudi Industrial Citi ines Authority - Aqiq | 811141 | 29000 | 401 | GF | Fahad Alrogy | HOC
ZMC302 | Macro | Aspiration | HOC | HO to CW Done | Makkah | 2020 | 21.4418 | 39.7878 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 24/04/2019 17:47:50 | SNR1009710 | SNR_I | District Support | 2019-04-29 | 2019-05-02 | 2019-05-02 | 2019-05-04 | NA | NA | 2019-05-14 | 2020-02-09 | 2020-07-08 | 2020-07-20 | 2020-09-08 | 2020-08-13 | NA | NA | 0 | 2020-08-13 | 2020-08-13 | 2020-02-06 | 21.4418 | 39.7878 | 2020-02-16 | 2020-02-17 | 35m-LP-GF | 7X3 | 2020-08-18 | Non-Private | GOV | وزارة العمل والتنميه الاجتماعيه |  | 40000 | 7X3 | GF | Adnan Alqorashy | HOC
ZKH728 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2020 | 18.5647 | 42.6897 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 19/05/2019 14:45:25 | SNR1010295 | NOBODY | ACCEPTED | 2019-03-20 | 2019-03-23 | 2019-03-23 | 2019-03-25 | NA | NA | 2019-05-02 | 2019-05-16 | 2019-05-16 | 2019-05-16 | 2019-06-19 | 2019-06-19 | NA | NA | 0 | 2019-06-19 | 2019-07-10 | 2019-06-11 | 18.5646 | 42.6897 | 2019-05-28 | 2019-05-28 | 60m-E4-GF | 20X20 | 2019-07-11 | Non-Private | Baladiya | Wadi Bin Hashbal Municipality | 4\15 | 25000 | 400 | GF | Mohammed elshehry | HOC
ZMC304 | Macro | Aspiration | HOC | HO to CW Done | Makkah | 2019 | 21.4487 | 39.8559 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 07/01/2020 16:27:54 | SNR1012572 | NOBODY | NA | 2020-01-05 | 2020-01-05 | 2020-01-09 | 2020-01-09 | 2020-02-26 | 2020-02-26 | [6 empty] | 2020-02-26 | 2020-03-11 | 0 | 2020-03-12 | 2020-06-25 | 44007 | 21.4487 | 39.8559 | 2020-03-24 | 2020-05-07 | 9m-RT-Tower |  | 2020-06-25 | Private | Private | يوسف العتيبي | 542339900 | 40000 | 10X10 | RT | Adnan Alqorashy | HOC | bar: 2019-11-13 to 2020-02-19
ZMC084 | Macro | Aspiration | HOC | HO to CW Done | Makkah | 2019 | 20.1445 | 40.2753 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 24/04/2019 17:41:28 | SNR1009709 | NOBODY | ACCEPTED | 2019-03-19 | 2019-03-19 | 2019-03-19 | 2019-03-19 | NA | NA | 2019-05-14 | 2020-09-02 | 2020-09-02 | 2020-09-02 | 2020-12-03 | 2020-12-10 | NA | NA | 6979 | 2020-12-10 | 2020-12-10 | 2020-02-06 | 20.1466 | 40.2786 | 2020-02-10 | 2020-02-12 | 45m-E4-GF | 225M | 2020-09-21 | Non-Private | Baladiya | بلدية الليث |  |  |  | GF | Adnan Alqorashy | HOC
ZMC301 | Macro | Aspiration | HOC | HO to CW Done | Makkah | 2019 | 21.4703 | 39.9607 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 12/05/2019 11:55:38 | SNR1010183 | NOBODY | ACCEPTED | 2019-03-09 | 2019-03-12 | 2019-03-12 | 2019-03-14 | NA | NA | 2019-03-21 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | NA | NA | 4005513201 | 2019-07-15 | 2019-08-05 | 2019-08-06 | 21.4703 | 39.9607 | 2019-08-04 | 2019-08-04 | 45M-E4-GF | 15X15 | 2019-08-20 | Non-Private | Baladiya | أمانة مكة المكرمة |  | NA | 15X15 | GF | Adnan Alqorashy | HOC
ZTF320 | Macro | Aspiration | HOC | HO to CW Done | Taif | 2019 | 20.6997 | 41.2246 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 17/06/2019 17:50:08 | SNR1010623 | NOBODY | ACCEPTED | 2019-09-16 | 2019-09-16 | 2020-02-06 | 2020-02-06 | NA | NA | 2019-07-05 | 2020-01-30 | 2020-01-30 | 2020-02-04 | 2020-02-26 | 2020-02-26 | NA | NA | 232903 | 2020-02-26 | 2020-02-26 | 2019-09-26 | 20.6997 | 41.2246 | 2019-12-23 | 2019-09-24 | 45m-E4-GF |  | 2020-02-26 | Non-Private | GOV | معهد تدريب الحرب الجبلية | ZTF320 | 25000 | 400 | GF | Fahad Alrogy | HOC
ZMC303 | Macro | Aspiration | HOC | HO to CW Done | Makkah | 2020 | 21.42 | 39.8171 | Nokia | New Site | New Location | Ram1441 |  | Macro | Doable |  | Approved | Approved | IGATE | 24/04/2019 17:53:07 | SNR1009711 | NOBODY | ACCEPTED | 2019-03-13 | 2019-03-16 | 2019-03-16 | 2019-03-18 | 2000-01-01 | 2000-01-01 | [6 empty] | 2000-01-01 | 2000-01-01 | 4005513095 | 2001-01-01 | 2020-06-25 | 2019-12-01 | 21.4191 | 39.8167 | 2020-06-25 | 2020-06-23 | 4.5M-WM-RT | 10X10 | 2020-06-25 | Private | Private | مساعد الراشدي | 505539560 | 40000 | 100M | RT | Adnan Alqorashy | HOC | bar: 2019-11-13 to 2020-02-19
ZMC305 | Macro | Aspiration | HOC | HO to CW Done | Makkah | 2019 | 21.3816 | 39.807 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 24/04/2019 17:57:59 | SNR1009712 | NOBODY | ACCEPTED | 2019-03-18 | 2019-03-18 | 2019-03-18 | 2019-03-18 | NA | NA | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | NA | NA | 4005513064 | 2019-07-11 | 2019-08-01 | 2019-07-25 | 21.3816 | 39.807 | 2019-07-23 | 2019-07-23 | 35m - Clock Tower | 7X3 | 2019-08-05 | Non-Private | Baladiya | أمانة مكة المكرمة |  | NA | 7X3 | GF | Adnan Alqorashy | HOC
ZMC315 | Macro | Aspiration | HOC | HO to CW Done | Makkah | 2020 | 21.4067 | 39.8214 | Nokia | New Site | New Location | Ram1441 |  | Macro | Doable |  | Approved | Approved | IGATE | 17/06/2019 13:14:37 | SNR1010596 | NOBODY | ACCEPTED | 2019-04-04 | 2019-04-07 | 2019-04-07 | 2019-04-09 | 2019-04-09 | 2019-12-15 | [6 empty] | 2019-12-22 | 2019-12-29 | 0 | 2020-01-01 | 2020-03-11 | 2020-01-21 | 21.4067 | 39.8214 | 2020-01-21 | 2020-01-21 | WM-Pole-RT | RT | 2020-01-21 | Private | Private | فندق اوان | 555655180 | 100000 | all roof | RT | Adnan Alqorashy | HOC | bar: 2019-11-13 to 2020-02-19
ZBH610 | Macro | Aspiration | HOC | HO to CW Done | Baha | 2020 | 19.8523 | 41.5712 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 14/05/2019 22:35:42 | SNR1010253 | NOBODY | ACCEPTED | 2019-09-16 | 2019-09-19 | 2019-09-19 | 2019-09-21 | 16/10/2019 14:35:05 | 17/10/2019 12:10:00 | [6 empty] | 2019-10-24 | 2019-10-29 | 0 | 2019-10-29 | 2020-07-05 | 2019-10-06 | 19.8524 | 41.5712 | 2019-11-24 | 2019-11-24 | 45m-E4-GF |  | 2019-11-17 | Private | Private | احمد محمد علي الغامدي | 554643224 | 30000 | 400M | GF | Fahad Alrogy | HOC | bar: 2019-11-13 to 2020-02-19
ZMC325 | Macro | Aspiration | Pending LA | IBP Not Issued | Makkah | 2020 | 21.4617 | 39.7212 | Nokia | New Site | New Location | Ram1441 |  | Macro | Doable |  | Approved | Approved | IGATE | 25/04/2019 13:29:28 | SNR1009721 | NOBODY | ACCEPTED | 2019-03-03 | 2019-03-06 | 2019-03-06 | 2019-03-08 | NA | NA | 2019-11-13: 2021-11-09 | NA | NA | CTR-21-11-000524 |  |  | 2019-12-01 | 21.4617 | 39.7212 | 2021-05-20 | 2021-06-23 | 60m-E4-GF | 20X20 |  | Non-Private | Baladiya | أمانة مكة المكرمة |  | NA | 20X20 | GF | Adnan Alqorashy | تم إعادة رفع معاملة طلب العقود من الأمانة على نظام فرص وجاري المتابعة مع الأمانة
ZMC300 | Macro | Aspiration | Pending FBP | FBP Not Issued | Makkah | 2019 | 21.3305 | 39.9575 | Nokia | New Site | New Location | Ram1441 |  | Macro | Doable |  | Approved | Approved | IGATE | 24/04/2019 17:26:24 | SNR1009707 | NOBODY | ACCEPTED | 2019-02-10 | 2019-02-13 | 2019-02-13 | 2019-02-15 | NA | NA | 2019-02-22 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | NA | NA | 4005513825 | 2000-01-01 |  | 2019-06-24 | 21.3305 | 39.9575 | 2019-06-23 | 2019-06-23 | 35-GRD sharable | 7X3.0 | 2019-08-04 | Non-Private | GOV | وزارة المواصلات بمكة المكرمة |  | NA | 7X3.0 | GF | Adnan Alqorashy | HOC
ZMC326 | Macro | Aspiration | HOC | HO to CW Done | Makkah | 2020 | 21.3018 | 39.6813 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 25/04/2019 10:43:29 | SNR1009715 | NOBODY | ACCEPTED | 2019-03-06 | 2019-03-09 | 2019-03-09 | 2019-03-11 | 18/09/2019 16:28:25 | 15/10/2019 10:18:41 | [6 empty] | 2019-10-30 | 2019-10-30 | 0 | 2019-10-31 | 2019-11-21 | 2019-11-02 | 21.3018 | 39.6813 | 2019-10-17 | 2019-10-17 | 60m-E4-GF | 20X20 | 2019-11-14 | Private | Private | سعد يحي ال عمانه | 503078292 | 35000 | 20X20 | GF | Adnan Alqorashy | HOC | bar: 2019-11-13 to 2020-02-19
ZMC335 | Macro | Aspiration | Pending FBP | FBP Not Issued | Makkah | 2019 | 21.6192 | 39.7019 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 05/05/2019 16:55:20 | SNR1010078 | NOBODY | ACCEPTED | 2019-04-18 | 2019-04-21 | 2019-04-21 | 2019-04-23 | NA | NA | 2019-05-14 | 2019-12-19 | 2019-12-19 | 2019-12-22 | 2019-12-25 | 2019-12-26 | NA | NA | 400089695 | 2020-01-01 |  | 2020-01-02 | 21.6192 | 39.7019 | 2020-12-30 | 2020-01-01 | 35m-Holly Name | 10 X 8 | 2019-12-26 | Non-Private | Baladiya | بلدية الجموم | 26\1441 | 55000 | 10 X 8 | GF | Adnan Alqorashy | HOC
ZTF328 | Macro | Aspiration | HOC | HO to CW Done | Taif | 2019 | 21.2789 | 40.4183 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 26/05/2019 13:14:50 | SNR1010406 | NOBODY | ACCEPTED | 2019-03-18 | 2019-03-21 | 2019-03-21 | 2019-03-23 | NA | NA | 2019-11-03 | 2019-11-10 | 2019-11-10 | 2019-11-10 | 2019-11-19 | 2019-11-28 | NA | NA | 0 | 2019-12-01 | 2020-02-03 | 2019-11-28 | 21.2789 | 40.4183 | 2019-12-03 | 2019-12-04 | 35m-LP-GF | 3.50 X 7.00 | 2019-12-01 | Non-Private | Baladiya | امانة الطائف | 441/470 | 30000 | 24.5 | GF | Fahad Alrogy | HOC
ZMC323 | Macro | Aspiration | HOC | HO to CW Done | Makkah | 2019 | 21.3796 | 39.7948 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 12/05/2019 12:27:08 | SNR1010194 | NOBODY | NA | 2019-03-18 | 2019-03-18 | 2019-03-18 | 2019-03-18 | 2020-03-18 | 2020-03-18 | [6 empty] | 2020-06-29 | 2020-06-29 | 4005513021 | 2020-06-29 | 2021-06-30 | 2021-07-12 | 21.3784 | 39.7945 | 2020-11-10 | 2020-11-10 | 9m-RT-Tower | 10X10 | 2021-07-01 | Private | Private | محمد الغامدي | 555777292 | 50000 | 10X10 | RT | Adnan Alqorashy | HOC | bar: 2019-11-13 to 2020-02-19
ZMC324 | Macro | Aspiration | HOC | HO to CW Done | Makkah | 2019 | 21.4096 | 39.7993 | Nokia | New Site | New Location | Hajj1440 |  | Macro | Doable |  | Approved | Approved | IGATE | 29/04/2019 16:24:24 | SNR1009820 | NOBODY | ACCEPTED | 2018-12-18 | 2018-12-21 | 2018-12-21 | 2018-12-23 | NA | NA | 2018-12-30 | 2021-06-05 | 2021-06-05 | 2021-06-05 | 2021-06-05 | 2021-06-05 | NA | NA | 4005513026 | 2019-06-24 | 2019-07-15 | 2019-06-18 | 21.4096 | 39.7993 | 2019-06-18 | 2019-06-18 | 35M-LP-GF | 4X4 | 2019-07-11 | Non-Private | Baladiya | أمانة مكة المكرمة |  | NA | 4X4 | GF | Adnan Alqorashy | HOC
ZMC331 | Macro | Aspiration | HOC | HO to CW Done | Makkah | 2019 | 21.3781 | 39.8323 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 25/04/2019 11:42:52 | SNR1009716 | NOBODY | ACCEPTED | 2019-03-24 | 2019-03-27 | 2019-03-27 | 2019-03-29 | 18/09/2019 18:59:11 | 01/10/2019 11:03:05 | [6 empty] | 2019-10-15 | 2019-10-27 | 0 | 2019-10-31 | 2019-11-21 | 2019-11-02 | 21.3781 | 39.8323 | 2019-10-17 | 2019-10-17 | WM-POLE-RT | 10X10 | 2019-11-14 | Private | Private | شركة بيت ال سعيدان | 555548795 | 60000 | 10X10 | RT | Adnan Alqorashy | HOC | bar: 2019-11-13 to 2020-02-19
ZMC330 | Macro | Aspiration | Pending FBP | FBP Not Issued | Makkah | 2020 | 21.6249 | 39.8245 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 14/05/2019 21:51:49 | SNR1010249 | NOBODY | ACCEPTED | 2019-03-02 | 2019-03-02 | 2019-03-02 | 2019-03-02 | NA | NA | 2019-07-22 | 2019-12-19 | 2019-12-19 | 2019-12-22 | 2019-12-25 | 2019-12-26 | NA | NA | 400110797 | 2020-01-01 |  | 2019-12-30 | 21.6249 | 39.8245 | 2019-12-30 | 2019-12-31 | 60m-E4-GF | 10X8 | 2019-12-26 | Non-Private | Baladiya | بلدية الجموم | 28\1441 | 25000 | 20X20 | GF | Adnan Alqorashy | HOC
ZMC342 | Macro | Aspiration | HOC | HO to CW Done | Makkah | 2019 | 21.3694 | 39.9803 | Nokia | New Site | New Location | Hajj1441 |  | Macro | Doable |  | Approved | Approved | IGATE | 29/04/2019 17:31:05 | SNR1009834 | NOBODY | ACCEPTED | 2019-01-24 | 2019-01-27 | 2019-01-27 | 2019-01-29 | NA | NA | 2019-02-05 | 2021-06-05 | 2021-06-05 | 2021-06-05 | 2021-06-05 | 2021-06-05 | NA | NA | 4005513024 | 2019-08-04 | 2019-08-25 | 2019-06-18 | 21.3694 | 39.9803 | 2019-06-18 | 2019-06-18 | 14.5m Concealed Pole | 1.8X1.8 | 2019-08-26 | Non-Private | Baladiya | أمانة مكة المكرمة |  | NA | 1.8X1.8 | GF | Adnan Alqorashy | HOC
ZMC609 | Macro | Aspiration | HOC | HO to CW Done | Makkah | 2019 | 21.4755 | 39.9833 | Nokia | New Site | New Location | Hajj1440 |  | Macro | Doable |  | Approved | Approved | IGATE | 25/04/2019 13:22:29 | SNR1009719 | NOBODY | ACCEPTED | 2019-03-03 | 2019-03-06 | 2019-03-06 | 2019-03-08 | 02/05/2019 15:07:20 | 08/05/2019 13:47:12 | [6 empty] | 2019-05-22 | 2019-05-22 | 0 | 2019-06-13 | 2019-07-04 | 2019-04-22 | 21.4755 | 39.9833 | 2019-04-21 | 2019-04-21 | 45M-E4-GF |  | 2019-07-04 | Private | Private | عادل عيضه القرشي | 590361188 | 55000 | 15X15 | GF | Adnan Alqorashy | HOC | bar: 2019-11-13 to 2020-02-19
ZMC339 | Macro | Aspiration | HOC | HO to CW Done | Makkah | 2019 | 22.7999 | 39.0372 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 25/04/2019 12:01:00 | SNR1009717 | NOBODY | NA | 2019-03-04 | 2019-03-07 | 2019-03-07 | 2019-03-09 | 2020-02-04 | 2020-02-04 | [6 empty] | 2020-02-04 | 2020-02-16 | 1440007615 | 2020-02-19 | 2020-06-18 | 2019-05-14 | 22.8003 | 39.038 | 2020-02-13 | 2020-02-16 | 12m-RT-Tower | Half of Roof | 2020-06-18 | Private | Private | خيشان عبد الله البلادي | 538860820 | 35000 | all roof | RT | Adnan Alqorashy | HOC | bar: 2019-11-13 to 2020-02-19
ZMC341 | Macro | Aspiration | HOC | HO to CW Done | Makkah | 2019 | 21.3686 | 39.9859 | Nokia | New Site | New Location | Hajj1441 |  | Macro | Doable |  | Approved | Approved | IGATE | 29/04/2019 16:35:38 | SNR1009823 | NOBODY | ACCEPTED | 2019-01-24 | 2019-01-27 | 2019-01-27 | 2019-01-29 | NA | NA | 2019-02-05 | 2021-06-05 | 2021-06-05 | 2021-06-05 | 2021-06-05 | 2021-06-05 | NA | NA | 4005513022 | 2019-08-04 | 2019-08-25 | 2019-06-18 | 21.3686 | 39.9859 | 2019-06-18 | 2019-06-18 | 14.5m Concealed Pole | 1.8X1.8 | 2019-08-26 | Non-Private | Baladiya | أمانة مكة المكرمة |  | NA | 1.8X1.8 | GF | Adnan Alqorashy | HOC
ZMC343 | Macro | Aspiration | HOC | HO to CW Done | Makkah | 2019 | 21.4235 | 39.8758 | Nokia | New Site | New Location | Hajj1441 |  | Macro | Doable |  | Approved | Approved | IGATE | 29/04/2019 17:40:27 | SNR1009835 | NOBODY | ACCEPTED | 2018-12-20 | 2018-12-23 | 2018-12-23 | 2018-12-25 | NA | NA | 2019-01-01 | 2021-06-05 | 2021-06-05 | 2021-06-05 | 2021-06-05 | 2021-06-05 | NA | NA | 4005513023 | 2019-08-04 | 2019-08-25 | 2019-06-23 | 21.4235 | 39.8758 | 2019-06-18 | 2019-06-18 | WM-POLE-RT | 1x1 | 2019-08-25 | Non-Private | Baladiya | أمانة مكة المكرمة |  | NA | 1x1 | RT | Adnan Alqorashy | HOC
ZMC559 | Macro | Aspiration | HOC | HO to CW Done | Makkah | 2019 | 21.3674 | 39.8354 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 14/05/2019 21:59:36 | SNR1010250 | NOBODY | ACCEPTED | 2019-03-13 | 2019-03-16 | 2019-03-16 | 2019-03-18 | 2019-10-20 | 2019-10-20 | [6 empty] | 2019-12-19 | 2019-12-19 | 4005513019 | 2019-12-29 | 2020-03-11 | 2020-01-29 | 21.3674 | 39.8354 | 2020-02-05 | 2019-11-05 | WM-Pole-RT | 10x10 | 2020-03-12 | Private | Private | شركة الشلوي العالمية للتجارة والمقاولات | 553538711 | 60000 | all roof | RT | Adnan Alqorashy | HOC | bar: 2019-11-13 to 2020-02-19
ZMC576 | Macro | Aspiration | HOC | HO to CW Done | Makkah | 2019 | 21.382 | 39.7833 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 30/04/2019 10:28:07 | SNR1009875 | NOBODY | ACCEPTED | 2019-03-18 | 2019-03-21 | 2019-03-21 | 2019-03-23 | NA | NA | 2019-03-30 | 2021-06-05 | 2021-06-05 | 2021-06-05 | 2021-06-05 | 2021-06-05 | NA | NA | 4005513070 | 2019-07-11 | 2019-08-01 | 2019-07-30 | 21.382 | 39.7833 | 2019-07-29 | 2019-07-29 | 35m - Clock Tower | 10X10 | 2019-08-06 | Non-Private | Baladiya | أمانة مكة المكرمة |  | NA | 10X10 | GF | Adnan Alqorashy | HOC
ZMC589 | Macro | Aspiration | HOC | HO to CW Done | Makkah | 2019 | 21.4691 | 40.0002 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 17/06/2019 12:19:44 | SNR1010572 | NOBODY | ACCEPTED | 2019-11-27 | 2019-12-15 | 2020-01-13 | 2020-01-13 | 2020-01-13 | 2020-01-13 | [6 empty] | 2020-01-28 | 2020-01-28 | 0 | 2020-02-04 | 2020-03-12 | 2020-02-02 | 21.4691 | 40.0002 | 2020-02-05 | 2020-02-05 | 60m-E4-GF |  | 2020-03-12 | Private | Private | حامد بن رده القرشي | 505560350 | 50000 | 400M | GF | Adnan Alqorashy | HOC | bar: 2019-11-13 to 2020-02-19
ZMC655 | Macro | Aspiration | HOC | HO to CW Done | Makkah | 2019 | 21.4636 | 39.9459 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 12/05/2019 12:43:09 | SNR1010200 | NOBODY | ACCEPTED | 2019-03-06 | 2019-03-09 | 2019-03-09 | 2019-03-11 | 2020-02-23 | 2020-03-02 | [6 empty] | 2020-03-02 | 2020-03-08 | 4005513090 | 2020-03-11 | 2020-06-25 | 2020-06-25 | 21.4639 | 39.9445 | 2020-06-25 | 2020-06-20 | 9m-RT-Tower | all roof | 2020-06-25 | Private | Private | عبد الغني بن صالح حمادة | 599233750 | 45000 | all roof | RT | Adnan Alqorashy | HOC | bar: 2019-11-13 to 2020-02-19
ZMC658 | Macro | Aspiration | HOC | HO to CW Done | Makkah | 2019 | 21.386 | 39.8144 | Nokia | New Site | New Location | Hajj1440 |  | Macro | Doable |  | Approved | Approved | IGATE | 30/04/2019 10:42:56 | SNR1009878 | NOBODY | ACCEPTED | 2019-03-24 | 2019-03-27 | 2019-03-27 | 2019-03-29 | NA | NA | 2019-04-05 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | NA | NA | 4001133514 | 2000-01-01 | 2001-01-01 | 2019-06-25 | 21.386 | 39.8144 | 2019-06-20 | 2019-06-20 | 50m GRD Sharable | 10X10 | 2019-07-04 | Non-Private | GOV | جامعة ام القرى(ادارة الاستثمار يوسف المبعوث ) |  | NA | 10X10 | GF | Adnan Alqorashy | HOC
ZMC665 | Macro | Aspiration | Pending LA | IBP Not Issued | Makkah | 2020 | 21.5138 | 40.0355 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 15/05/2019 22:23:28 | SNR1010275 | SNR_I | District Support | 2019-03-02 | 2019-03-02 | 2019-03-02 | 2019-03-02 | NA | NA | 2019-11-13: 2021-11-09 | NA | NA | CTR-21-11-000523 |  |  | 2021-06-30 | 21.5278 | 40.0423 | 2021-07-12 | 2021-07-25 | 60m-E4-GF | 20X20 |  | Non-Private | Baladiya | امانة مكة المكرمة |  |  | 20X20 | GF | Adnan Alqorashy | تم إعادة رفع معاملة طلب العقود من الأمانة على نظام فرص وجاري المتابعة مع الأمانة
ZMC664 | Macro | Aspiration | HOC | HO to CW Done | Makkah | 2020 | 21.3923 | 39.7796 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 30/04/2019 10:46:43 | SNR1009879 | NOBODY | ACCEPTED | 2019-03-10 | 2019-03-13 | 2019-03-13 | 2019-03-15 | NA | NA | 2019-03-22 | 2021-06-05 | 2021-06-05 | 2021-06-05 | 2021-06-05 | 2021-06-05 | NA | NA | 4005513068 | 2019-07-11 | 2019-08-01 | 2019-07-25 | 21.3923 | 39.7796 | 2019-07-23 | 2019-07-23 | 35m - Clock Tower | 3X7 | 2019-08-05 | Non-Private | Baladiya | أمانة مكة المكرمة |  | NA | 3X7 | GF | Adnan Alqorashy | HOC
ZMC713 | Macro | Aspiration | HOC | HO to CW Done | Taif | 2019 | 20.4601 | 40.8915 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 24/04/2019 16:02:22 | SNR1009702 | NOBODY | ACCEPTED | 2019-03-20 | 2019-03-23 | 2019-03-23 | 2019-03-25 | NA | NA | 2019-08-19 | 2019-08-26 | 2019-12-24 | 2019-12-25 | 2020-01-02 | 2020-01-02 | NA | NA | 8/12 القيد | 2020-01-05 | 2020-03-08 | 2019-06-30 | 20.4601 | 40.8915 | 2019-07-09 | 2019-07-09 | 60m-E4-GF | 225M | 2019-12-26 | Non-Private | Baladiya | بلدية اضم | 18 ج | 30000 | 225 | GF | Fahad Alrogy | HOC
ZMC616 | Macro | Aspiration | HOC | HO to CW Done | Makkah | 2019 | 21.4911 | 39.9556 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 05/05/2019 17:03:24 | SNR1010079 | NOBODY | ACCEPTED | 2019-03-10 | 2019-03-13 | 2019-03-13 | 2019-03-15 | NA | NA | 2019-03-22 | 2021-06-05 | 2021-06-05 | 2021-06-05 | 2021-06-05 | 2021-06-05 | NA | NA | 4005513108 | 2019-07-15 | 2019-08-05 | 2019-08-06 | 21.4911 | 39.9556 | 2019-08-04 | 2019-08-04 | 35M-LP-GF | 7X3 | 2019-08-20 | Non-Private | Baladiya | أمانة مكة المكرمة |  | NA | 7X3 | GF | Adnan Alqorashy | HOC
ZMC685 | Macro | Aspiration | HOC | HO to CW Done | Makkah | 2020 | 21.4794 | 39.836 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 14/05/2019 22:30:05 | SNR1010252 | NOBODY | ACCEPTED | 2019-03-02 | 2019-03-05 | 2019-03-05 | 2019-03-07 | NA | NA | 2019-05-15 | 2020-11-16 | 2020-11-16 | 2020-11-16 | 2020-11-16 | 2020-11-16 | NA | NA | 4005513066 | 2020-11-16 | 2020-11-16 | 2020-09-03 | 21.4792 | 39.8359 | 2020-09-03 | 2020-11-16 | Sharing Mobily 35m | 15X15 | 2020-11-19 | Non-Private | Sharing | Sharing With Mobily | NA | NA | Sharing | Sharing | Adnan Alqorashy | HOC
ZMC686 | Macro | Aspiration | HOC | HO to CW Done | Makkah | 2019 | 21.3539 | 39.8916 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 12/05/2019 12:50:49 | SNR1010202 | NOBODY | ACCEPTED | 2019-03-10 | 2019-03-13 | 2019-03-13 | 2019-03-15 | NA | NA | 2019-05-15 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | NA | NA | 4005513076 | 2001-01-01 | 2021-10-26 | 2019-12-15 | 21.3539 | 39.8916 | 2019-12-18 | 2019-08-07 | 35m - Clock Tower | 8.7X8.7 | 2021-10-27 | Non-Private | Baladiya | أمانة مكة المكرمة | NA | NA | 8.7X8.7 | GF | Adnan Alqorashy | HOC
ZMC695 | Macro | Aspiration | Pending FBP | FBP Not Issued | Makkah | 2020 | 21.6158 | 39.8054 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 30/04/2019 10:51:49 | SNR1009882 | NOBODY | ACCEPTED | 2019-03-05 | 2019-03-05 | 2019-03-05 | 2019-03-05 | NA | NA | 2019-07-22 | 2019-12-19 | 2019-12-19 | 2019-12-22 | 2019-12-25 | 2019-12-26 | NA | NA | 400110583 | 2020-01-01 |  | 2020-12-29 | 21.6159 | 39.8054 | 2020-12-30 | 2020-01-01 | 60m-E4-GF | 20X20 | 2019-12-26 | Non-Private | Baladiya | بلدية الجموم | 29\1441 | 25000 | 20X20 | GF | Adnan Alqorashy | HOC
ZMC696 | Macro | Aspiration | HOC | HO to CW Done | Makkah | 2020 | 21.3913 | 39.8076 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 15/05/2019 22:32:43 | SNR1010276 | NOBODY | ACCEPTED | 2019-03-13 | 2019-03-16 | 2019-03-16 | 2019-03-18 | NA | NA | 2019-08-04 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | NA | NA | 4005513048 | 2001-01-01 | 2021-10-26 | 2020-02-04 | 21.3913 | 39.8076 | 2020-02-09 | 2019-08-07 | 35m - Clock Tower | 10X10 | 2021-10-27 | Non-Private | Baladiya | أمانة مكة المكرمة | NA | NA | 10X10 | GF | Adnan Alqorashy | HOC
ZMC703 | Macro | Aspiration | HOC | HO to CW Done | Makkah | 2019 | 21.4632 | 39.5569 | Nokia | New Site | New Location | Hajj1440 |  | Macro | Doable |  | Approved | Approved | IGATE | 30/04/2019 11:03:38 | SNR1009887 | NOBODY | ACCEPTED | 2019-03-06 | 2019-03-09 | 2019-03-09 | 2019-03-11 | NA | NA | 2019-03-18 | 2021-06-05 | 2021-06-05 | 2021-06-05 | 2021-06-05 | 2021-06-05 | NA | NA | 4005513025 | 2019-06-24 | 2019-07-15 | 2019-06-18 | 21.4632 | 39.5569 | 2019-06-18 | 2019-06-18 | 60m-E4-GF | 15X15 | 2019-07-11 | Non-Private | Baladiya | أمانة مكة المكرمة |  | NA | 15X15 | GF | Adnan Alqorashy | HOC
ZMC617 | Macro | Aspiration | HOC | HO to CW Done | Makkah | 2020 | 21.2771 | 39.9654 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 30/04/2019 10:32:18 | SNR1009876 | NOBODY | ACCEPTED | 2019-03-06 | 2019-03-09 | 2019-03-09 | 2019-03-11 | NA | NA | 2019-03-18 | 2021-06-05 | 2021-06-05 | 2021-06-05 | 2021-06-05 | 2021-06-05 | NA | NA | 4005513200 | 2019-07-15 | 2019-08-05 | 2019-08-06 | 21.2771 | 39.9654 | 2019-08-04 | 2019-08-04 | 60m-E4-GF | 15X15 | 2019-08-21 | Non-Private | Baladiya | أمانة مكة المكرمة |  | NA | 15X15 | GF | Adnan Alqorashy | HOC
ZMC714 | Macro | Aspiration | HOC | HO to CW Done | Taif | 2019 | 20.4168 | 40.8577 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 24/04/2019 16:14:09 | SNR1009703 | NOBODY | ACCEPTED | 2019-03-20 | 2019-03-23 | 2019-03-23 | 2019-03-25 | NA | NA | 2019-08-19 | 2019-08-26 | 2019-12-24 | 2019-12-25 | 2020-01-02 | 2020-01-02 | NA | NA | 8/12 القيد | 2020-01-05 | 2020-03-05 | 2019-08-25 | 20.4168 | 40.8577 | 2019-10-13 | 2019-10-14 | 60m-E4-GF | 225M | 2019-12-26 | Non-Private | Baladiya | بلدية اضم | 19 ج | 30000 | 225 | GF | Fahad Alrogy | HOC
ZMC757 | Macro | Aspiration | HOC | HO to CW Done | Makkah | 2019 | 21.4529 | 39.9354 | Nokia | New Site | New Location | Hajj1440 |  | Macro | Doable |  | Approved | Approved | IGATE | 12/05/2019 11:48:06 | SNR1010180 | NOBODY | ACCEPTED | 2019-03-03 | 2019-03-06 | 2019-03-06 | 2019-03-08 | NA | NA | 2019-03-15 | 2021-06-05 | 2021-06-05 | 2021-06-05 | 2021-06-05 | 2021-06-05 | NA | NA | 4005513018 | 2019-06-24 | 2019-07-15 | 2019-06-18 | 21.4529 | 39.9354 | 2019-06-18 | 2019-06-18 | 45M-E4-GF | 15X15 | 2019-07-11 | Non-Private | Baladiya | أمانة مكة المكرمة |  | NA | 15X15 | GF | Adnan Alqorashy | HOC
ZMC783 | Macro | Aspiration | HOC | HO to CW Done | Makkah | 2019 | 21.3859 | 39.895 | Nokia | New Site | New Location | Ram1441 |  | Macro | Doable |  | Approved | Approved | IGATE | 30/04/2019 11:44:07 | SNR1009900 | NOBODY | ACCEPTED | 2019-01-15 | 2019-01-18 | 2019-01-18 | 2019-01-20 | NA | NA | 2019-01-27 | 2021-06-05 | 2021-06-05 | 2021-06-05 | 2021-06-05 | 2021-06-05 | NA | NA | 4005513014 | 2019-08-04 | 2019-08-25 | 2019-06-18 | 21.3859 | 39.895 | 2019-06-18 | 2019-06-18 | 35M-LP-GF | 7X3.5 | 2019-08-25 | Non-Private | Baladiya | أمانة مكة المكرمة |  | NA | 7X3.5 | GF | Adnan Alqorashy | HOC
ZMC840 | Macro | Aspiration | HOC | HO to CW Done | Makkah | 2019 | 22.7921 | 39.0482 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 29/04/2019 16:17:22 | SNR1009818 | NOBODY | NA | 2019-03-04 | 2019-03-07 | 2019-03-07 | 2019-03-09 | 2020-03-18 | 2020-03-18 | [6 empty] | 2020-05-06 | 2020-04-27 | 1440007615 | 2020-06-18 | 2020-06-18 | 2019-05-14 | 22.7921 | 39.0482 | 2019-05-09 | 2019-12-02 | 45m-E4-GF | 225M | 2020-06-18 | Private | Private | علوه الشهري |  | 35000 | 15X15 | GF | Adnan Alqorashy | HOC | bar: 2019-11-13 to 2020-02-19
ZMC861 | Macro | Aspiration | HOC | HO to CW Done | Makkah | 2019 | 21.4063 | 39.8133 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 30/04/2019 11:11:07 | SNR1009891 | NOBODY | NA | 2019-03-12 | 2019-03-12 | 2019-03-12 | 2019-03-12 | 2020-03-18 | 2020-03-18 | [6 empty] | 2020-06-02 | 2020-06-02 | 4005513074 | 2020-06-02 | 2020-06-25 | 2020-11-02 | 21.4064 | 39.8138 | 2020-06-25 | 2020-06-23 | 9m-RT-Tower | 7x3.5 | 2020-06-25 | Private | Private | نورة الشريف |  | 50000 | 10X10 | RT | Adnan Alqorashy | HOC | bar: 2019-11-13 to 2020-02-19
ZTF426 | Macro | Aspiration | HOC | HO to CW Done | Taif | 2020 | 21.3274 | 40.4366 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 26/05/2019 13:06:02 | SNR1010405 | NOBODY | ACCEPTED | 2019-05-21 | 2019-05-24 | 2019-05-24 | 2019-05-26 | NA | NA | 2019-07-05 | 2020-01-30 | 2020-01-30 | 2020-02-04 | 2020-02-26 | 2020-02-26 | NA | NA | 232903 | 2020-02-26 | 2020-02-26 | 2019-06-30 | 21.3274 | 40.4366 | 2019-07-07 | 2019-07-07 | 45m-E4-GF |  | 2020-02-26 | Non-Private | GOV | معهد سلاح الصيانه بالطائف | ZTF426 | 38000 |  | GF | Fahad Alrogy | HOC
ZMD488 | Macro | Aspiration | HOC | HO to CW Done | Madinah | 2019 | 24.4121 | 39.5626 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 30/04/2019 14:51:15 | SNR1009954 | NOBODY | ACCEPTED | 2019-03-18 | 2019-03-21 | 2019-03-21 | 2019-03-23 | NA | NA | 2019-07-02 | 2019-07-09 | 2019-07-09 | 2019-07-09 | 2019-08-07 | 2019-10-13 | NA | NA | 410109 | 2019-10-13 | 2020-01-21 | 2019-07-06 | 24.4121 | 39.5625 | 2019-08-04 | 2019-08-05 | 35M-LP-GF |  | 2019-10-14 | Non-Private | Baladiya | امانة المدينة المنورة | 41/19 | 100000 | 400 | GF | Fahad Aljohany | HOC
ZMD517 | Macro | Aspiration | HOC | HO to CW Done | Madinah | 2019 | 24.4809 | 39.6445 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 21/05/2019 22:57:03 | SNR1010345 | NOBODY | ACCEPTED | 2019-03-18 | 2019-03-18 | 2019-03-18 | 2019-03-18 | NA | NA | 2019-10-28 | 2019-11-04 | 2019-11-04 | 2019-11-04 | 2019-12-16 | 2020-01-06 | NA | NA | 0 | 2020-01-13 | 2020-09-13 | 2019-11-17 | 24.4809 | 39.6445 | 2019-12-02 | 2019-11-14 | 35m-LP-GF | 7x3.5 | 2020-01-01 | Non-Private | Baladiya | أمانة المدينة المنورة | 41/40 | 120000 | 24.5 | GF | Fahad Aljohany | HOC
ZMD716 | Macro | Aspiration | HOC | HO to CW Done | Madinah | 2020 | 24.4838 | 39.5082 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 12/05/2019 14:09:17 | SNR1010212 | NOBODY | ACCEPTED | 2019-03-14 | 2019-03-17 | 2019-03-17 | 2019-03-19 | NA | NA | 2019-07-02 | 2019-07-09 | 2019-07-09 | 2019-07-09 | 2019-08-07 | 2019-10-13 | NA | NA | 410111 | 2019-10-13 | 2020-01-21 | 2019-07-06 | 24.4836 | 39.5084 | 2019-08-04 | 2019-08-05 | 35m-LP-GF |  | 2019-10-14 | Non-Private | Baladiya | امانة المدينة المنورة | 41/13 | 100000 | 400 | GF | Fahad Aljohany | HOC
ZMH229 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2020 | 18.507 | 42.0687 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 28/04/2019 16:33:22 | SNR1009776 | NOBODY | ACCEPTED | 2019-03-20 | 2019-03-23 | 2019-03-23 | 2019-03-25 | NA | NA | 2019-04-18 | 2019-05-02 | 2019-05-02 | 2019-05-02 | 2019-10-02 | 2019-10-02 | NA | NA | 0 | 2019-10-30 | 2019-11-20 | 2019-06-11 | 18.5071 | 42.0686 | 2019-05-30 | 2019-05-30 | 45M-E4-GF | 400M | 2019-11-10 | Non-Private | Baladiya | بلدية محايل عسير | ZMH229 | 36000 | 400 | GF | Mohammed elshehry | HOC
ZMH232 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2020 | 18.5875 | 42.0282 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 28/04/2019 15:32:13 | SNR1009771 | NOBODY | ACCEPTED | 2019-03-20 | 2019-03-23 | 2019-03-23 | 2019-03-25 | NA | NA | 2019-04-18 | 2019-05-02 | 2019-05-02 | 2019-05-02 | 2019-06-19 | 2019-06-19 | NA | NA | 0 | 2019-07-03 | 2019-07-24 | 2019-06-11 | 18.5874 | 42.0281 | 2019-05-28 | 2019-05-28 | 60m-E4-GF | 20X20 | 2019-07-25 | Non-Private | Baladiya | Muhail Municipality | ZMH232 | 28000 | 400 | GF | Mohammed elshehry | HOC
ZMJ098 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2020 | 19.1207 | 41.9125 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 27/04/2019 16:16:19 | SNR1009734 | NOBODY | ACCEPTED | 2019-03-23 | 2019-03-26 | 2019-03-26 | 2019-03-28 | 2020-02-23 | 2020-02-26 | [6 empty] | 2020-02-26 | 2020-03-05 | 0 | 2020-03-08 | 2020-03-29 | 2020-03-01 | 19.1207 | 41.9125 | 2020-03-02 | 2020-03-04 | 45m-E4-GF |  | 2020-03-29 | Private | Private | معيض الشهري | 562713805 | 25000 | 20X20 | GF | Mohammed elshehry | HOC | bar: 2019-11-13 to 2020-02-19
ZMD499 | Macro | Aspiration | HOC | HO to CW Done | Madinah | 2019 | 23.783 | 38.7813 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 01/05/2019 12:26:15 | SNR1009999 | NOBODY | ACCEPTED | 2019-03-21 | 2019-03-24 | 2019-03-24 | 2019-03-26 | NA | NA | 2019-04-11 | 2020-02-11 | 2020-02-11 | 2020-02-16 | 2020-02-26 | 2020-03-03 | NA | NA | NI-35/192 | 2020-03-03 | 2020-03-25 | 2020-02-04 | 23.783 | 38.7813 | 2020-02-09 | 2020-02-10 | 45m-E4-GF | 12 X 12 | 2020-03-25 | Non-Private | Baladiya | بلدية محافظة بدر | 41010 | 36000 | 12X12 | GF | Fahad Aljohany | HOC
ZMJ099 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2020 | 19.1535 | 41.9161 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 27/04/2019 16:22:35 | SNR1009735 | NOBODY | ACCEPTED | 2019-03-19 | 2019-03-22 | 2019-03-22 | 2019-03-24 | 2019-10-13 | 2019-10-21 | [6 empty] | 2019-10-29 | 2019-11-24 | 0 | 2019-11-24 | 2020-03-01 | 2019-12-01 | 19.1536 | 41.9162 | 2019-11-12 | 2019-10-13 | 60m-E4-GF | 20 X 20 | 2019-12-01 | Private | Private | علي الشهري | 504747196 | 30000 | 400 | GF | Mohammed elshehry | HOC | bar: 2019-11-13 to 2020-02-19
ZMM054 | Macro | Aspiration | HOC | HO to CW Done | Madinah | 2019 | 24.8743 | 40.5317 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 30/04/2019 15:18:40 | SNR1009962 | NOBODY | ACCEPTED | 2019-03-03 | 2019-03-06 | 2019-03-06 | 2019-03-08 | 23/06/2019 17:58:39 | 24/06/2019 16:10:59 | [6 empty] | 2019-07-17 | 2019-07-18 | NI-35/182 | 2019-07-18 | 2020-02-20 | 2019-04-23 | 24.8744 | 40.5317 | 2019-07-15 | 2019-07-21 | 45M-E4-GF |  | 2019-11-24 | Private | Private | محمد المخلفي | 555447033 | 30000 | 400 | GF | Fahad Aljohany | HOC | bar: 2019-11-13 to 2020-02-19
ZMD577 | Macro | Aspiration | HOC | HO to CW Done | Madinah | 2019 | 24.4497 | 39.6485 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 21/05/2019 23:10:54 | SNR1010346 | NOBODY | ACCEPTED | 2019-04-04 | 2019-04-07 | 2019-04-07 | 2019-04-09 | NA | NA | 2019-07-02 | 2019-07-09 | 2019-07-09 | 2019-07-09 | 2019-12-16 | 2020-01-06 | NA | NA | COO-2 /23 | 2020-01-13 | 2020-06-04 | 2019-07-13 | 24.4497 | 39.6485 | 2019-08-04 | 2019-07-07 | 35m-LP-GF | 12x12 | 2020-01-01 | Non-Private | Baladiya | أمانة المدينة المنورة | 41/37 | 120000 | 144 | GF | Fahad Aljohany | HOC
ZMC925 | Macro | Aspiration | Pending LA | IBP Not Issued | Makkah | 2020 | 21.4901 | 39.7388 | Nokia | New Site | New Location | Ram1441 |  | Macro | Doable |  | Approved | Approved | IGATE | 30/04/2019 11:24:59 | SNR1009896 | NOBODY | ACCEPTED | 2019-03-03 | 2019-03-06 | 2019-03-06 | 2019-03-08 | NA | NA | 2019-11-13: 2021-11-09 | NA | NA | CTR-21-11-000521 |  |  | 2019-12-01 | 21.4897 | 39.7388 | 2021-08-01 | 2021-08-02 | 60m-E4-GF | 20 x 20 |  | Non-Private | Baladiya | أمانة مكة المكرمة |  | NA | 20 x 20 | GF | Adnan Alqorashy | تم إعادة رفع معاملة طلب العقود من الأمانة على نظام فرص وجاري المتابعة مع الأمانة
ZMD688 | Macro | Aspiration | HOC | HO to CW Done | Madinah | 2019 | 24.4884 | 39.6953 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 17/06/2019 13:24:03 | SNR1010600 | NOBODY | ACCEPTED | 2019-04-04 | 2019-04-07 | 2019-04-07 | 2019-04-09 | NA | NA | 2019-07-02 | 2019-07-09 | 2019-07-09 | 2019-07-09 | 2019-08-07 | 2019-10-13 | NA | NA | 410109 | 2019-10-13 | 2020-03-17 | 2019-07-06 | 24.4884 | 39.6953 | 2019-08-04 | 2019-08-05 | 35m-LP-GF |  | 2019-10-14 | Non-Private | Baladiya | امانة المدينة المنورة | 41/15 | 100000 | 400 | GF | Fahad Aljohany | HOC
ZMM058 | Macro | Aspiration | HOC | HO to CW Done | Madinah | 2020 | 25.6666 | 39.2928 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 21/05/2019 23:16:37 | SNR1010347 | NOBODY | ACCEPTED | 2019-03-24 | 2019-03-27 | 2019-03-27 | 2019-03-29 | 11/06/2019 15:55:51 | 13/06/2019 11:12:11 | [6 empty] | 2019-07-03 | 2019-07-30 | 0 | 2019-07-30 | 2019-08-01 | 2019-07-06 | 25.6666 | 39.2928 | 2019-08-04 | 2019-08-05 | 45M-E4-GF | 400M | 2019-08-06 | Private | Private | محمد موسى | 500545399 | 20000 | 400 | GF | Fahad Aljohany | HOC | bar: 2019-11-13 to 2020-02-19
ZMM082 | Macro | Aspiration | HOC | HO to CW Done | Madinah | 2020 | 25.5457 | 39.3368 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 25/04/2019 13:34:46 | SNR1009722 | NOBODY | ACCEPTED | 2019-03-24 | 2019-03-27 | 2019-03-27 | 2019-03-29 | 29/04/2019 14:44:14 | 08/05/2019 13:51:46 | [6 empty] | 2019-06-13 | 2019-06-13 | 0 | 2019-06-13 | 2019-07-02 | 2019-05-08 | 25.5457 | 39.3368 | 2019-07-01 | 2019-07-07 | 60m-E4-GF |  | 2019-07-07 | Private | Private | سعد نشر | 505368832 | 35000 | 400 | GF | Fahad Aljohany | HOC | bar: 2019-11-13 to 2020-02-19
ZMM202 | Macro | Aspiration | HOC | HO to CW Done | Madinah | 2019 | 24.4538 | 39.5203 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 09/09/2019 14:19:01 | SNR1011836 | NOBODY | ACCEPTED | 2019-03-26 | 2019-03-29 | 2019-03-29 | 2019-03-31 | NA | NA | 2019-08-25 | 2019-09-01 | 2019-09-01 | 2019-09-01 | 2019-12-22 | 2020-01-06 | NA | NA | 0 | 2020-01-13 | 2020-06-04 | 2019-11-17 | 24.4538 | 39.5203 | 2019-12-02 | 2019-11-04 | 35m-LP-GF | 20x20 | 2020-01-01 | Non-Private | Baladiya | أمانة المدينة المنورة | Non | 100000 | 400M | GF | Fahad Aljohany | HOC
ZMM203 | Macro | Aspiration | HOC | HO to CW Done | Madinah | 2019 | 24.426 | 39.4993 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 25/09/2019 09:12:06 | SNR1011929 | NOBODY | ACCEPTED | 2019-03-03 | 2019-03-06 | 2019-03-06 | 2019-03-08 | NA | NA | 2019-10-07 | 2019-10-14 | 2019-10-14 | 2019-10-14 | 2019-12-16 | 2020-01-06 | NA | NA | 0 | 2020-01-13 | 2020-06-04 | 2019-11-17 | 24.426 | 39.4993 | 2019-12-02 | 2019-11-04 | 35m-LP-GF | 15x15 | 2020-01-01 | Non-Private | Baladiya | أمانة المدينة المنورة | 41/38 | 100000 | 225 | GF | Fahad Aljohany | HOC
ZMM201 | Macro | Aspiration | HOC | HO to CW Done | Madinah | 2019 | 24.5621 | 39.6849 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 06/05/2019 13:44:58 | SNR1010106 | NOBODY | ACCEPTED | 2019-03-13 | 2019-03-16 | 2019-03-16 | 2019-03-18 | NA | NA | 2019-07-02 | 2019-07-09 | 2019-07-09 | 2019-07-09 | 2019-08-07 | 2019-10-13 | NA | NA | 410108 | 2019-10-13 | 2020-01-14 | 2019-07-06 | 24.5622 | 39.6848 | 2019-08-04 | 2019-08-05 | 25m-LP-GF |  | 2019-10-14 | Non-Private | Baladiya | امانة المدينة المنورة | 41/16 | 100000 | 144 | GF | Fahad Aljohany | HOC
ZMM083 | Macro | Aspiration | HOC | HO to CW Done | Madinah | 2019 | 23.4873 | 40.8766 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 30/04/2019 15:27:08 | SNR1009966 | NOBODY | ACCEPTED | 2019-03-04 | 2019-03-07 | 2019-03-07 | 2019-03-09 | NA | NA | 2019-08-19 | 2019-08-26 | 2019-08-26 | 2019-08-26 | 2019-09-08 | 2019-09-18 | NA | NA | NI-35/191 | 2019-09-18 | 2019-07-02 | 2019-06-26 | 23.4873 | 40.8766 | 2019-07-01 | 2019-07-07 | 45M-E4-GF |  | 2019-09-24 | Non-Private | Baladiya | بلدية المهــــد | ZMM083 | 28129 | 225 | GF | Fahad Aljohany | HOC
ZMM210 | Macro | Aspiration | HOC | HO to CW Done | Madinah | 2019 | 24.3881 | 39.6248 | Nokia | New Site | New Location | Hajj1440 |  | Macro | Doable |  | Approved | Approved | IGATE | 12/05/2019 13:30:24 | SNR1010203 | NOBODY | ACCEPTED | 2019-04-04 | 2019-04-07 | 2019-04-07 | 2019-04-09 | NA | NA | 2019-06-02 | 2019-06-09 | 2019-06-09 | 2019-06-09 | 2019-07-11 | 2019-08-18 | NA | NA | 404408 | 2019-08-18 | 2020-01-26 | 2019-06-20 | 24.3881 | 39.6248 | 2019-07-15 | 2019-06-16 | 35-GRD sharable |  | 2019-07-11 | Non-Private | Baladiya | امانة المدينة المنورة | 41/116 | 100000 | 400 | GF | Fahad Aljohany | HOC
ZMM212 | Macro | Aspiration | HOC | HO to CW Done | Madinah | 2019 | 24.4914 | 39.5139 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 30/04/2019 15:49:05 | SNR1009972 | NOBODY | ACCEPTED | 2019-03-17 | 2019-03-20 | 2019-03-20 | 2019-03-22 | 06/10/2019 10:23:53 | 13/10/2019 10:54:33 | [6 empty] | 2019-10-15 | 2019-10-17 | 143079 | 2019-10-17 | 2019-11-19 | 2019-07-06 | 24.4914 | 39.514 | 2019-11-24 | 2019-11-24 | 35M-LP-GF |  | 2019-11-24 | Private | Private | محمد رميزان امروانى | 566667580 | 55000 | 400 | GF | Fahad Aljohany | HOC | bar: 2019-11-13 to 2020-02-19
ZMM213 | Macro | Aspiration | HOC | HO to CW Done | Madinah | 2020 | 24.3784 | 39.5173 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 17/06/2019 12:48:27 | SNR1010586 | NOBODY | ACCEPTED | 2019-03-03 | 2019-03-06 | 2019-03-06 | 2019-03-08 | 09/10/2019 16:11:32 | 13/10/2019 13:37:26 | [6 empty] | 2019-10-20 | 2019-10-24 | 141357 | 2019-10-24 | 2019-11-21 | 2019-10-16 | 24.3783 | 39.5172 | 2019-11-24 | 2019-11-24 | 35M-LP-GF |  | 2019-11-24 | Private | Private | غازي سلامة الحجيلي | 504593884 | 45000 | 400 | GF | Fahad Aljohany | HOC | bar: 2019-11-13 to 2020-02-19
ZMM230 | Macro | Aspiration | HOC | HO to CW Done | Madinah | 2019 | 24.4843 | 39.5427 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 01/05/2019 09:48:36 | SNR1009987 | NOBODY | ACCEPTED | 2019-03-27 | 2019-03-30 | 2019-03-30 | 2019-04-01 | NA | NA | 2019-06-01 | 2019-12-10 | 2019-12-10 | 2019-12-10 | 2020-06-15 | 2020-06-04 | NA | NA | CEO-1/14 | 2020-06-04 | 2020-06-04 | 2019-09-22 | 24.4844 | 39.5427 | 2020-03-05 | 2020-03-06 | 35m-PT-Sharable |  | 2020-06-11 | Non-Private | GOV | جامعة طيبة | 39 | 70000 | 100 | GF | Fahad Aljohany | HOC
ZMM217 | Macro | Aspiration | HOC | HO to CW Done | Madinah | 2019 | 24.4664 | 39.4595 | Nokia | New Site | New Location | Hajj1440 |  | Macro | Doable |  | Approved | Approved | IGATE | 15/05/2019 17:22:25 | SNR1010270 | NOBODY | ACCEPTED | 2019-03-24 | 2019-03-27 | 2019-03-27 | 2019-03-29 | NA | NA | 2019-06-02 | 2019-06-09 | 2019-06-09 | 2019-06-09 | 2019-07-11 | 2019-08-18 | NA | NA | 404409 | 2019-08-18 | 2020-01-26 | 2019-06-20 | 24.4664 | 39.4595 | 2019-06-30 | 2019-06-20 | 35M-LP-GF |  | 2019-07-07 | Non-Private | Baladiya | امانة المدينة المنورة | 40/115 | 80000 | 324M | GF | Fahad Aljohany | HOC
ZMM233 | Macro | Aspiration | HOC | HO to CW Done | Madinah | 2020 | 24.8996 | 40.5058 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 30/10/2019 18:47:43 | SNR1012275 | NOBODY | ACCEPTED | 2019-03-05 | 2019-03-08 | 2019-03-08 | 2019-03-10 | NA | NA | 2019-09-18 | 2019-09-25 | 2019-09-25 | 2019-09-25 | 2019-11-12 | 2019-11-13 | NA | NA | 0 | 2019-11-13 | 2020-02-20 | 2019-11-02 | 24.8996 | 40.5058 | 2019-11-05 | 2019-11-05 | 35M-LP-GF |  | 2019-11-17 | Non-Private | Baladiya | بلدية الحناكية | ZMM233 | 30000 | 24.5 | GF | Fahad Aljohany | HOC
ZMM235 | Macro | Aspiration | HOC | HO to CW Done | Madinah | 2019 | 23.4978 | 40.8925 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 13/06/2019 15:57:14 | SNR1010515 | NOBODY | ACCEPTED | 2019-03-04 | 2019-03-07 | 2019-03-07 | 2019-03-09 | NA | NA | 2019-08-19 | 2019-08-26 | 2019-08-26 | 2019-08-26 | 2019-09-08 | 2019-09-18 | NA | NA | NI-35138 | 2019-09-18 | 2019-05-14 | 2019-08-25 | 23.4978 | 40.8925 | 2019-10-01 | 2019-10-01 | 35M-LP-GF |  | 2019-10-02 | Non-Private | Baladiya | بلدية المهــــد | ZMM235 | 3062.5 | 24.5 | GF | Fahad Aljohany | HOC
ZMM234 | Macro | Aspiration | HOC | HO to CW Done | Madinah | 2019 | 23.5048 | 40.8931 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 21/05/2019 23:26:09 | SNR1010348 | NOBODY | ACCEPTED | 2019-03-03 | 2019-03-06 | 2019-03-06 | 2019-03-08 | 09/06/2019 13:11:21 | 11/06/2019 12:17:23 | [6 empty] | 2019-06-20 | 2019-06-23 | 0 | 2019-06-23 | 2019-06-25 | 2019-06-26 | 23.5048 | 40.8931 | 2019-07-01 | 2019-07-01 | 45M-E4-GF |  | 2019-06-27 | Private | Private | عبدالعزيز زويد المطيري | 534617173 | 25000 | 400 | GF | Fahad Aljohany | HOC | bar: 2019-11-13 to 2020-02-19
ZMM941 | Macro | Aspiration | HOC | HO to CW Done | Madinah | 2020 | 24.3807 | 39.5501 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 17/06/2019 12:46:47 | SNR1010585 | NOBODY | ACCEPTED | 2019-01-21 | 2019-01-24 | 2019-01-24 | 2019-01-26 | NA | NA | 2019-07-02 | 2019-07-09 | 2019-07-09 | 2019-12-16 | 2019-12-16 | 2020-01-06 | NA | NA | COO-2/37 | 2020-01-13 | 2021-10-25 | 2019-11-17 | 24.3807 | 39.5501 | 2019-12-18 | 2019-10-17 | 45m-E4-GF | 20x20 | 2020-01-01 | Non-Private | Baladiya | أمانة المدينة المنورة | 41/39 | 100000 | 400 | GF | Fahad Aljohany | HOC
ZMM220 | Macro | Aspiration | HOC | HO to CW Done | Madinah | 2019 | 24.3726 | 39.6042 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 29/07/2019 17:37:11 | SNR1011497 | NOBODY | ACCEPTED | 2019-03-04 | 2019-03-07 | 2019-03-07 | 2019-03-09 | NA | NA | 2019-07-02 | 2019-07-09 | 2019-07-09 | 2019-07-09 | 2019-12-22 | 2020-01-06 | NA | NA | 0 | 2020-01-13 | 2020-06-04 | 2019-11-17 | 24.3724 | 39.6043 | 2019-12-02 | 2019-07-07 | 35m-LP-GF | 15x15 | 2020-01-01 | Non-Private | Baladiya | أمانة المدينة المنورة | Non | 100000 | 225M | GF | Fahad Aljohany | HOC
ZMM942 | Macro | Aspiration | HOC | HO to CW Done | Madinah | 2019 | 24.5036 | 39.7011 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 15/05/2019 22:11:12 | SNR1010273 | NOBODY | ACCEPTED | 2019-03-13 | 2019-03-16 | 2019-03-16 | 2019-03-18 | 09/06/2019 13:13:39 | 12/09/2019 15:04:08 | [6 empty] | 2019-09-19 | 2019-10-01 | 129935 | 2019-10-01 | 2019-10-16 | 2019-09-22 | 24.5036 | 39.7011 | 2019-10-17 | 2019-10-17 | 35M-LP-GF |  | 2019-10-21 | Private | Private | محمد السفرانى | 504352676 | 50000 | 400 | GF | Fahad Aljohany | HOC | bar: 2019-11-13 to 2020-02-19
ZMM944 | Macro | Aspiration | HOC | HO to CW Done | Madinah | 2020 | 24.4609 | 39.6104 | Nokia | New Site | New Location | Ram1441 |  | Macro | Doable |  | Approved | Approved | IGATE | 12/05/2019 14:44:05 | SNR1010216 | NOBODY | ACCEPTED | 2019-03-10 | 2019-03-10 | 2019-03-10 | 2019-03-10 | 2020-02-16 | 2020-03-19 | [6 empty] | 2020-03-19 | 2020-03-22 | 0 | 2020-03-31 | 2020-09-20 | 2020-03-26 | 24.4609 | 39.6104 | 2020-03-30 | 2020-04-01 | 9m-RT-Tower |  | 2020-04-09 | Private | Private | وقف عبد الله نياز | 505305350 | 50000 | all roof | RT | Fahad Aljohany | HOC | bar: 2019-11-13 to 2020-02-19
ZMM925 | Macro | Aspiration | HOC | HO to CW Done | Madinah | 2020 | 24.5185 | 39.5023 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 06/05/2019 13:54:06 | SNR1010107 | NOBODY | ACCEPTED | 2019-03-20 | 2019-03-23 | 2019-03-23 | 2019-03-25 | NA | NA | 2019-07-02 | 2019-07-09 | 2019-07-09 | 2019-07-09 | 2019-08-07 | 2019-10-13 | NA | NA | 410112 | 2019-10-13 | 2020-01-29 | 2019-07-06 | 24.5185 | 39.5023 | 2019-10-15 | 2019-10-15 | 45M-E4-GF |  | 2019-10-15 | Non-Private | Baladiya | امانة المدينة المنورة | 41/18 | 90000 | 400 | GF | Fahad Aljohany | HOC
ZMM926 | Macro | Aspiration | HOC | HO to CW Done | Madinah | 2020 | 24.4801 | 39.6569 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 21/05/2019 20:25:19 | SNR1010327 | NOBODY | ACCEPTED | 2019-03-16 | 2019-03-19 | 2019-03-19 | 2019-03-21 | NA | NA | 2019-07-02 | 2019-07-09 | 2019-07-09 | 2019-07-09 | 2019-08-07 | 2019-10-13 | NA | NA | 410113 | 2019-10-13 | 2020-01-28 | 2019-09-22 | 24.4798 | 39.6568 | 2019-10-14 | 2019-10-14 | 35M-LP-GF |  | 2019-10-14 | Non-Private | Baladiya | امانة المدينة المنورة | 41/20 | 100000 | 400 | GF | Fahad Aljohany | HOC
ZMM950 | Macro | Aspiration | HOC | HO to CW Done | Madinah | 2020 | 24.3575 | 39.5136 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 25/04/2019 13:47:26 | SNR1009723 | NOBODY | ACCEPTED | 2019-03-01 | 2019-03-04 | 2019-03-04 | 2019-03-06 | 31/07/2019 12:51:30 | 31/07/2019 16:26:02 | [6 empty] | 2019-08-07 | 2019-08-07 | 123702 | 2019-08-07 | 2019-11-05 | 2019-05-08 | 24.3575 | 39.5136 | 2019-07-15 | 2019-07-21 | 35M-LP-GF |  | 2019-11-06 | Private | Private | علي بخيت العوفي | 505307106 | 45000 | 320 | GF | Fahad Aljohany | HOC | bar: 2019-11-13 to 2020-02-19
ZMM946 | Macro | Aspiration | HOC | HO to CW Done | Madinah | 2019 | 24.4384 | 39.5286 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 06/05/2019 14:12:26 | SNR1010114 | SNR_I | District Support | 2019-03-27 | 2019-03-27 | 2019-03-27 | 2019-03-27 | NA | NA | 2019-08-04 | 2020-09-16 | 2020-09-16 | 2020-09-16 | 2020-09-21 | 2020-10-26 | NA | NA | COO-2/36 | 2020-10-28 | 2021-08-29 | 2021-08-29 | 24.439 | 39.5268 | 2020-02-24 | 2020-03-11 | 40m-LP-GF |  | 2020-09-30 | Non-Private | Baladiya | امانة المدينة المنورة |  |  |  | GF | Fahad Aljohany | HOC
ZMM952 | Macro | Aspiration | HOC | HO to CW Done | Madinah | 2019 | 24.4884 | 39.5947 | Nokia | New Site | New Location | Hajj1440 |  | Macro | Doable |  | Approved | Approved | IGATE | 06/05/2019 14:18:57 | SNR1010117 | NOBODY | ACCEPTED | 2019-03-19 | 2019-03-22 | 2019-03-22 | 2019-03-24 | 09/06/2019 11:28:42 | 11/06/2019 11:19:53 | [6 empty] | 2019-06-20 | 2019-05-28 | 0 | 2019-05-28 | 2019-07-03 | 2019-05-08 | 24.4884 | 39.5947 | 2019-06-24 | 2019-06-20 | WM-POLE-RT |  | 2019-07-07 | Private | Private | وقف قاضى زاده | 505308326 | 40000 | 300 | RT | Fahad Aljohany | HOC | bar: 2019-11-13 to 2020-02-19
ZMM986 | Macro | Aspiration | HOC | HO to CW Done | Madinah | 2019 | 24.4775 | 39.5556 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 01/05/2019 10:00:31 | SNR1009989 | NOBODY | ACCEPTED | 2019-03-14 | 2019-03-17 | 2019-03-17 | 2019-03-19 | NA | NA | 2019-06-05 | 2020-02-20 | 2020-02-20 | 2020-02-24 | 2020-03-02 | 2020-03-11 | NA | NA | CEO-1/14 | 2020-03-11 | 2020-12-01 | 2020-02-24 | 24.4775 | 39.5556 | 2020-03-03 | 2020-03-04 | 35m-LP-GF |  | 2020-03-12 | Non-Private | Baladiya | أمانة المدينة المنورة | 41/60 | 100000 | 24.5 | GF | Fahad Aljohany | HOC
ZMM927 | Macro | Aspiration | HOC | HO to CW Done | Madinah | 2019 | 24.4836 | 39.6521 | Nokia | New Site | New Location | Hajj1440 |  | Macro | Doable |  | Approved | Approved | IGATE | 12/05/2019 14:00:09 | SNR1010209 | NOBODY | ACCEPTED | 2019-03-20 | 2019-03-23 | 2019-03-23 | 2019-03-25 | NA | NA | 2019-06-02 | 2019-06-09 | 2019-06-09 | 2019-06-09 | 2019-07-11 | 2019-08-18 | NA | NA | 404398 | 2019-08-18 | 2020-01-21 | 2019-06-23 | 24.4836 | 39.6521 | 2019-06-30 | 2019-06-20 | 35M-LP-GF |  | 2019-07-07 | Non-Private | Baladiya | امانة المدينة المنورة | 40/114 | 100000 | 100 | GF | Fahad Aljohany | HOC
ZNM096 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2020 | 19.1443 | 42.1099 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 27/04/2019 16:27:52 | SNR1009736 | NOBODY | ACCEPTED | 2019-03-16 | 2019-03-19 | 2019-03-19 | 2019-03-21 | NA | NA | 2019-05-18 | 2019-06-01 | 2019-06-01 | 2019-06-01 | 2019-10-02 | 2019-10-02 | NA | NA | 0 | 2019-10-30 | 2019-11-20 | 2019-07-07 | 19.1443 | 42.1099 | 2019-05-25 | 2019-05-28 | 60m-E4-GF | 20X20 | 2019-11-17 | Non-Private | Baladiya | بلدية النماص | 144025 | 30000 | 400 | GF | Mohammed elshehry | HOC
ZNM099 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2020 | 19.1121 | 42.1352 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 17/06/2019 18:08:17 | SNR1010629 | NOBODY | ACCEPTED | 2019-03-16 | 2019-03-19 | 2019-03-19 | 2019-03-19 | 2020-01-05 | 2020-01-05 | [6 empty] | 2020-01-12 | 2020-01-19 | 0 | 2020-01-19 | 2020-04-09 | 2019-07-07 | 19.1121 | 42.1352 | 2019-12-31 | 2020-01-06 | 45m-E4-GF | 20X20 | 2020-01-21 | Private | Private | صالح البكري | 505727828 | 25000 | 400M | GF | Mohammed elshehry | HOC | bar: 2019-11-13 to 2020-02-19
ZTF327 | Macro | Aspiration | HOC | HO to CW Done | Taif | 2019 | 21.4347 | 40.4985 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 28/04/2019 16:08:36 | SNR1009774 | NOBODY | ACCEPTED | 2019-03-05 | 2019-03-08 | 2019-03-08 | 2019-03-10 | NA | NA | 2019-09-01 | 2019-09-08 | 2019-09-08 | 2019-09-08 | 2019-06-15 | 2019-06-18 | NA | NA | 40001165 | 2019-06-18 | 2019-11-21 | 2019-06-29 | 21.4347 | 40.4985 | 2019-07-09 | 2019-07-09 | 35M-LP-GF |  | 2019-11-17 | Non-Private | Baladiya | امانة الطائف | 440/450 | 30000 | 400 | GF | Fahad Alrogy | HOC
ZMM934 | Macro | Aspiration | HOC | HO to CW Done | Madinah | 2019 | 24.4208 | 39.5856 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 21/05/2019 23:59:02 | SNR1010349 | NOBODY | ACCEPTED | 2019-04-04 | 2019-04-07 | 2019-04-07 | 2019-04-09 | NA | NA | 2019-07-02 | 2019-07-09 | 2019-07-09 | 2019-07-09 | 2019-08-07 | 2019-10-13 | NA | NA | 410114 | 2019-10-13 | 2020-01-14 | 2019-09-22 | 24.4207 | 39.5856 | 2019-10-14 | 2019-10-14 | 35M-LP-GF |  | 2019-10-14 | Non-Private | Baladiya | امانة المدينة المنورة | 41/14 | 100000 | 400 | GF | Fahad Aljohany | HOC
ZTF329 | Macro | Aspiration | HOC | HO to CW Done | Taif | 2019 | 21.2438 | 40.419 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 01/05/2019 10:10:34 | SNR1009990 | NOBODY | ACCEPTED | 2019-03-10 | 2019-03-13 | 2019-03-13 | 2019-03-15 | NA | NA | 2019-06-09 | 2019-06-16 | 2019-06-16 | 2019-06-16 | 2019-06-20 | 2019-06-27 | NA | NA | 0 | 2019-06-27 | 2019-06-30 | 2019-06-30 | 21.2438 | 40.419 | 2019-07-09 | 2019-07-09 | 35M-LP-GF |  | 2019-08-20 | Non-Private | Baladiya | Taif Municipality | 440/448 | 30000 | 196 | GF | Fahad Alrogy | HOC
ZTF331 | Macro | Aspiration | HOC | HO to CW Done | Taif | 2020 | 21.2815 | 40.3969 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 28/04/2019 14:51:51 | SNR1009766 | NOBODY | ACCEPTED | 2019-03-12 | 2019-03-15 | 2019-03-15 | 2019-03-17 | NA | NA | 2019-06-08 | 2019-06-15 | 2019-06-15 | 2019-06-15 | 2019-09-08 | 2019-10-01 | NA | NA | 41000126 | 2019-10-01 | 2019-11-12 | 2019-06-30 | 21.2815 | 40.3969 | 2019-10-13 | 2019-10-13 | 35m-Holly Name |  | 2019-11-11 | Non-Private | Baladiya | امانة الطائف | 441/462 | 30000 | 400 | GF | Fahad Alrogy | HOC
ZTF334 | Macro | Aspiration | HOC | HO to CW Done | Taif | 2019 | 21.9177 | 42.0276 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 28/04/2019 15:01:32 | SNR1009768 | NOBODY | ACCEPTED | 2019-03-09 | 2019-03-12 | 2019-03-12 | 2019-03-14 | NA | NA | 2019-07-09 | 2019-07-16 | 2019-07-16 | 2019-07-16 | 2019-08-07 | 2019-07-11 | NA | NA | 0 | 2019-07-11 | 2019-08-26 | 2019-07-08 | 21.9177 | 42.0276 | 2019-07-31 | 2019-07-31 | 45M-E4-GF | 400M | 2019-09-02 | Non-Private | Baladiya | Khurma Municipality | ZTF334 | 20000 | 400 | GF | Fahad Alrogy | HOC
ZTF337 | Macro | Aspiration | HOC | HO to CW Done | Taif | 2019 | 21.4572 | 40.4846 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 01/05/2019 10:22:25 | SNR1009992 | NOBODY | ACCEPTED | 2019-03-04 | 2019-03-07 | 2019-03-07 | 2019-03-09 | NA | NA | 2019-06-09 | 2019-06-16 | 2019-06-16 | 2019-06-16 | 2019-06-20 | 2019-06-27 | NA | NA | 0 | 2019-06-27 | 2019-06-30 | 2019-06-13 | 21.4572 | 40.4846 | 2019-07-28 | 2019-07-30 | 35M-LP-GF | 20 X 20 | 2019-08-20 | Non-Private | Baladiya | Taif Municipality | 440/444 | 30000 | 196 | GF | Fahad Alrogy | HOC
ZMM973 | Macro | Aspiration | HOC | HO to CW Done | Madinah | 2019 | 24.4164 | 39.5003 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 01/05/2019 12:32:18 | SNR1010000 | NOBODY | ACCEPTED | 2019-03-19 | 2019-03-22 | 2019-03-22 | 2019-03-24 | 16/06/2019 12:18:08 | 18/06/2019 16:32:23 | [6 empty] | 2019-07-15 | 2019-07-18 | 113042 | 2019-07-18 | 2019-10-10 | 2019-05-08 | 24.4164 | 39.5003 | 2019-07-15 | 2019-07-21 | 35M-LP-GF | 20 X 19 | 2019-10-10 | Private | Private | عوض ضيف الله الجابري | 591187088 | 43000 | 380 | GF | Fahad Aljohany | HOC | bar: 2019-11-13 to 2020-02-19
ZMM955 | Macro | Aspiration | HOC | HO to CW Done | Madinah | 2020 | 24.3822 | 39.616 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 15/05/2019 22:14:53 | SNR1010274 | NOBODY | ACCEPTED | 2019-03-27 | 2019-03-30 | 2019-03-30 | 2019-04-01 | 16/09/2019 16:57:47 | 17/09/2019 11:02:09 | [6 empty] | 2019-10-15 | 2019-10-31 | 0 | 2019-10-31 | 2019-11-19 | 2019-09-22 | 24.3822 | 39.616 | 2019-11-24 | 2019-11-24 | 35m-LP-GF |  | 2019-11-17 | Private | Private | ورثه طالع المطيرى | 505550270 | 47000 | 436.37 | GF | Fahad Aljohany | HOC | bar: 2019-11-13 to 2020-02-19
ZTF340 | Macro | Aspiration | HOC | HO to CW Done | Taif | 2020 | 21.4638 | 40.4263 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 21/11/2019 08:49:04 | SNR1012380 | NOBODY | ACCEPTED | 2019-03-20 | 2019-03-20 | 2019-08-04 | 2019-08-04 | 2019-08-03 | 2019-12-12 | [6 empty] | 2019-12-12 | 2019-12-22 | 0 | 2019-12-22 | 2020-02-13 | 2019-07-01 | 21.4638 | 40.4263 | 2020-01-27 | 2020-01-28 | 60m-E4-GF | 400 | 2020-01-21 | Private | Private | مسعود بن سليمان العصيمي | 505704683 | 40000 | 20X20 | GF | Fahad Alrogy | HOC | bar: 2019-11-13 to 2020-02-19
ZTF341 | Macro | Aspiration | HOC | HO to CW Done | Taif | 2020 | 21.3714 | 40.2886 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 02/05/2019 18:13:52 | SNR1010032 | NOBODY | ACCEPTED | 2019-03-20 | 2019-03-23 | 2019-03-23 | 2019-03-25 | NA | NA | 2019-06-08 | 2019-06-15 | 2019-06-15 | 2019-06-15 | 2019-09-08 | 2019-10-01 | NA | NA | 41000127 | 2019-10-01 | 2019-11-12 | 2019-06-30 | 21.3714 | 40.2886 | 2019-07-07 | 2019-07-08 | 45M-E4-GF |  | 2019-11-11 | Non-Private | Baladiya | امانة الطائف | 441/464 | 30000 | 400 | GF | Fahad Alrogy | HOC
ZTF346 | Macro | Aspiration | HOC | HO to CW Done | Taif | 2020 | 20.7244 | 40.8332 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 29/04/2019 13:29:36 | SNR1009804 | NOBODY | ACCEPTED | 2019-03-20 | 2019-03-23 | 2019-03-23 | 2019-03-25 | NA | NA | 2019-08-12 | 2019-11-11 | 2019-11-11 | 2019-11-11 | 2019-11-28 | 2019-12-15 | NA | NA | 300370 | 2019-12-15 | 2019-12-15 | 2019-06-30 | 20.7244 | 40.8332 | 2019-07-10 | 2019-07-11 | 60m-E4-GF | 20 X 20 | 2019-12-15 | Non-Private | Baladiya | بلدية ميسان | ث/40/127 | 20000 | 400 | GF | Fahad Alrogy | HOC
ZTF449 | Macro | Aspiration | HOC | HO to CW Done | Taif | 2020 | 21.2077 | 40.3565 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 17/06/2019 17:59:53 | SNR1010626 | NOBODY | ACCEPTED | 2019-08-18 | 2019-08-21 | 2019-08-21 | 2019-08-23 | NA | NA | 2019-09-01 | 2019-09-08 | 2019-09-08 | 2019-09-08 | 2019-10-06 | 2019-10-20 | NA | NA | 41000157 | 2019-10-20 | 2019-11-14 | 2019-08-25 | 21.2077 | 40.3565 | 2019-10-09 | 2019-10-09 | 45M-E4-GF |  | 2019-11-10 | Non-Private | Baladiya | امانة الطائف | 441/465 | 30000 | 400 | GF | Fahad Alrogy | HOC
ZTF342 | Macro | Aspiration | HOC | HO to CW Done | Taif | 2020 | 21.2124 | 40.3899 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 29/04/2019 13:11:29 | SNR1009803 | NOBODY | ACCEPTED | 2019-03-19 | 2019-03-22 | 2019-03-22 | 2019-03-24 | 12/05/2019 14:43:17 | 16/05/2019 13:44:07 | [6 empty] | 2019-07-03 | 2019-05-26 | 0 | 2019-05-26 | 2019-07-07 | 2019-07-08 | 21.2124 | 40.3899 | 2019-07-31 | 2019-07-25 | 45M-E4-GF |  | 2019-08-01 | Private | Private | عبد الله حسين عوض الله النفيعي | 500511551 | 30000 | 400 | GF | Fahad Alrogy | HOC | bar: 2019-11-13 to 2020-02-19
ZTF348 | Macro | Aspiration | HOC | HO to CW Done | Taif | 2020 | 21.2205 | 40.6058 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 01/05/2019 12:01:09 | SNR1009998 | NOBODY | ACCEPTED | 2019-03-18 | 2019-03-21 | 2019-03-21 | 2019-03-23 | NA | NA | 2019-06-09 | 2019-06-16 | 2019-06-16 | 2019-06-16 | 2019-06-20 | 2019-06-27 | NA | NA | 40001166 | 2019-06-27 | 2019-06-30 | 2019-06-13 | 21.2205 | 40.6058 | 2019-07-01 | 2019-07-07 | 45M-E4-GF |  | 2019-08-06 | Non-Private | Baladiya | Taif Municipality | 440/443 | 30000 | 400 | GF | Fahad Alrogy | HOC
ZTF349 | Macro | Aspiration | HOC | HO to CW Done | Taif | 2020 | 21.1251 | 40.8365 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 23/12/2019 19:45:05 | SNR1012521 | NOBODY | ACCEPTED | 2019-03-18 | 2019-03-21 | 2019-03-21 | 2019-03-23 | 2019-10-01 | 2019-10-02 | [6 empty] | 2020-01-23 | 2020-01-28 | 0 | 2020-01-30 | 2020-03-08 | 2019-12-24 | 21.1242 | 40.8368 | 2020-01-22 | 2020-01-29 | 60m-E4-GF | 20 X 20 | 2020-01-28 | Private | Private | ساير الجعيد | 504704920 | 20000 | 400M | GF | Fahad Alrogy | HOC | bar: 2019-11-13 to 2020-02-19
ZMK163 | Macro | Aspiration | HOC | HO to CW Done | Makkah | 2020 | 21.4312 | 39.8369 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 30/04/2019 11:34:12 | SNR1009898 | NOBODY | ACCEPTED | 2019-03-14 | 2019-03-17 | 2019-03-17 | 2019-03-19 | NA | NA | 2019-03-26 | 2021-06-05 | 2021-06-05 | 2021-06-05 | 2021-06-05 | 2021-06-05 | NA | NA | 4005513073 | 2019-09-29 | 2019-10-20 | 2019-10-15 | 21.4312 | 39.8369 | 2019-08-06 | 2019-08-06 | 36m-E4-GF | 10 X 10 | 2019-10-21 | Non-Private | Baladiya | أمانة مكة المكرمة |  | NA | 10 X 10 | GF | Adnan Alqorashy | HOC
ZMM951 | Macro | Aspiration | HOC | HO to CW Done | Madinah | 2019 | 24.4601 | 39.4994 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 22/05/2019 00:33:27 | SNR1010351 | NOBODY | ACCEPTED | 2019-03-17 | 2019-03-20 | 2019-03-20 | 2019-03-22 | NA | NA | 2019-07-02 | 2019-07-09 | 2019-07-09 | 2019-07-09 | 2019-08-07 | 2019-10-13 | NA | NA | 410115 | 2019-10-13 | 2020-01-14 | 2019-07-06 | 24.4603 | 39.4993 | 2019-08-04 | 2019-08-05 | 35M-LP-GF |  | 2019-10-14 | Non-Private | Baladiya | امانة المدينة المنورة | 41/17 | 100000 | 400 | GF | Fahad Aljohany | HOC
ZTF419 | Macro | Aspiration | HOC | HO to CW Done | Taif | 2019 | 21.5318 | 40.6064 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 29/04/2019 14:28:42 | SNR1009809 | NOBODY | ACCEPTED | 2019-03-14 | 2019-03-17 | 2019-03-17 | 2019-03-19 | 26/05/2019 13:47:30 | 18/06/2019 15:22:28 | [6 empty] | 2019-07-03 | 2019-07-07 | 0 | 2019-07-07 | 2019-07-07 | 2019-07-11 | 21.53176 | 40.6064 | 2019-07-31 | 2019-07-25 | 60m-E4-GF |  | 2019-08-01 | Private | Private | محمد مبارك القرشي | 555584795 | 25000 | 400 | GF | Fahad Alrogy | HOC | bar: 2019-11-13 to 2020-02-19
ZTF429 | Macro | Aspiration | HOC | HO to CW Done | Taif | 2020 | 21.3415 | 40.5662 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 29/04/2019 13:49:53 | SNR1009807 | NOBODY | ACCEPTED | 2019-03-07 | 2019-03-10 | 2019-03-10 | 2019-03-12 | NA | NA | 2019-06-26 | 2019-07-03 | 2019-07-03 | 2019-07-03 | 2019-07-03 | 2019-08-20 | NA | NA | 0 | 2019-08-20 | 2019-06-11 | 2019-06-30 | 21.3415 | 40.5662 | 2019-07-07 | 2019-07-07 | 45M-E4-GF |  | 2019-08-06 | Non-Private | Baladiya | Taif Municipality | 440/456 | 30000 | 400 | GF | Fahad Alrogy | HOC
ZTF487 | Macro | Aspiration | HOC | HO to CW Done | Taif | 2019 | 21.9057 | 42.0062 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 17/06/2019 17:57:30 | SNR1010625 | NOBODY | ACCEPTED | 2019-06-14 | 2019-06-14 | 2019-08-13 | 2019-08-13 | NA | NA | 2019-11-01 | 2019-12-23 | 2019-12-29 | 2020-01-05 | 2020-01-05 | 2020-01-05 | NA | NA | 1191 | 2020-01-08 | 2020-01-13 | 2020-01-02 | 21.9057 | 42.0062 | 2020-01-09 | 2020-01-12 | 60m-E4-GF | 20X20 | 2020-01-01 | Non-Private | Baladiya | بلدية الخرمه | ZTF487 | 20000 | 400 | GF | Fahad Alrogy | HOC
ZTF430 | Macro | Aspiration | HOC | HO to CW Done | Taif | 2020 | 21.3521 | 40.5409 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 24/04/2019 16:57:51 | SNR1009704 | NOBODY | ACCEPTED | 2019-03-16 | 2019-03-19 | 2019-03-19 | 2019-03-21 | NA | NA | 2019-06-09 | 2019-06-16 | 2019-06-16 | 2019-06-16 | 2019-06-20 | 2019-06-27 | NA | NA | 40001168 | 2019-06-27 | 2019-06-30 | 2019-06-30 | 21.35211 | 40.5409 | 2019-07-10 | 2019-07-10 | 60m-E4-GF |  | 2019-08-19 | Non-Private | Baladiya | Taif Municipality | 440/449 | 30000 | 400 | GF | Fahad Alrogy | HOC
ZMK569 | Macro | Aspiration | Pending LA | IBP Not Issued | Makkah | 2020 | 21.4289 | 39.8293 | Nokia | New Site | New Location | Ram1441 |  | Macro | Doable |  | Approved | Approved | IGATE | 01/05/2019 15:10:04 | SNR1010011 | NOBODY | ACCEPTED | 2019-03-03 | 2019-03-03 | 2019-03-03 | 2019-03-03 | NA | NA | 2019-11-13: 2021-11-09 | NA | NA | CTR-21-11-000522 |  |  | 2021-06-30 | 21.4293 | 39.8299 | 2021-07-12 | 2021-07-25 | 35m-LP-GF | 10X10 |  | Non-Private | Baladiya | أمانة مكة المكرمة |  | NA | 3X7 | GF | Adnan Alqorashy | تم إعادة رفع معاملة طلب العقود من الأمانة على نظام فرص وجاري المتابعة مع الأمانة
ZMM948 | Macro | Aspiration | HOC | HO to CW Done | Madinah | 2020 | 24.4262 | 39.5302 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 17/06/2019 13:01:39 | SNR1010593 | NOBODY | ACCEPTED | 2019-04-04 | 2019-04-07 | 2019-04-07 | 2019-04-09 | 01/10/2019 15:05:12 | 03/10/2019 11:19:51 | [6 empty] | 2019-10-10 | 2019-10-17 | 142321 | 2019-10-17 | 2019-11-24 | 2019-09-22 | 24.4262 | 39.5303 | 2019-11-24 | 2019-11-24 | 35m-LP-GF |  | 2019-11-11 | Private | Private | الوكيل عمر صالح | 533133398 | 40000 | 400 | GF | Fahad Aljohany | HOC | bar: 2019-11-13 to 2020-02-19
ZTF440 | Macro | Aspiration | HOC | HO to CW Done | Taif | 2019 | 21.4747 | 40.4802 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 30/04/2019 13:09:57 | SNR1009924 | NOBODY | ACCEPTED | 2019-03-17 | 2019-03-20 | 2019-03-20 | 2019-03-22 | 18/06/2019 10:48:23 | 18/06/2019 15:28:13 | [6 empty] | 2019-07-03 | 2019-07-07 | 0 | 2019-07-07 | 2019-07-07 | 2019-06-30 | 21.4747 | 40.4802 | 2019-07-07 | 2019-07-07 | 45M-E4-GF |  | 2019-08-06 | Private | Private | فهد سعود الذيابي | 505705951 | 30000 | 400 | GF | Fahad Alrogy | HOC | bar: 2019-11-13 to 2020-02-19
ZTF491 | Macro | Aspiration | HOC | HO to CW Done | Taif | 2019 | 21.4983 | 40.5073 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 02/05/2019 18:44:11 | SNR1010033 | NOBODY | ACCEPTED | 2019-04-30 | 2019-05-03 | 2019-05-03 | 2019-05-05 | NA | NA | 2019-06-09 | 2019-06-16 | 2019-06-16 | 2019-06-16 | 2019-09-19 | 2019-10-01 | NA | NA | 41000128 | 2019-10-01 | 2019-11-12 | 2019-08-25 | 21.4983 | 40.5073 | 2019-10-15 | 2019-10-16 | 60m-E4-GF |  | 2019-11-11 | Non-Private | Baladiya | امانة الطائف | 441/463 | 30000 | 400 | GF | Fahad Alrogy | HOC
ZTF439 | Macro | Aspiration | HOC | HO to CW Done | Taif | 2020 | 21.4744 | 40.4955 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 24/04/2019 17:03:26 | SNR1009705 | NOBODY | ACCEPTED | 2019-03-13 | 2019-03-16 | 2019-03-16 | 2019-03-18 | NA | NA | 2019-06-09 | 2019-06-16 | 2019-06-16 | 2019-06-16 | 2019-06-20 | 2019-06-27 | NA | NA | 40001167 | 2019-06-27 | 2019-06-30 | 2019-06-13 | 21.4744 | 40.4955 | 2019-06-27 | 2019-07-01 | 45M-E4-GF |  | 2019-10-07 | Non-Private | Baladiya | Taif Municipality | 440/445 | 30000 | 20X20 | GF | Fahad Alrogy | HOC
CWN201 | COW | Aspiration | HOC | HO to CW Done | Makkah | 2019 | 21.3709 | 39.9894 | Nokia | New Site | New Location | Ram1441 |  | COW | Doable |  | Approved | Approved | IGATE | 21/05/2019 21:25:01 | SNR1010335 | NOBODY | ACCEPTED | 2019-05-14 | 2019-05-17 | 2019-05-17 | 2019-05-19 | NA | NA | 2019-05-19 | 2019-05-19 | 2019-05-19 | 2019-05-19 | 2019-05-19 | 2019-05-19 | NA | NA | 0 | 2019-06-15 | 2019-06-15 | 2019-06-12 | 21.3709 | 39.9894 | 2019-06-11 | 2019-06-11 | COW - 15m | 4.5X12 | 2019-06-15 | Non-Private | Baladiya | أمانة مكة المكرمة |  | NA | 4.5X12 | GF | Adnan Alqorashy | HOC
CWN202 | COW | Aspiration | HOC | HO to CW Done | Makkah | 2019 | 21.3444 | 39.9594 | Nokia | New Site | New Location | Ram1441 |  | COW | Doable |  | Approved | Approved | IGATE | 21/05/2019 20:43:36 | SNR1010328 | NOBODY | ACCEPTED | 2019-05-14 | 2019-05-17 | 2019-05-17 | 2019-05-19 | NA | NA | 2019-05-19 | 2019-05-19 | 2019-05-19 | 2019-05-19 | 2019-05-19 | 2019-05-19 | NA | NA | 0 | 2019-06-15 | 2019-06-15 | 2019-06-12 | 21.3444 | 39.9594 | 2019-06-11 | 2019-06-11 | COW- 10m | 4.5X12 | 2019-06-15 | Non-Private | Baladiya | أمانة مكة المكرمة |  | NA | 4.5X12 | GF | Adnan Alqorashy | HOC
CWN203 | COW | Aspiration | HOC | HO to CW Done | Makkah | 2019 | 21.3422 | 39.9607 | Nokia | New Site | New Location | Ram1441 |  | COW | Doable |  | Approved | Approved | IGATE | 21/05/2019 20:48:33 | SNR1010329 | NOBODY | ACCEPTED | 2019-05-14 | 2019-05-17 | 2019-05-17 | 2019-05-19 | NA | NA | 2019-05-19 | 2019-05-19 | 2019-05-19 | 2019-05-19 | 2019-05-19 | 2019-05-19 | NA | NA | 0 | 2019-06-15 | 2019-06-15 | 2019-06-12 | 21.3422 | 39.9607 | 2019-06-11 | 2019-06-11 | COW - 12m | 4.5X12 | 2019-06-15 | Non-Private | Baladiya | أمانة مكة المكرمة |  | NA | 4.5X12 | GF | Adnan Alqorashy | HOC
ZTF495 | Macro | Aspiration | HOC | HO to CW Done | Taif | 2019 | 21.209 | 40.3695 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 17/06/2019 17:54:25 | SNR1010624 | NOBODY | ACCEPTED | 2019-03-17 | 2019-03-20 | 2019-03-20 | 2019-03-20 | NA | NA | 2019-10-03 | 2019-12-17 | 2019-12-17 | 2019-12-17 | 2019-12-17 | 2019-12-17 | NA | NA | مشاركة موبايلي | 2019-12-17 | 2019-12-17 | 2019-08-25 | 21.209 | 40.3695 | 2019-10-03 | 2019-10-06 | Sharing with Operator |  | 2019-12-17 | Non-Private | Sharing | Sharing With Mobily | NA | NA | Sharing | Sharing | Fahad Alrogy | HOC
CWN204 | COW | Aspiration | HOC | HO to CW Done | Makkah | 2019 | 21.3405 | 39.9955 | Nokia | New Site | New Location | Ram1441 |  | COW | Doable |  | Approved | Approved | IGATE | 21/05/2019 20:54:31 | SNR1010330 | NOBODY | ACCEPTED | 2019-05-14 | 2019-05-17 | 2019-05-17 | 2019-05-19 | NA | NA | 2019-05-19 | 2019-05-19 | 2019-05-19 | 2019-05-19 | 2019-05-19 | 2019-05-19 | NA | NA | 0 | 2019-06-15 | 2019-06-15 | 2019-06-12 | 21.3405 | 39.9955 | 2019-06-11 | 2019-06-11 | COW - 12m | 4.5X12 | 2019-06-15 | Non-Private | Baladiya | أمانة مكة المكرمة |  | NA | 4.5X12 | GF | Adnan Alqorashy | HOC
CWN205 | COW | Aspiration | HOC | HO to CW Done | Makkah | 2019 | 21.3762 | 39.9823 | Nokia | New Site | New Location | Ram1441 |  | COW | Doable |  | Approved | Approved | IGATE | 21/05/2019 20:59:26 | SNR1010331 | NOBODY | ACCEPTED | 2019-05-14 | 2019-05-17 | 2019-05-17 | 2019-05-19 | NA | NA | 2019-05-19 | 2019-05-19 | 2019-05-19 | 2019-05-19 | 2019-05-19 | 2019-05-19 | NA | NA | 0 | 2019-06-15 | 2019-06-15 | 2019-06-12 | 21.3762 | 39.9823 | 2019-06-11 | 2019-06-11 | COW - 15m | 4.5X12 | 2019-06-15 | Non-Private | Baladiya | أمانة مكة المكرمة |  | NA | 4.5X12 | GF | Adnan Alqorashy | HOC
CWN206 | COW | Aspiration | HOC | HO to CW Done | Makkah | 2019 | 21.3592 | 39.974 | Nokia | New Site | New Location | Ram1441 |  | COW | Doable |  | Approved | Approved | IGATE | 21/05/2019 21:07:19 | SNR1010332 | NOBODY | ACCEPTED | 2019-05-14 | 2019-05-17 | 2019-05-17 | 2019-05-19 | NA | NA | 2019-05-19 | 2019-05-19 | 2019-05-19 | 2019-05-19 | 2019-05-19 | 2019-05-19 | NA | NA | 0 | 2019-06-15 | 2019-06-15 | 2019-06-12 | 21.3592 | 39.974 | 2019-06-11 | 2019-06-11 | COW - 15m | 4.5X12 | 2019-06-15 | Non-Private | Baladiya | أمانة مكة المكرمة |  | NA | 4.5X12 | GF | Adnan Alqorashy | HOC
ZMC317 | Macro | Aspiration | HOC | HO to CW Done | Makkah | 2019 | 21.3895 | 39.7938 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 14/05/2019 22:43:07 | SNR1010254 | NOBODY | ACCEPTED | 2019-03-18 | 2019-03-21 | 2019-03-21 | 2019-03-23 | 23/10/2019 14:18:00 | 26/10/2019 13:53:34 | [6 empty] | 2019-11-03 | 2019-11-10 | 0 | 2019-11-10 | 2020-03-01 | 2019-11-10 | 21.3895 | 39.7938 | 2019-10-17 | 2019-10-17 | WM-Pole-RT | 10X10 | 2019-11-24 | Private | Private | علي الزهراني | 503515913 | 35000 | RT | RT | Adnan Alqorashy | HOC | bar: 2019-11-13 to 2020-02-19
CWN207 | COW | Aspiration | HOC | HO to CW Done | Makkah | 2019 | 21.3692 | 39.9772 | Nokia | New Site | New Location | Ram1441 |  | COW | Doable |  | Approved | Approved | IGATE | 21/05/2019 21:14:17 | SNR1010333 | NOBODY | ACCEPTED | 2019-05-14 | 2019-05-17 | 2019-05-17 | 2019-05-19 | NA | NA | 2019-05-19 | 2019-05-19 | 2019-05-19 | 2019-05-19 | 2019-05-19 | 2019-05-19 | NA | NA | 0 | 2019-06-15 | 2019-06-15 | 2019-06-12 | 21.3692 | 39.9772 | 2019-06-11 | 2019-06-11 | COW - 15m | 4.5X12 | 2019-06-15 | Non-Private | Baladiya | أمانة مكة المكرمة |  | NA | 4.5X12 | GF | Adnan Alqorashy | HOC
ZTF448 | Macro | Aspiration | HOC | HO to CW Done | Taif | 2020 | 22.4363 | 41.7547 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 02/05/2019 17:32:11 | SNR1010028 | NOBODY | ACCEPTED | 2019-03-23 | 2019-03-26 | 2019-03-26 | 2019-03-28 | 23/05/2019 16:53:53 | 26/05/2019 14:02:59 | [6 empty] | 2019-06-20 | 2019-06-25 | 0 | 2019-06-25 | 2019-06-24 | 2019-06-23 | 22.4363 | 41.7547 | 2019-06-27 | 2019-06-27 | 45M-E4-GF |  | 2019-06-27 | Private | Private | بزيع شديد العتيبي | 503416116 | 20000 | 400 | GF | Fahad Alrogy | HOC | bar: 2019-11-13 to 2020-02-19
CWN208 | COW | Aspiration | HOC | HO to CW Done | Makkah | 2019 | 21.3934 | 39.9166 | Nokia | New Site | New Location | Ram1441 |  | COW | Doable |  | Approved | Approved | IGATE | 21/05/2019 21:20:12 | SNR1010334 | NOBODY | ACCEPTED | 2019-05-15 | 2019-05-18 | 2019-05-18 | 2019-05-20 | NA | NA | 2019-05-19 | 2019-05-19 | 2019-05-19 | 2019-05-19 | 2019-05-19 | 2019-05-19 | NA | NA | 0 | 2019-06-15 | 2019-06-15 | 2019-06-12 | 21.3934 | 39.9166 | 2019-06-11 | 2019-06-11 | COW- 10m | 4.5X12 | 2019-06-15 | Non-Private | Baladiya | أمانة مكة المكرمة |  | NA | 4.5X12 | GF | Adnan Alqorashy | HOC
CWN209 | COW | Aspiration | HOC | HO to CW Done | Makkah | 2019 | 21.3917 | 39.8962 | Nokia | New Site | New Location | Ram1441 |  | COW | Doable |  | Approved | Approved | IGATE | 21/05/2019 21:38:24 | SNR1010336 | NOBODY | ACCEPTED | 2019-05-15 | 2019-05-18 | 2019-05-18 | 2019-05-20 | NA | NA | 2019-05-19 | 2019-05-19 | 2019-05-19 | 2019-05-19 | 2019-05-19 | 2019-05-19 | NA | NA | 0 | 2019-06-15 | 2019-06-15 | 2019-06-12 | 21.3917 | 39.8962 | 2019-06-11 | 2019-06-11 | COW - 15m | 4.5X12 | 2019-06-15 | Non-Private | Baladiya | أمانة مكة المكرمة |  | NA | 4.5X12 | GF | Adnan Alqorashy | HOC
ZTF478 | Macro | Aspiration | HOC | HO to CW Done | Taif | 2020 | 21.3037 | 40.445 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 05/05/2019 18:50:44 | SNR1010085 | NOBODY | ACCEPTED | 2019-03-27 | 2019-03-30 | 2019-03-30 | 2019-04-01 | NA | NA | 2019-06-09 | 2019-06-16 | 2019-06-16 | 2019-06-16 | 2019-06-20 | 2019-06-27 | NA | NA | 0 | 2019-06-27 | 2019-06-30 | 2019-06-30 | 21.3037 | 40.445 | 2019-07-13 | 2019-07-14 | 35M-LP-GF |  | 2019-08-20 | Non-Private | Baladiya | Taif Municipality | 440/452 | 30000 | 196 | GF | Fahad Alrogy | HOC
CWN210 | COW | Aspiration | HOC | HO to CW Done | Makkah | 2019 | 21.3829 | 39.9045 | Nokia | New Site | New Location | Ram1441 |  | COW | Doable |  | Approved | Approved | IGATE | 21/05/2019 21:42:49 | SNR1010337 | NOBODY | ACCEPTED | 2019-05-15 | 2019-05-18 | 2019-05-18 | 2019-05-20 | NA | NA | 2019-05-19 | 2019-05-19 | 2019-05-19 | 2019-05-19 | 2019-05-19 | 2019-05-19 | NA | NA | 0 | 2019-06-15 | 2019-06-15 | 2019-06-12 | 21.3829 | 39.9045 | 2019-06-11 | 2019-06-11 | COW - 15m | 4.5X12 | 2019-06-15 | Non-Private | Baladiya | أمانة مكة المكرمة |  | NA | 4.5X12 | GF | Adnan Alqorashy | HOC
CWN211 | COW | Aspiration | HOC | HO to CW Done | Makkah | 2019 | 21.3893 | 39.9069 | Nokia | New Site | New Location | Ram1441 |  | COW | Doable |  | Approved | Approved | IGATE | 21/05/2019 21:47:09 | SNR1010338 | NOBODY | ACCEPTED | 2019-05-15 | 2019-05-18 | 2019-05-18 | 2019-05-20 | NA | NA | 2019-05-19 | 2019-05-19 | 2019-05-19 | 2019-05-19 | 2019-05-19 | 2019-05-19 | NA | NA | 0 | 2019-06-15 | 2019-06-15 | 2019-06-12 | 21.3893 | 39.9069 | 2019-06-11 | 2019-06-11 | COW- 10m | 4.5X12 | 2019-06-15 | Non-Private | Baladiya | أمانة مكة المكرمة |  | NA | 4.5X12 | GF | Adnan Alqorashy | HOC
ZTF555 | Macro | Aspiration | HOC | HO to CW Done | Taif | 2019 | 21.3409 | 40.4658 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 02/05/2019 18:58:41 | SNR1010034 | NOBODY | ACCEPTED | 2019-03-19 | 2019-03-22 | 2019-03-22 | 2019-03-24 | 22/07/2019 11:13:36 | 22/07/2019 16:28:14 | [6 empty] | 2019-08-21 | 2019-08-21 | 6180 | 2019-08-21 | 2019-11-17 | 2019-06-30 | 21.3409 | 40.4658 | 2019-07-09 | 2019-07-09 | 60m-E4-GF |  | 2019-11-17 | Private | Private | عواض بن حمود الجعيد | 555714103 | 28000 | 400M | GF | Fahad Alrogy | HOC | bar: 2019-11-13 to 2020-02-19
CWN212 | COW | Aspiration | HOC | HO to CW Done | Makkah | 2019 | 21.3855 | 39.9012 | Nokia | New Site | New Location | Ram1441 |  | COW | Doable |  | Approved | Approved | IGATE | 21/05/2019 21:53:58 | SNR1010339 | NOBODY | ACCEPTED | 2019-05-15 | 2019-05-18 | 2019-05-18 | 2019-05-20 | NA | NA | 2019-05-19 | 2019-05-19 | 2019-05-19 | 2019-05-19 | 2019-05-19 | 2019-05-19 | NA | NA | 0 | 2019-06-15 | 2019-06-15 | 2019-06-12 | 21.3855 | 39.9012 | 2019-06-11 | 2019-06-11 | COW - 12m | 4.5X12 | 2019-06-15 | Non-Private | Baladiya | أمانة مكة المكرمة |  | NA | 4.5X12 | GF | Adnan Alqorashy | HOC
CWN213 | COW | Aspiration | HOC | HO to CW Done | Makkah | 2019 | 21.3884 | 39.9024 | Nokia | New Site | New Location | Ram1441 |  | COW | Doable |  | Approved | Approved | IGATE | 21/05/2019 21:57:33 | SNR1010340 | NOBODY | ACCEPTED | 2019-05-15 | 2019-05-18 | 2019-05-18 | 2019-05-20 | NA | NA | 2019-05-19 | 2019-05-19 | 2019-05-19 | 2019-05-19 | 2019-05-19 | 2019-05-19 | NA | NA | 0 | 2019-06-15 | 2019-06-15 | 2019-06-12 | 21.3884 | 39.9024 | 2019-06-11 | 2019-06-11 | COW - 12m | 4.5X12 | 2019-06-15 | Non-Private | Baladiya | أمانة مكة المكرمة |  | NA | 4.5X12 | GF | Adnan Alqorashy | HOC
CWN214 | COW | Aspiration | HOC | HO to CW Done | Makkah | 2019 | 21.392 | 39.9038 | Nokia | New Site | New Location | Ram1441 |  | COW | Doable |  | Approved | Approved | IGATE | 21/05/2019 22:07:50 | SNR1010341 | NOBODY | ACCEPTED | 2019-05-15 | 2019-05-18 | 2019-05-18 | 2019-05-20 | NA | NA | 2019-05-19 | 2019-05-19 | 2019-05-19 | 2019-05-19 | 2019-05-19 | 2019-05-19 | NA | NA | 0 | 2019-06-15 | 2019-06-15 | 2019-06-12 | 21.392 | 39.9038 | 2019-06-11 | 2019-06-11 | COW - 15m | 4.5X12 | 2019-06-15 | Non-Private | Baladiya | أمانة مكة المكرمة |  | NA | 4.5X12 | GF | Adnan Alqorashy | HOC
ZTF515 | Macro | Aspiration | HOC | HO to CW Done | Taif | 2019 | 21.4476 | 40.4958 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 01/05/2019 11:42:44 | SNR1009996 | NOBODY | ACCEPTED | 2019-03-17 | 2019-03-20 | 2019-03-20 | 2019-03-22 | NA | NA | 2019-06-09 | 2019-06-16 | 2019-06-16 | 2019-06-16 | 2019-06-20 | 2019-06-27 | NA | NA | 0 | 2019-06-27 | 2019-06-30 | 2019-06-13 | 21.4476 | 40.4958 | 2019-06-27 | 2019-07-01 | 35M-LP-GF |  | 2019-08-20 | Non-Private | Baladiya | أمانة الطائف | 440/447 | 30000 | 196 | GF | Fahad Alrogy | HOC
CWN215 | COW | Aspiration | HOC | HO to CW Done | Makkah | 2019 | 21.3871 | 39.8995 | Nokia | New Site | New Location | Ram1441 |  | COW | Doable |  | Approved | Approved | IGATE | 21/05/2019 22:11:22 | SNR1010342 | NOBODY | ACCEPTED | 2019-05-15 | 2019-05-18 | 2019-05-18 | 2019-05-20 | NA | NA | 2019-05-19 | 2019-05-19 | 2019-05-19 | 2019-05-19 | 2019-05-19 | 2019-05-19 | NA | NA | 0 | 2019-06-15 | 2019-06-15 | 2019-06-12 | 21.3871 | 39.8995 | 2019-06-11 | 2019-06-11 | COW - 15m | 4.5X12 | 2019-06-15 | Non-Private | Baladiya | أمانة مكة المكرمة |  | NA | 4.5X12 | GF | Adnan Alqorashy | HOC
ZTF493 | Macro | Aspiration | HOC | HO to CW Done | Taif | 2020 | 21.3745 | 40.538 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 25/04/2019 15:33:08 | SNR1009724 | NOBODY | ACCEPTED | 2019-03-16 | 2019-03-19 | 2019-03-19 | 2019-03-21 | NA | NA | 2019-06-09 | 2019-06-16 | 2019-06-16 | 2019-06-16 | 2019-06-20 | 2019-06-27 | NA | NA | 40001169 | 2019-06-27 | 2019-06-30 | 2019-06-30 | 21.3745 | 40.538 | 2019-07-10 | 2019-07-10 | 70m-E4-GF |  | 2019-10-15 | Non-Private | Baladiya | Taif Municipality | 440/446 | 30000 | 400 | GF | Fahad Alrogy | HOC
ZTF563 | Macro | Aspiration | Pending FBP | FBP Not Issued | Taif | 2020 | 21.4444 | 40.4333 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 01/05/2019 10:46:24 | SNR1009994 | SNR_O | Technical Procurement Section Manager | 2019-03-24 | 2019-03-24 | 2019-06-22 | 2019-06-22 | NA | NA | 2020-06-14 | 2020-11-16 | 2020-11-16 | 2020-11-16 | 2020-12-17 | 2020-12-21 | NA | NA | 0 | 2020-09-10 |  | 2020-08-18 | 21.4454 | 40.4313 | 2020-11-04 | 2020-11-08 | 60m-E4-GF | 20 X 20 | 2020-08-18 | Non-Private | Baladiya | بلدية الطائف |  | 30000 | 20X20 | GF | Fahad Alrogy | HOC
ZTF443 | Macro | Aspiration | HOC | HO to CW Done | Taif | 2020 | 21.4767 | 40.4493 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 24/04/2019 17:11:28 | SNR1009706 | NOBODY | ACCEPTED | 2019-08-18 | 2019-08-21 | 2019-08-21 | 2019-08-23 | NA | NA | 2019-09-01 | 2019-09-08 | 2019-09-08 | 2019-09-08 | 2019-11-19 | 2019-11-28 | NA | NA | 0 | 2019-11-28 | 2020-01-23 | 2019-08-19 | 21.4767 | 40.4493 | 2019-07-04 | 2019-07-07 | 45m-E4-GF |  | 2019-11-17 | Non-Private | Baladiya | امانة الطائف | 441/471 | 30000 | 225 | GF | Fahad Alrogy | HOC
ZTF814 | Macro | Aspiration | HOC | HO to CW Done | Taif | 2020 | 21.2829 | 40.3731 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 06/05/2019 13:32:09 | SNR1010105 | NOBODY | ACCEPTED | 2019-03-17 | 2019-03-20 | 2019-03-20 | 2019-03-22 | NA | NA | 2019-06-09 | 2019-06-16 | 2019-06-16 | 2019-06-16 | 2019-06-20 | 2019-06-27 | NA | NA | 0 | 2019-06-27 | 2020-01-23 | 2019-06-13 | 21.2829 | 40.3731 | 2019-06-27 | 2019-07-01 | 45m-E4-GF |  | 2019-08-20 | Non-Private | Baladiya | Taif Municipality | 440/451 | 30000 | 196 | GF | Fahad Alrogy | HOC
ZTL018 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2020 | 19.5219 | 43.543 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 28/04/2019 16:55:54 | SNR1009781 | NOBODY | ACCEPTED | 2019-03-18 | 2019-03-21 | 2019-03-21 | 2019-03-23 | NA | NA | 2019-04-17 | 2019-05-01 | 2019-05-01 | 2019-05-01 | 2019-06-13 | 2019-06-13 | NA | NA | 0 | 2019-06-02 | 2019-06-23 | 2019-04-28 | 19.5218 | 43.5431 | 2019-04-22 | 2019-04-22 | 60m-E4-GF |  | 2019-06-25 | Non-Private | Baladiya | Tathlith Municipality | 865 | 40000 | 400 | GF | Mohammed elshehry | HOC
ZTL019 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2020 | 19.5011 | 43.5243 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 28/04/2019 16:42:54 | SNR1009779 | NOBODY | ACCEPTED | 2019-03-18 | 2019-03-21 | 2019-03-21 | 2019-03-23 | NA | NA | 2019-04-17 | 2019-05-01 | 2019-05-01 | 2019-05-01 | 2019-06-13 | 2019-06-13 | NA | NA | 0 | 2019-06-02 | 2019-06-23 | 2019-04-28 | 19.5011 | 43.5243 | 2019-04-22 | 2019-04-22 | 60m-E4-GF |  | 2019-06-25 | Non-Private | Baladiya | Tathlith Municipality | 866 | 40000 | 400 | GF | Mohammed elshehry | HOC
ZUA021 | Macro/Replacement | Aspiration | HOC | HO to CW Done | Madinah | 2020 | 26.6624 | 37.9078 | Nokia | New Site | New Location | NA | ZUA002 | Macro | Doable |  | Approved | Approved | IGATE | 16/10/2019 18:28:19 | SNR1012123 | SNR_I | District Support | 2019-07-22 | 2019-07-22 | 2019-07-22 | 2019-07-22 | NA | NA | 2020-12-09 | 2021-01-05 | 2021-03-07 | 2021-03-07 | 2021-03-09 | 2021-03-11 | NA | NA | 0 | 2021-03-14 | 2021-03-14 | 2021-03-11 | 26.6656 | 37.9036 | 2021-03-13 | 2021-03-15 | 40m-LP-GF | 20X20 | 2021-03-15 | Non-Private | Baladiya | امانة العلا |  |  | 20 x 20 | GF | Fahad Aljohany | HOC
ZMC555 | Macro/Replacement | Aspiration | Pending FBP | FBP Not Issued | Makkah | 2020 | 21.6244 | 39.6984 | Nokia | New Site | New Location | NA | ZMC982 | Macro | Doable |  | Approved | Approved | IGATE | 13/10/2019 18:15:46 | SNR1012090 | NOBODY | ACCEPTED | 2018-10-16 | 2018-10-19 | 2018-10-19 | 2018-10-21 | NA | NA | 2019-03-27 | 2019-12-19 | 2019-12-19 | 2019-12-22 | 2019-12-25 | 2019-12-26 | NA | NA | 400070492 | 2020-01-01 |  | 2020-01-02 | 21.6244 | 39.6984 | 2020-01-02 | 2020-01-02 | 35m-LP-GF | 4X3.5 | 2019-12-26 | Non-Private | Baladiya | بلدية الجموم | 27\1441 | 50000 | 4X3.5 | GF | Adnan Alqorashy | HOC
PMD891 | Macro/Redeployment | Aspiration | HOC | HO to CW Done | Madinah | 2020 | 24.4718 | 39.6124 | Nokia | New Site | New Location | NA | Replacement/Redeployment | Macro | Doable |  | Approved | Approved | IGATE |  | SNR000 | NOBODY | NA | 2019-01-15 | 2019-01-15 | 2019-01-15 | 2019-01-15 | 2020-03-18 | 2020-03-18 | [6 empty] | 2020-05-06 | 2020-04-23 | 0 | 2020-07-09 | 2020-07-09 | 2020-06-21 | 24.472 | 39.6125 | 2020-07-07 | 2020-07-08 | 10m-WM-RT |  | 2020-07-09 | Private | Private | فندق حياة التقوى | 148271221 | 90000 | WM | RT | Fahad Aljohany | HOC | bar: 2019-11-13 to 2020-02-19
ZMM923 | Macro/Replacement | Aspiration | HOC | HO to CW Done | Madinah | 2020 | 24.4613 | 39.7076 | Nokia | New Site | New Location | NA | ZMD758 | Macro | Doable |  | Approved | Approved | Non IGATE | NA | SNR000 | NOBODY | ACCEPTED | 2018-04-29 | 2018-04-29 | 2018-04-29 | 2018-04-29 | NA | NA | 2018-09-24 | 2018-10-01 | 2018-10-01 | 2018-10-01 | 2018-10-30 | 2018-10-30 | NA | NA | 0 | 2018-10-30 | 2018-12-19 | 2018-09-27 | 24.4613 | 39.7076 | 2018-10-15 | 2018-10-29 | 25m-LP-GF |  | 2018-12-24 | Non-Private | Baladiya | امانة المدينة المنورة |  | 100000 |  | GF | Fahad Aljohany | HOC
ZTF592 | Macro | Aspiration | HOC | HO to CW Done | Taif | 2020 | 21.3389 | 40.349 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 06/05/2019 13:23:18 | SNR1010103 | NOBODY | ACCEPTED | 2019-03-16 | 2019-03-19 | 2019-03-19 | 2019-03-21 | NA | NA | 2019-09-01 | 2019-09-08 | 2019-09-08 | 2019-09-08 | 2019-11-19 | 2019-11-28 | NA | NA | NI-35/708 | 2019-11-28 | 2020-09-10 | 2019-11-17 | 21.3389 | 40.349 | 2019-10-14 | 2019-08-25 | 45m-E4-GF | 20X20 | 2019-11-17 | Non-Private | Baladiya | امانة الطائف |  | 30000 | 400 | GF | Fahad Alrogy | HOC
ZAB432 | Macro | Aspiration | HOC | HO to CW Done | Assir | 2020 | 18.2234 | 42.5797 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 26/10/2019 12:56:49 | SNR1012199 | NOBODY | ACCEPTED | 2019-08-28 | 2019-08-31 | 2019-08-31 | 2019-09-02 | NA | NA | 2019-10-10 | 2019-10-20 | 2019-10-20 | 2019-10-20 | 2019-11-20 | 2019-11-20 | NA | NA | 0 | 2019-11-21 | 2019-12-30 | 2019-12-03 | 18.2234 | 42.5797 | 2019-11-24 | 2019-11-24 | 45m-E4-GF |  | 2019-11-24 | Non-Private | Baladiya | امانة عسير | 4100105 | 30000 | 400 | GF | Mohammed elshehry | HOC
ZMD574 | Macro | Aspiration | HOC | HO to CW Done | Madinah | 2020 | 24.4328 | 39.4755 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 28/10/2019 14:33:02 | SNR1012230 | NOBODY | ACCEPTED | 2019-10-07 | 2019-10-10 | 2019-10-10 | 2019-10-12 | 11/11/2019 14:58:20 | 04/11/2019 07:51:31 | [6 empty] | 2019-11-07 | 2019-11-12 | 0 | 2019-11-12 | 2019-12-01 | 2019-11-15 | 24.4328 | 39.4755 | 2019-11-24 | 2019-11-24 | 45M-E4-GF |  | 2019-11-24 | Private | Private | خالد الدوسري | 505329491 | 45000 | 400 | GF | Fahad Aljohany | HOC | bar: 2019-11-13 to 2020-02-19
ZMM215 | Macro | Aspiration | HOC | HO to CW Done | Madinah | 2019 | 24.5064 | 39.7221 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 04/11/2019 18:41:04 | SNR1012308 | NOBODY | ACCEPTED | 2019-10-23 | 2019-10-26 | 2019-10-26 | 2019-10-28 | 07/11/2019 09:34:29 | 11/11/2019 15:31:35 | [6 empty] | 2019-11-12 | 2019-11-16 | 0 | 2019-11-16 | 2019-11-26 | 2019-11-15 | 24.5064 | 39.7221 | 2019-11-24 | 2019-11-24 | 35M-LP-GF |  | 2019-11-24 | Private | Private | مهمل هويمل البلادي | 504365328 | 40000 | 400 | GF | Fahad Aljohany | HOC | bar: 2019-11-13 to 2020-02-19
ZMM231 | Macro | Aspiration | HOC | HO to CW Done | Madinah | 2019 | 24.3895 | 39.6023 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 19/10/2019 14:46:48 | SNR1012147 | NOBODY | ACCEPTED | 2019-09-02 | 2019-09-05 | 2019-09-05 | 2019-09-07 | 27/10/2019 15:48:22 | 28/10/2019 11:01:25 | [6 empty] | 2019-11-03 | 2019-11-07 | 0 | 2019-11-07 | 2019-11-26 | 2019-11-15 | 24.3895 | 39.6023 | 2019-11-21 | 2019-11-19 | 35M-LP-GF |  | 2019-11-17 | Private | Private | مريم سعد الحسيني | 503325225 | 45000 | 400 | GF | Fahad Aljohany | HOC | bar: 2019-11-13 to 2020-02-19
ZMM947 | Macro | Aspiration | HOC | HO to CW Done | Madinah | 2019 | 24.465 | 39.4898 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 28/10/2019 16:56:16 | SNR1012233 | NOBODY | ACCEPTED | 2019-10-23 | 2019-10-26 | 2019-10-26 | 2019-10-28 | NA | NA | 2019-10-28 | 2019-11-04 | 2019-11-04 | 2019-11-04 | 2019-12-16 | 2020-01-06 | NA | NA | 0 | 2020-01-13 | 2020-06-04 | 2019-11-17 | 24.465 | 39.4898 | 2019-12-02 | 2019-12-03 | 35m-LP-GF | 20x20 | 2020-01-01 | Non-Private | Baladiya | أمانة المدينة المنورة | 41/42 | 100000 | 400 | GF | Fahad Aljohany | HOC
ZMM963 | Macro | Aspiration | HOC | HO to CW Done | Madinah | 2019 | 24.4536 | 39.5787 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 04/11/2019 07:42:21 | SNR1012296 | NOBODY | ACCEPTED | 2019-11-04 | 2019-11-07 | 2019-11-07 | 2019-11-09 | NA | NA | 2019-11-04 | 2019-11-11 | 2019-11-11 | 2019-11-11 | 2019-12-16 | 2020-01-06 | NA | NA | 0 | 2020-01-13 | 2020-06-04 | 2019-11-17 | 24.4536 | 39.5787 | 2019-12-02 | 2019-12-03 | 35m-LP-GF | 15x15 | 2020-01-01 | Non-Private | Baladiya | أمانة المدينة المنورة | 41/63 | 100000 | 225 | GF | Fahad Aljohany | HOC
ZMM977 | Macro | Aspiration | HOC | HO to CW Done | Madinah | 2019 | 24.3859 | 39.591 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 28/10/2019 17:08:20 | SNR1012234 | NOBODY | ACCEPTED | 2019-09-05 | 2019-09-08 | 2019-09-08 | 2019-09-10 | NA | NA | 2019-10-21 | 2019-10-28 | 2019-10-28 | 2019-10-28 | 2019-12-16 | 2020-01-06 | NA | NA | 0 | 2020-01-13 | 2020-06-04 | 2019-11-17 | 24.3859 | 39.591 | 2019-12-02 | 2019-11-18 | 35m-LP-GF | 15x15 | 2020-01-01 | Non-Private | Baladiya | أمانة المدينة المنورة | 41/41 | 100000 | 225 | GF | Fahad Aljohany | HOC
ZMC541 | Macro/Replacement | Aspiration | HOC | HO to CW Done | Makkah | 2020 | 21.2833 | 39.677 | Nokia | New Site | New Location | NA | ZR27001 | Macro | Doable |  | Approved | Approved | IGATE |  | SNR000 | NOBODY | ACCEPTED | 2019-10-22 | 2019-10-22 | 2019-10-22 | 2019-10-22 | NA | NA | 2019-10-25 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | NA | NA | 4105503905 | 2001-01-01 | 2021-10-26 | 2020-01-08 | 21.2828 | 39.6767 | Draft | 2021-06-23 | 60m-E4-GF | 20X20 | 2021-10-27 | Non-Private | Baladiya | أمانة مكة المكرمة |  |  | 20X20 | GF | Adnan Alqorashy | HOC
ZMC660 | Macro/Redeployment | Aspiration | HOC | HO to CW Done | Makkah | 2020 | 21.3821 | 39.7212 | Nokia | New Site | New Location | NA | Replacement/Redeployment | Macro | Doable |  | Approved | Approved | Non IGATE | NA | SNR000 | NOBODY | ACCEPTED | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2021-10-28 | 2021-11-02 | [6 empty] | 2021-11-02 | 2021-11-03 |  | 2021-11-03 | 2021-11-18 | 2021-01-08 | 21.3813 | 39.7223 | Draft | 2021-11-18 | 60m-E4-GF | 400 | 2021-11-21 | Private | Private | عبد الله العريفي | 504535657 | 80000 | 400 | GF | Adnan Alqorashy | HOC | bar: 2019-11-13 to 2020-02-19
ZMC517 | Macro/Replacement | Aspiration | HOC | HO to CW Done | Makkah |  | 21.4039 | 39.8752 | Nokia | New Site | New Location | NA | ZMKA939 | Macro | Doable |  | Approved | Approved | IGATE | 29/12/2019 15:05:08 | SNR1012538 | NOBODY | ACCEPTED | 2019-11-18 | 2019-11-18 | 2019-11-18 | 2019-11-18 | 2020-07-01 | 2020-07-01 | [6 empty] | 2020-01-23 | 2020-01-30 | 0 | 2020-01-30 | 2020-03-11 | 2020-01-27 | 21.4039 | 39.8752 | 2020-02-05 | 2020-02-03 | WM-Pole-RT |  | 2020-03-12 | Private | Private | الاميرة شيخة بنت عبد الرحمن آل سعود | 555621835 | 60000 | 100M | RT | Adnan Alqorashy | HOC | bar: 2019-11-13 to 2020-02-19
Z1C001 | Macro/Redeployment | Aspiration | HOC | HO to CW Done | Makkah |  | 21.6946 | 39.581 | Nokia | New Site | New Location | NA | Relocation/Redeployment | Macro | Doable |  | Approved | Approved | Non IGATE | NA | SNR000 | NOBODY | ACCEPTED | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | NA | NA | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | NA | NA | 0 | 2001-01-01 | 2001-01-01 | NA | 21.6946 | 39.581 | NA | NA | 60m-E4-GF |  | 2019-12-05 | Non-Private | Baladiya | NA |  | NA |  | GF | Adnan Alqorashy | HOC
ZMM229 | Macro | Aspiration | HOC | HO to CW Done | Madinah |  | 24.5255 | 39.6463 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 15/12/2019 09:42:04 | SNR1012491 | NOBODY | ACCEPTED | 2019-11-02 | 2019-11-02 | 2019-11-02 | 2019-11-02 | NA | NA | 2019-10-28 | 2019-11-04 | 2019-11-04 | 2019-11-04 | 2019-12-16 | 2020-01-06 | NA | NA | 0 | 2020-01-13 | 2020-10-07 | 2019-11-17 | 24.5255 | 39.6463 | 2019-12-22 | 2019-11-20 | 35m-LP-GF | 10x10 | 2020-01-01 | Non-Private | Baladiya | أمانة المدينة المنورة | 41/35 | 100000 | 100 | GF | Fahad Aljohany | HOC
ZTF308 | Macro/Replacement | Aspiration | HOC | HO to CW Done | Taif |  | 21.3178 | 40.4342 | Nokia | New Site | New Location | NA | ZTF922 | Macro | Doable |  | Approved | Approved | IGATE | NA | SNR000 | NOBODY | ACCEPTED | 2019-12-30 | 2019-12-30 | 2020-03-09 | 2020-03-09 | NA | NA | 2020-03-09 | 2020-03-09 | 2020-03-09 | 2020-03-12 | 2020-03-16 | 2020-03-16 | NA | NA | 0 | 2020-03-16 | 2020-03-22 | 2020-03-12 | 21.3178 | 40.4342 | 2020-03-15 | 2020-03-22 | 45m-E4-GF |  | 2020-03-23 | Non-Private | GOV | معهد سلاح الصيانه بالطائف | ZTF308 | 40000 | 400 | GF | Fahad Alrogy | HOC
ZMM929 | Macro | Aspiration | HOC | HO to CW Done | Madinah |  | 24.4139 | 39.6717 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 17/06/2019 13:12:14 | SNR1010595 | NOBODY | ACCEPTED | 2020-01-19 | 2020-01-19 | 2020-01-19 | 2020-02-03 | NA | NA | 2020-01-19 | 2020-01-19 | 2020-01-19 | 2020-02-05 | 2020-02-19 | 2020-03-11 | NA | NA | 0 | 2020-03-11 | 2020-10-08 | 2020-02-04 | 24.4139 | 39.6717 | 2020-02-24 | 2020-02-27 | 35m-LP-GF |  | 2020-03-12 | Non-Private | Baladiya | أمانة المدينة المنورة | 41/57 | 100000 | 100 | GF | Fahad Aljohany | HOC
ZMC981 | Macro | Aspiration | HOC | HO to CW Done | Makkah |  | 21.4728 | 39.8869 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | 30/04/2019 11:29:19 | SNR1009897 | NOBODY | ACCEPTED | 2020-01-21 | 2020-01-21 | 2020-01-21 | 2020-01-21 | NA | NA | 2020-03-12 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | NA | NA | 0 | 2001-01-01 | 2020-09-21 | 2020-04-20 | 21.4726 | 39.8882 | 2020-04-21 | 2020-09-21 | 9m-RT-Tower | All Roof | 2020-09-27 | Private | Private | محمد العميري | 555546832 | 46000 | All Roof | RT | Adnan Alqorashy | HOC
ZMM933 | Macro | Aspiration | HOC | HO to CW Done | Madinah |  | 24.4915 | 39.657 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE | NA | SNR000 | NOBODY | ACCEPTED | 2020-02-20 | 2020-02-20 | 2020-02-20 | 2020-02-20 | NA | NA | 2020-02-20 | 2020-02-20 | 2020-02-20 | 2020-02-24 | 2020-03-02 | 2020-03-11 | NA | NA | 0 | 2020-03-11 | 2020-10-08 | 2020-03-08 | 24.4915 | 39.657 | 2020-03-11 | 2020-03-11 | 35m-LP-GF |  | 2020-03-12 | Non-Private | Baladiya | أمانة المدينة المنورة | 41/59 | 100000 | 24.5 | GF | Fahad Aljohany | HOC
ZMM887 | Macro/Replacment | Aspiration | HOC | HO to CW Done | Madinah |  | 24.4693 | 39.6281 | Nokia | New Site | New Location | NA | ZMD940 | Macro | Doable |  | Approved | Approved | IGATE | 08/01/2020 17:17:53 | SNR1012578 | NOBODY | ACCEPTED | 2020-02-03 | 2020-02-03 | 2020-02-03 | 2020-02-03 | NA | NA | 2020-02-03 | 2020-02-03 | 2020-02-03 | 2020-02-05 | 2020-02-12 | 2020-03-12 | NA | NA | 410536 | 2020-03-12 | NA | 2020-02-17 | 24.4693 | 39.6281 | 2020-02-19 | 2020-02-19 | 35m-LP-GF |  | 2020-02-23 | Non-Private | Baladiya | أمانة المدينة المنورة | 41/58 | 120000 | 24.5 | GF | Fahad Aljohany | HOC
ZMC702 | Macro | Aspiration | HOC | HO to CW Done | Makkah |  | 21.3696 | 39.8216 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE |  | SNR000 | NOBODY | NA | 2020-02-27 | 2020-02-27 | 2020-02-27 | 2020-02-27 | 2020-02-27 | 2020-03-16 | [6 empty] | 2020-03-16 | 2020-03-25 | 0 | 2020-03-25 | 2020-06-25 | 2020-06-25 | 21.3696 | 39.8216 | 2020-04-23 | 2020-04-27 | 9m-RT-Tower |  | 2020-06-25 | Private | Private | حسين الزهراني | 503781278 | 50000 | 100M | RT | Adnan Alqorashy | HOC | bar: 2019-11-13 to 2020-02-19
ZMC400 | Macro | Aspiration | Pending LA | IBP Not Issued | Makkah |  | 21.3514 | 39.596 | Nokia | New Site | New Location | Ram1441 |  | Macro | Doable |  | Approved | Approved | IGATE |  | SNR000 | SNR_I | District Support | 2020-03-04 | 2020-03-04 | 2020-03-04 | 2020-03-04 | NA | NA | 2019-11-13: 2020-03-04 |  |  | Mobily Sharing |  |  | 2020-07-06 | 21.3512 | 39.5974 | 2021-04-26 | 2021-06-23 | 60m-E4-GF | Sharing |  | Non-Private | Sharing | Sharing With Mobily | NA | NA | Sharing | Sharing | Adnan Alqorashy | انتظار بناء البرج من قبل موبايلي ليتم المشاركة
ZMM924 | Macro | Aspiration | HOC | HO to CW Done | Madinah |  | 24.4686 | 39.6073 | Nokia | New Site | New Location | NA |  | Macro | Doable |  | Approved | Approved | IGATE |  | SNR000 | SNR_I | District Support | 2020-03-11 | 2020-03-11 | 2020-03-11 | 2020-03-11 | 2020-08-30 | 2020-09-28 | [6 empty] | 2020-09-28 | 2020-10-04 | 0 | 2020-10-04 | 2020-12-06 | 2020-09-01 | 24.469 | 39.6046 | 2020-09-20 | 2020-09-20 | WM-Pole-RT |  | 2020-09-30 | Private | Private | فندق توليب |  |  |  | RT | Fahad Aljohany | HOC | bar: 2019-11-13 to 2020-02-19
ZMDA021 | Macro/Redeployment | Aspiration | HOC | HO to CW Done | Madinah |  | 24.5317 | 39.5717 | Nokia | New Site | New Location |  |  | Macro | Doable |  | Approved | Approved | Non IGATE | NA | SNR000 | NOBODY | ACCEPTED | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | NA | NA | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | NA | NA | 0 | 2001-01-01 | 2001-01-01 | NA | NA | NA | NA | NA | NA |  | 2020-05-18 | Non-Private | Baladiya | NA |  | NA | NA | GF | Fahad Aljohany | HOC
ZMC513 | Macro/Replacment | Aspiration | HOC | HO to CW Done | Makkah |  | 21.4165 | 39.8548 | Nokia | New Site | New Location |  | ZMC720 | Macro | Doable |  | Approved | Approved | IGATE |  | SNR000 | SNR_I | District Support | 2020-08-17 | 2020-08-17 | 2020-08-17 | 2020-08-17 | 2021-02-07 | 2021-02-23 | [6 empty] | 2021-02-23 | 2021-03-21 | 42055177654 | 2021-09-22 | 2021-11-02 | 2021-03-24 | 21.416 | 39.8548 | 2021-08-15 | 2021-06-22 | WM-Pole-RT | 10X10 | 2021-11-02 | Private | Private | ورثة سعد الحربي | 504517174 | 75000 | RT | RT | Adnan Alqorashy | HOC | bar: 2019-11-13 to 2020-02-19
PMK488 | Macro/Replacement | Aspiration | HOC | HO to CW Done | Makkah |  | 21.4243 | 39.8063 | Nokia | New Site | New Location |  | PMK844 | Macro | Doable |  | Approved | Approved | IGATE |  | SNR000 | SNR_I | District Support | 2020-08-12 | 2020-08-12 | 2020-08-12 | 2020-08-12 | 2020-08-12 | 2020-08-12 | [6 empty] | 2020-08-12 | 2020-08-12 | CTL-21-9-000260 | 2021-09-22 | 2021-11-02 | 2020-09-08 | 21.4245 | 39.807 | 2020-11-23 | 2020-11-22 | WM-Pole-RT | 10X10 | 2021-11-02 | Private | Private | ناصر الهيبي | 569333797 | 40000 | RT | RT | Adnan Alqorashy | HOC | bar: 2019-11-13 to 2020-02-19
ZAB392 | Macro | Aspiration | Pending FBP | FBP Not Applied | Assir |  | 18.324 | 42.6146 | Nokia | New Site | New Location |  |  | Macro | Doable |  | Approved | Approved | IGATE |  | SNR000 | SNR_I | District Support | 2020-07-13 | 2020-07-13 | 2020-07-13 | 2020-07-13 | NA | NA | 2020-07-13 | 2020-08-25 | 2020-11-03 | 2020-11-03 | 2020-11-09 | 2020-12-03 | NA | NA | 0 |  |  | 2020-08-27 | 18.3192 | 42.6217 | 2020-08-30 | 2020-08-30 | 45m-E4-GF |  | 2020-08-31 | Non-Private | Baladiya | امانة عسير |  |  | 14x14 | GF | Mohammed elshehry | HOC
ZTF306 | Macro | Aspiration | HOC | HO to CW Done | Taif |  | 21.274 | 40.4405 | Nokia | New Site | New Location |  |  | Macro | Doable |  | Approved | Approved | IGATE |  | SNR000 | SNR_I | District Support | 2020-08-13 | 2020-08-13 | 2020-08-13 | 2020-08-13 | NA | NA | 2020-08-13 | 2020-09-01 | 2020-09-01 | 2020-09-01 | 2020-09-06 | 2020-09-10 | NA | NA | 0 | 2020-09-10 | 2020-10-26 | 2020-08-17 | 21.2727 | 40.4404 | 2020-09-03 | 2020-09-03 | 35m-LP-GF | 20X20 | 2020-09-03 | Non-Private | Baladiya | امانة الطائف |  |  | 20X20 | GF | Fahad Alrogy | HOC
ZTF307 | Macro | Aspiration | HOC | HO to CW Done | Taif |  | 21.4936 | 40.4717 | Nokia | New Site | New Location |  |  | Macro | Doable |  | Approved | Approved | IGATE |  | SNR000 | SNR_I | District Support | 2020-08-13 | 2020-08-13 | 2020-08-13 | 2020-08-13 | NA | NA | 2020-08-13 | 2020-08-13 | 2020-08-13 | 2020-08-13 | 2020-08-23 | 2020-08-31 | NA | NA | 0 | 2020-08-31 | 2020-10-25 | 2020-08-17 | 21.4937 | 40.4717 | 2020-08-26 | 2020-08-26 | 45m-E4-GF | 20X20 | 2020-08-31 | Non-Private | Baladiya | امانة الطائف |  |  | 20X20 | GF | Fahad Alrogy | HOC
ZAB365 | Macro | Aspiration | Pending FBP | FBP Not Applied | Assir |  | 18.2407 | 42.6394 | Nokia | New Site | New Location |  |  | Macro | Doable |  | Approved | Approved | IGATE |  | SNR000 | SNR_I | District Support | 2020-08-13 | 2020-08-13 | 2020-08-13 | 2020-08-13 | NA | NA | 2020-08-13 | 2020-08-25 | 2020-11-03 | 2020-11-03 | 2020-11-09 | 2020-12-03 | NA | NA | 0 |  |  | 2020-08-27 | 18.2411 | 42.6388 | 2020-08-27 | 2020-08-30 | 35m-LP-GF | 10X10 | 2020-08-31 | Non-Private | Baladiya | امانة عسير |  |  | 10X10 | GF | Mohammed elshehry | HOC
ZUA981 | Macro | Aspiration | HOC | HO to CW Done | Madinah |  | 26.605 | 37.949 | Nokia | New Site | New Location |  |  | Macro | Doable |  | Approved | Approved | IGATE |  | SNR000 | SNR_I | District Support | 2020-08-13 | 2020-08-13 | 2020-08-13 | 2020-08-13 | NA | NA | 2020-08-13 | 2021-01-05 | 2021-03-07 | 2021-03-07 | 2021-03-09 | 2021-03-11 | NA | NA | 5179 | 2021-03-14 | 2021-03-14 | 2020-09-21 | 26.6002 | 37.9485 | 2020-09-21 | 2020-09-21 | 40m-LP-GF | 20X20 | 2021-03-14 | Non-Private | Baladiya | امانة العلا |  |  | 20X20 | GF | Fahad Aljohany | HOC
ZUA982 | Macro | Aspiration | HOC | HO to CW Done | Madinah |  | 26.5897 | 37.9386 | Nokia | New Site | New Location |  |  | Macro | Doable |  | Approved | Approved | IGATE |  | SNR000 | SNR_I | District Support | 2020-08-13 | 2020-08-13 | 2020-08-13 | 2020-08-13 | 2020-08-13 | 2020-08-13 | [6 empty] | 2020-08-13 | 2020-08-13 | NI-35/181 | 2020-08-13 | 2020-08-20 | 2020-08-20 | 26.589 | 37.9428 | 2020-08-23 | 2020-08-23 | 40m-LP-GF | 10X10 | 2020-08-24 | Private | Private | احمد بن سالم بن عبدالله المزروعي |  |  | 10X10 | GF | Fahad Aljohany | HOC | bar: 2019-11-13 to 2020-02-19
ZUA988 | Macro | Aspiration | HOC | HO to CW Done | Madinah |  | 26.532 | 37.9765 | Nokia | New Site | New Location |  |  | Macro | Doable |  | Approved | Approved | IGATE |  | SNR000 | SNR_I | District Support | 2020-08-13 | 2020-08-13 | 2020-08-13 | 2020-08-13 | NA | NA | 2020-08-13 | 2021-01-05 | 2021-03-07 | 2021-03-07 | 2021-03-09 | 2021-03-11 | NA | NA | NI-35/181 | 2021-03-14 | 2021-03-14 | 2020-09-21 | 26.532 | 37.9765 | 2020-09-21 | 2020-09-21 | 40m-LP-GF | 20X20 | 2021-03-14 | Non-Private | Baladiya | امانة العلا |  |  | 20X20 | GF | Fahad Aljohany | HOC
ZUA989 | Macro | Aspiration | HOC | HO to CW Done | Madinah |  | 18.2407 | 42.6394 | Nokia | New Site | New Location |  |  | Macro | Doable |  | Approved | Approved | IGATE |  | SNR000 | SNR_I | District Support | 2020-08-13 | 2020-08-13 | 2020-08-13 | 2020-08-13 | NA | NA | 2020-08-13 | 2021-01-05 | 2021-03-07 | 2021-03-07 | 2021-03-09 | 2021-03-11 | NA | NA | NI-35/181 | 2021-03-14 | 2021-03-14 | 2020-09-21 | 26.549 | 37.956 | 2020-09-21 | 2020-09-21 | 40m-LP-GF | 20X20 | 2021-03-14 | Non-Private | Baladiya | امانة العلا |  |  | 20X20 | GF | Fahad Aljohany | HOC
ZMM945 | Macro | Aspiration | HOC | HO to CW Done | Madinah |  | 24.4644 | 39.5182 | Nokia | New Site | New Location |  |  | Macro | Doable |  | Approved | Approved | IGATE |  | SNR000 | SNR_I | District Support | 2021-06-08 | 2021-06-08 | 2021-06-09 | 2021-06-09 | NA | NA | 2021-06-10 | 2021-07-07 | 2021-07-08 | 2021-07-12 | 2021-08-08 | 2021-08-17 | NA | NA | 4200774484 | 2021-11-09 | 2021-12-01 | 2021-06-20 | 24.464 | 39.5166 | 2021-07-05 | 2021-07-06 | 35m-LP-GF | 3.5X7 | 2021-07-12 | Non-Private | Baladiya | امانة المدينة المنورة |  |  | 3.5X7 | GF | Fahad Aljohany | HOC
ZMK657 | Macro | Aspiration | HOC | HO to CW Done | Makkah |  | 22.8312 | 39.0269 | Nokia | New Site | New Location |  |  | Macro | Doable |  | Approved | Approved | IGATE |  | SNR000 | SNR_I | District Support | 2020-09-21 | 2020-09-21 | 2020-09-21 | 2020-09-21 | 2020-09-21 | 2020-09-21 | [6 empty] | 2020-09-21 | 2020-09-21 | 1440007615 | 2020-10-04 | 2021-11-15 | 2020-09-21 | 22.8295 | 39.0275 | 2020-09-20 | 2021-06-27 | 45m-E4-GF | 15x15 | 2021-11-01 | Private | Private | عبيد عتيق اليوبي |  |  | 15x15 | GF | Adnan Alqorashy | HOC | bar: 2021-06-10 to 2021-08-17
ZMM223 | Macro | Aspiration | HOC | HO to CW Done | Madinah |  | 24.4984 | 39.5657 | Nokia | New Site | New Location |  |  | Macro | Doable |  | Approved | Approved | IGATE |  | SNR000 | SNR_I | District Support | 2020-09-21 | 2020-09-21 | 2020-09-21 | 2020-09-21 | NA | NA | 2020-09-21 | 2020-09-21 | 2020-09-21 | 2020-09-21 | 2020-09-21 | 2021-03-16 | NA | NA | 0 | 2021-03-16 | 2021-03-16 | 2020-09-28 | 24.4965 | 39.5647 | 2020-10-28 | 2021-03-16 | 35m-LP-GF | 20X20 | 2021-03-16 | Non-Private | Gov | الحرس الوطني |  | 46000 | 20X20 | GF | Fahad Aljohany | HOC
ZMM859 | Macro/Redeployment | Aspiration | HOC | HO to CW Done | Madinah |  | 24.4512 | 39.5017 | Nokia | New Site | New Location |  |  | Macro | Doable |  | Approved | Approved | IGATE |  | SNR000 | SNR_I | District Support | 2020-09-29 | 2020-09-29 | 2020-09-29 | 2020-09-29 | NA | NA | 2020-09-29 | 2020-09-29 | 2020-09-29 | 2020-09-29 | 2020-10-22 | 2020-10-28 | NA | NA | 420233 | 2020-10-28 | 2021-08-04 | NA | 24.4517 | 39.5016 | 2020-11-11 | 2020-11-11 | 35m-LP-GF | 5X5 | 2020-11-16 | Non-Private | Baladiya | أمانة المدينة المنورة |  |  | 5X5 | GF | Fahad Aljohany | HOC
ZMK517 | Macro/Redeployment | Aspiration | HOC | HO to CW Done | Makkah |  | 21.4223 | 39.7843 | Nokia | New Site | New Location |  |  | Macro | Doable |  | Approved | Approved | Non IGATE | NA | SNR000 | NOBODY | ACCEPTED | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | NA | NA | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | NA | NA | 0 | 2000-01-01 | 2000-01-01 | NA | NA | NA | NA | NA | NA |  | 2020-11-30 | Private | Private | يحي الزهراني |  | NA | NA | RT | Adnan Alqorashy | HOC
ZMD684 | Macro/Replacement | Aspiration | HOC | HO to CW Done | Madinah |  | NA | NA | Nokia | New Site | New Location |  |  | Macro | Doable |  | Approved | Approved | IGATE |  | SNR000 | SNR_I | District Support | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | NA | NA | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | NA | NA | 0 | 2000-01-01 | 2000-01-01 | NA | NA | NA | NA | NA | NA | NA | 2020-11-23 | NA | NA | NA | NA | NA | NA | NA | NA | HOC
ZYB775 | Macro/Replacement | Aspiration | HOC | HO to CW Done | Yanbu |  | 24.0813 | 38.0413 | Nokia | New Site | New Location |  | ZYB995 | Macro | Doable |  | Approved | Approved | IGATE |  | SNR000 | SNR_I | District Support | 2020-11-23 | 2020-11-23 | 2020-12-06 | 2020-12-06 | NA | NA | 2020-12-06 | 2021-07-29 | 2021-07-29 | 2021-08-03 | 2021-08-08 | 2021-08-10 | NA | NA | 0 | NA | NA | 2021-07-28 | 24.0816 | 38.042 | 2021-08-01 | 2021-08-02 | 35m-LP-GF | 3.5X7 | 2021-08-15 | Non-Private | Baladiya | بلدية ينبع |  |  | 3.5X7 | GF | Fahad Aljohany | HOC
ZMC494 | Macro/Replacement | Aspiration | Pending LA | IBP Not Issued | Makkah |  | 21.5169 | 39.7813 | Nokia | New Site | New Location |  | ZMK454 | Macro | Doable |  | Approved | Approved | IGATE |  | SNR000 | SNR_I | District Support | 2020-11-23 | 2020-11-23 | 2020-11-25 | 2020-11-25 | NA | NA | 2021-06-10: 2021-11-09 | NA | NA | CTR-21-11-000520 |  |  | 2020-12-22 | 21.517 | 39.7833 | 2021-06-17 | GPON | 60m-E4-GF | 15x15 |  | Non-Private | Baladiya | أمانة مكة المكرمة |  |  | 15x15 | GF | Adnan Alqorashy | تم إعادة رفع معاملة طلب العقود من الأمانة على نظام فرص وجاري المتابعة مع الأمانة
PMK594 | relocation | Aspiration | HOC | HO to CW Done | Makkah |  | NA | NA | Nokia | New Site | New Location |  |  | Macro | Doable |  | Approved | Approved | IGATE |  | SNR000 | SNR_I | District Support | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | NA | NA | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | NA | NA | 0 | 2000-01-01 | 2000-01-01 | NA | NA | NA | NA | NA | NA | NA | 2020-11-23 | NA | NA | NA | NA | NA | NA | NA | NA | HOC
PMK593 | relocation | Aspiration | HOC | HO to CW Done | Makkah |  | NA | NA | Nokia | New Site | New Location |  |  | Macro | Doable |  | Approved | Approved | IGATE |  | SNR000 | SNR_I | District Support | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | NA | NA | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | NA | NA | 0 | 2000-01-01 | 2000-01-01 | NA | NA | NA | NA | NA | NA | NA | 2020-11-23 | NA | NA | NA | NA | NA | NA | NA | NA | HOC
ZMC500 | Macro/Replacement | Aspiration | HOC | HO to CW Done | Makkah |  | 21.5405 | 39.9489 | Nokia | New Site | New Location |  | ZMK499 | Macro | Doable |  | Approved | Approved | IGATE |  | SNR000 | SNR_I | District Support | 2021-06-07 | 2021-06-08 | 2021-06-13 | 2021-06-13 | 2021-09-22 | 2021-09-22 | [6 empty] | 2021-09-22 | 2021-09-22 | 0 | 2021-09-22 | 2021-11-02 | 2021-09-22 | 21.5418 | 39.948 | 2021-10-12 | 2021-11-03 | 60m-E4-GF | 15x15 | 2021-11-02 | Private | Private | جميل السواط |  |  | 15x15 | GF | Adnan Alqorashy | HOC | bar: 2021-06-10 to 2021-08-17
ZMC497 | Macro | Aspiration | Pending LA | IBP Not Issued | Makkah |  | 21.2493 | 39.8316 | Nokia | New Site | New Location |  |  | Macro | Doable |  | Approved | Approved | IGATE |  | SNR000 | SNR_I | District Support | 2021-01-05 | 2021-01-05 | 2021-01-05 | 2021-01-05 | NA | NA | 2021-06-10: 2021-11-09 | NA | NA | CTR-21-10-000453 |  |  | 2021-01-06 | 21.2512 | 39.8284 | 2021-06-01 | 2021-06-29 | 45m-E4-GF | 15x15 |  | Non-Private | Baladiya | أمانة مكة المكرمة |  |  | 15x15 | GF | Adnan Alqorashy | تم إعادة رفع معاملة طلب العقود من الأمانة على نظام فرص وجاري المتابعة مع الأمانة
ZMC499 | Macro | Aspiration | HOC | HO to CW Done | Makkah |  | 21.3094 | 39.7041 | Nokia | New Site | New Location |  |  | Macro | Doable |  | Approved | Approved | IGATE |  | SNR000 | SNR_I | District Support | 2021-01-11 | 2021-01-11 | 2021-01-11 | 2021-01-11 | 2021-01-11 | 2021-01-11 | [6 empty] | 2021-01-18 | 2021-01-20 | CTL-21-9-000264 | 2021-09-22 | 2021-11-02 | 2021-02-14 | 21.3112 | 39.7042 | 2021-05-24 | GPON | 45m-E4-GF | 15x15 | 2021-11-02 | Private | Private | نسيم سندي | 507222069 | 50000 | 15x15 | GF | Adnan Alqorashy | HOC | bar: 2021-06-10 to 2021-08-17
ZMC512 | Macro | Aspiration | HOC | HO to CW Done | Makkah |  | 21.3601 | 39.8279 | Nokia | New Site | New Location |  |  | Macro | Doable |  | Approved | Approved | IGATE |  | SNR000 | SNR_I | District Support | 2021-01-11 | 2021-01-11 | 2021-01-11 | 2021-01-11 | 2021-01-11 | 2021-01-11 | [6 empty] | 2021-01-18 | 2021-01-20 | 4201506855 | 2021-01-20 | 2021-07-08 | 2021-02-14 | 21.3604 | 39.8275 | 2021-05-04 | 2021-06-23 | 45m-E4-GF | 15x15 | 2021-07-08 | Private | Private | علي العتيبي | 555536114 | 90000 | 15x15 | GF | Adnan Alqorashy | HOC | bar: 2021-06-10 to 2021-08-17
ZMC510 | Macro | Aspiration | HOC | HO to CW Done | Makkah |  | 21.3543 | 39.8349 | Nokia | New Site | New Location |  |  | Macro | Doable |  | Approved | Approved | IGATE |  | SNR000 | SNR_I | District Support | 2021-01-11 | 2021-01-11 | 2021-01-11 | 2021-01-11 | 2021-01-11 | 2021-01-11 | [6 empty] | 2021-01-18 | 2021-01-20 | 4201506866 | 2021-01-20 | 2021-07-08 | 2021-02-14 | 21.355 | 39.8358 | 2021-05-24 | 2021-06-14 | 45m-E4-GF | 15x15 | 2021-07-08 | Private | Private | عبد الله الكريديس | 555501570 | 80000 | 15x15 | GF | Adnan Alqorashy | HOC | bar: 2021-06-10 to 2021-08-17
ZMD522 | Macro | Aspiration | HOC | HO to CW Done | Madinah |  | 24.5006 | 39.5906 | Nokia | New Site | New Location |  |  | Macro | Doable |  | Approved | Approved | IGATE |  | SNR000 | SNR_I | District Support | 2021-01-11 | 2021-01-11 | 2021-01-11 | 2021-01-11 | NA | NA | 2021-01-11 | 2021-01-17 | 2021-05-27 | 2021-06-02 | 2021-06-09 | 2021-06-15 | NA | NA | 420920 | 2021-06-20 | 2021-11-18 | 2021-01-24 | 24.4995 | 39.5903 | 2021-05-09 | 2021-06-21 | 35M-LP-GF | 10X10 | 2021-06-22 | Non-Private | Baladiya | أمانة المدينة المنورة |  |  | 10X10 | GF | Fahad Aljohany | HOC
ZMM126 | Macro/Replacement | Aspiration | Pending FBP | FBP Not Issued | Madinah |  | 24.4779 | 39.6207 | Nokia | New Site | New Location |  | ZMD479 | Macro | Doable |  | Approved | Approved | IGATE |  | SNR000 | SNR_I | District Support | 2021-01-18 | 2021-01-18 | 2021-01-18 | 2021-01-18 | NA | NA | 2021-01-25 | 2021-03-18 | 2021-05-27 | 2021-06-02 | 2021-06-09 | 2021-06-28 | NA | NA | 0 | 2021-06-28 |  | 2021-06-07 | 24.4788 | 39.6233 | 2021-06-22 | 2021-06-10 | 35m-LP-GF | 3.5X7 | 2021-06-22 | Non-Private | Baladiya | أمانة المدينة المنورة |  |  | 3.5X7 | GF | Fahad Aljohany | HOC
ZMM935 | Macro | Aspiration | HOC | HO to CW Done | Madinah |  | 24.3873 | 39.6547 | Nokia | New Site | New Location |  |  | Macro | Doable |  | Approved | Approved | IGATE |  | SNR000 | SNR_I | District Support | 2021-01-20 | 2021-01-20 | 2021-01-20 | 2021-01-20 | NA | NA | 2021-01-24 | 2021-02-07 | 2021-05-27 | 2021-06-02 | 2021-06-09 | 2021-06-15 | NA | NA | 420918 | 2021-06-20 | 2021-08-19 | 2021-02-20 | 24.389 | 39.6575 | 2021-06-14 | 2021-06-20 | 40M-LP-GF | 10X10 | 2021-06-22 | Non-Private | Baladiya | امانة المدينة المنورة |  |  | 10X10 | GF | Fahad Aljohany | HOC
ZMD491 | Macro | Aspiration | Pending FBP | FBP Not Issued | Madinah |  | 24.4491 | 39.6303 | Nokia | New Site | New Location |  |  | Macro | Doable |  | Approved | Approved | IGATE |  | SNR000 | SNR_I | District Support | 2021-01-20 | 2021-01-20 | 2021-01-20 | 2021-01-20 | NA | NA | 2021-02-04 | 2021-04-12 | 2021-05-27 | 2021-06-02 | 2021-06-09 | 2021-06-28 | NA | NA | 0 | 2021-06-28 |  | 2021-02-20 | 24.4484 | 39.6291 | 2021-06-14 | 2021-06-15 | 35M-LP-GF | 10X10 | 2021-06-22 | Non-Private | Baladiya | امانة المدينة المنورة |  |  | 10X10 | GF | Fahad Aljohany | HOC
ZMM218 | Macro | Aspiration | HOC | HO to CW Done | Madinah |  | 24.3527 | 39.5253 | Nokia | New Site | New Location |  |  | Macro | Doable |  | Approved | Approved | IGATE |  | SNR000 | SNR_I | District Support | 2021-05-24 | 2021-05-26 | 2021-05-26 | 2021-05-26 | NA | NA | 2021-05-26 | 2021-05-26 | 2021-05-27 | 2021-06-02 | 2021-06-14 | 2021-07-11 | NA | NA | 0 | 2021-06-22 | 2021-09-08 | 2021-06-20 | 24.3568 | 39.5252 | 2021-06-22 | 2021-06-22 | 40M-LP-GF | 10X10 | 2021-06-22 | Non-Private | Baladiya | امانة المدينة المنورة |  |  | 10X10 | GF | Fahad Aljohany | HOC
ZMM966 | Macro | Aspiration | HOC | HO to CW Done | Madinah |  | 24.5214 | 39.6908 | Nokia | New Site | New Location |  |  | Macro | Doable |  | Approved | Approved | IGATE |  | SNR000 | SNR_I | District Support | 2021-01-20 | 2021-01-20 | 2021-01-20 | 2021-01-20 | NA | NA | 2021-01-24 | 2021-02-07 | 2021-05-27 | 2021-06-02 | 2021-06-09 | 2021-06-15 | NA | NA | 420919 | 2021-06-20 | 2021-12-01 | 2021-02-20 | 24.5205 | 39.6909 | 2021-05-20 | 2021-06-20 | 35M-LP-GF | 10X10 | 2021-06-22 | Non-Private | Baladiya | امانة المدينة المنورة |  |  | 10X10 | GF | Fahad Aljohany | HOC
ZMD708 | Macro | Aspiration | HOC | HO to CW Done | Madinah |  | 24.4947 | 39.7086 | Nokia | New Site | New Location |  |  | Macro | Doable |  | Approved | Approved | IGATE |  | SNR000 | SNR_I | District Support | 2021-01-20 | 2021-01-20 | 2021-01-20 | 2021-01-20 | NA | NA | 2021-02-04 | 2021-04-12 | 2021-05-27 | 2021-06-02 | 2021-06-09 | 2021-06-15 | NA | NA | 420917 | 2021-06-20 | 2021-08-18 | 2021-02-20 | 24.4941 | 39.7078 | 2021-06-08 | 2021-06-22 | 35M-LP-GF | 10X10 | 2021-06-22 | Non-Private | Baladiya | امانة المدينة المنورة |  |  | 10X10 | GF | Fahad Aljohany | HOC
ZMM209 | Macro | Aspiration | HOC | HO to CW Done | Madinah |  | 24.5454 | 39.6864 | Nokia | New Site | New Location |  |  | Macro | Doable |  | Approved | Approved | IGATE |  | SNR000 | SNR_I | District Support | 2021-01-20 | 2021-01-20 | 2021-01-20 | 2021-01-20 | NA | NA | 2021-02-04 | 2021-04-12 | 2021-05-27 | 2021-06-02 | 2021-06-09 | 2021-06-15 | NA | NA | 420921 | 2021-06-20 | 2021-10-17 | 2021-02-20 | 24.5455 | 39.687 | 2021-05-20 | 2021-06-20 | 35M-LP-GF | 3.5X7 | 2021-06-22 | Non-Private | Baladiya | امانة المدينة المنورة |  |  | 10X10 | GF | Fahad Aljohany | HOC
ZMM208 | Macro | Aspiration | HOC | HO to CW Done | Madinah |  | 24.5016 | 39.6821 | Nokia | New Site | New Location |  |  | Macro | Doable |  | Approved | Approved | IGATE |  | SNR000 | SNR_I | District Support | 2021-06-08 | 2021-06-08 | 2021-06-09 | 2021-06-09 | NA | NA | 2021-06-10 | 2021-07-07 | 2021-07-08 | 2021-07-12 | 2021-08-08 | 2021-08-17 | NA | NA | 4200774549 | 2021-10-01 | 2021-10-17 | 2021-06-20 | 24.501 | 39.6826 | 2021-06-23 | 2021-06-27 | 35m-LP-GF | 10x10 | 2021-07-08 | Non-Private | Baladiya | امانة المدينة المنورة |  |  | 10x10 | GF | Fahad Aljohany | HOC
ZMM928 | Macro | Aspiration | HOC | HO to CW Done | Madinah |  | 24.3834 | 39.605 | Nokia | New Site | New Location |  |  | Macro | Doable |  | Approved | Approved | IGATE |  | SNR000 | SNR_I | District Support | 2021-01-20 | 2021-01-20 | 2021-01-20 | 2021-01-20 | 2021-02-04 | 2021-02-25 | [6 empty] | 2021-02-25 | 2021-03-02 | 420878 | 2021-05-31 | 2021-09-18 | 2021-02-20 | 24.3832 | 39.6042 | 2021-05-04 | 2021-06-21 | 35M-LP-GF | 20X20 | 2021-09-19 | Private | Private | محمد كتبي | 590700055 | 48000 | 420M | GF | Fahad Aljohany | HOC | bar: 2021-06-10 to 2021-08-17
ZMD693 | Macro | Aspiration | HOC | HO to CW Done | Madinah |  | 24.5015 | 39.5842 | Nokia | New Site | New Location |  |  | Macro | Doable |  | Approved | Approved | IGATE |  | SNR000 | SNR_I | District Support | 2021-01-20 | 2021-01-20 | 2021-01-20 | 2021-01-20 | 2021-02-04 | 2021-02-21 | [6 empty] | 2021-02-21 | 2021-02-22 | 0 | 2021-05-31 | 2021-08-23 | 2021-02-20 | 24.5025 | 39.5842 | 2021-05-20 | 2021-06-20 | 40M-LP-GF | 20X20 | 2021-08-24 | Private | Private | محمد ابوالعلا | 507013335 | 45000 | 20X20 | GF | Fahad Aljohany | HOC | bar: 2021-06-10 to 2021-08-17
ZMC023 | Macro/Redeployment | Aspiration | HOC | HO to CW Done | Makkah |  | 21.424 | 39.8216 | Nokia | New Site | New Location |  |  | Macro | Doable |  | Approved | Approved | IGATE |  | SNR000 | SNR_I | District Support | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 2000-01-01 | NA | NA | 0 | NA | NA | NA | NA | NA | NA | NA | NA |  | 2021-03-02 | Non-Private | Gov | هيئة تطوير مكة |  | NA |  | GF | Adnan Alqorashy | HOC
ZMM800 | Macro/Replacement | Aspiration | HOC | HO to CW Done | Madinah |  | 24.4132 | 39.5405 | Nokia | New Site | New Location |  | ZMDA991 | Macro | Doable |  | Approved | Approved | IGATE |  | SNR000 | SNR_I | District Support | 2021-03-15 | 2021-03-15 | 2021-03-18 | 2021-03-18 | NA | NA | 2021-03-21 | 2021-06-27 | 2021-06-27 | 2021-07-12 | 2021-08-08 | 2021-08-17 | NA | NA | 4200722608 | 2021-10-01 | 2021-10-17 | 2021-06-03 | 24.4158 | 39.5428 | 2021-06-22 | 2021-06-23 | 40m-LP-GF | 3.5X7 | 2021-06-29 | Non-Private | Baladiya | امانة المدينة المنورة |  |  | 3.5X7 | GF | Fahad Aljohany | HOC
ZKL011 | Macro | Aspiration | HOC | HO to CW Done | Makkah |  | 22.1493 | 39.3132 | Nokia | New Site | New Location |  |  | Macro | Doable |  | Approved | Approved | IGATE |  | SNR000 | SNR_I | District Support | 2021-02-08 | 2021-03-21 | 2021-03-21 | 2021-03-21 | 2021-02-10 | 2021-04-11 | [6 empty] | 2021-04-11 | 2021-05-22 | 0 | 2021-10-11 | 2021-11-08 | 2021-05-25 | 22.0834 | 39.3149 | 2021-06-17 | 2021-07-01 | 60m-E4-GF | 20X20 | 2021-11-01 | Private | Private | عبد الخالق الصبحي | 503837851 | 30000 | 20X20 | GF | Adnan Alqorashy | HOC | bar: 2021-06-10 to 2021-08-17
ZMM207 | Macro | Aspiration | HOC | HO to CW Done | Madinah |  | 24.4376 | 39.4816 | Nokia | New Site | New Location |  |  | Macro | Doable |  | Approved | Approved | IGATE |  | SNR000 | SNR_I | District Support | 2021-01-23 | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2021-05-06 | [6 empty] | 2021-05-06 | 2021-05-10 | 0 | 2021-05-31 | 2021-08-24 | 2021-06-07 | 24.4362 | 39.4829 | 2021-06-20 | 2021-06-10 | 40M-LP-GF | 400M | 2021-08-24 | Private | Private | فهد العرفي | 560596517 | 40000 | 20X20 | GF | Fahad Aljohany | HOC | bar: 2021-06-10 to 2021-08-17
ZMD532 | Macro | Aspiration | HOC | HO to CW Done | Madinah |  | 24.4837 | 39.6083 | Nokia | New Site | New Location |  |  | Macro | Doable |  | Approved | Approved | IGATE |  | SNR000 | SNR_I | District Support | 2021-01-23 | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2021-05-06 | [6 empty] | 2021-05-06 | 2021-05-27 | 0 | 2021-05-31 | 2021-08-22 | 2021-06-07 | 24.4849 | 39.608 | 2021-08-15 | 2021-08-22 | 15m-RT | 100M-RT | 2021-08-22 | Private | Private | وليد الأرفلي | 505306773 | 70000 | Roof | RT | Fahad Aljohany | HOC | bar: 2021-06-10 to 2021-08-17
ZTF289 | Macro | Aspiration | HOC | HO to CW Done | Taif |  | 21.3686 | 40.4734 | Nokia | New Site | New Location |  |  | Macro | Doable |  | Approved | Approved | IGATE |  | SNR000 | SNR_I | District Support | 2021-03-21 | 2021-03-21 | 2021-03-25 | 2021-03-25 | NA | NA | [6 empty] | NA | NA | 0 | NA | NA | 2021-03-25 | 21.3681 | 40.477 | 2021-03-29 | 2021-03-29 | 40m-PT-GF | GF | 2021-03-31 | Non-Private | Gov | قصر الحوية |  | Free | 10X10 | GF | Fahad Alrogy | HOC | bar: 2021-06-10 to 2021-08-17
ZTF465 | Macro | Aspiration | Pending FBP | FBP Not Applied | Taif |  | 21.2159 | 40.4634 | Nokia | New Site | New Location |  |  | Macro | Doable |  | Approved | Approved | IGATE |  | SNR000 | SNR_I | District Support | 2021-03-24 | 2021-03-24 | 2021-03-24 | 2021-03-24 | NA | NA | 2021-03-28 | 2021-04-05 | 2021-06-14 | 2021-06-16 | 2021-06-22 | 2021-06-23 | NA | NA | 0 |  |  | 2021-03-30 | 21.2157 | 40.4633 | 2021-04-12 | 2021-05-26 | 45m-E4-GF | 20X20 | 2021-06-23 | Non-Private | Baladiya | بلدية الطائف |  |  | 20X20 | GF | Fahad Alrogy | HOC
ZMM105 | Macro | Aspiration | HOC | HO to CW Done | Madinah |  | 24.0923 | 39.5966 | Nokia | New Site | New Location |  |  | Macro | Doable |  | Approved | Approved | IGATE |  | SNR000 | SNR_I | District Support | 2021-04-07 | 2021-04-07 | 2021-04-08 | 2021-04-08 | NA | NA | 2021-06-28 | 2021-06-28 | 2021-06-28 | 2021-06-28 | 2021-08-11 | 2021-08-30 | NA | NA | 0 | 2021-08-30 | 2021-08-30 | 2021-07-29 | 24.5469 | 40.0194 | 2021-09-06 | 2021-09-06 | 40M-LP-GF | 15x15 | 2021-08-30 | Non-Private | Gov | هيئة عقارات الدولة |  |  | 15x15 | GF | Fahad Aljohany | HOC
ZMM106 | Macro | Aspiration | HOC | HO to CW Done | Madinah |  | 24.5468 | 40.0203 | Nokia | New Site | New Location |  |  | Macro | Doable |  | Approved | Approved | IGATE |  | SNR000 | SNR_I | District Support | 2021-04-07 | 2021-04-07 | 2021-04-08 | 2021-04-08 | NA | NA | 2021-06-28 | 2021-06-28 | 2021-06-28 | 2021-06-28 | 2021-08-11 | 2021-08-30 | NA | NA | 0 | 2021-08-30 | 2021-08-30 | 2021-07-29 | 24.0928 | 39.5954 | 2021-09-06 | 2021-09-06 | 40M-LP-GF | 15x15 | 2021-08-30 | Non-Private | Gov | هيئة عقارات الدولة |  |  | 15x15 | GF | Fahad Aljohany | HOC
ZTF288 | Macro/Replacement | Aspiration | Pending FBP | FBP Not Applied | Taif |  | 21.2324 | 40.4105 | Nokia | New Site | New Location |  | ZTF776 | Macro | Doable |  | Approved | Approved | IGATE |  | SNR000 | SNR_I | District Support | 2021-04-22 | 2021-04-22 | 2021-05-02 | 2021-05-02 | NA | NA | 2021-05-31 | 2021-06-14 | 2021-06-14 | 2021-06-16 | 2021-06-22 | 2021-06-23 | NA | NA | 0 |  |  | 2021-05-11 | 21.23300 | 40.4088 | 2021-05-27 | 2021-06-03 | 35M-LP-GF | 10X10 | 2021-06-23 | Non-Private | Baladiya | بلدية الطائف |  |  | 10X10 | GF | Fahad Alrogy | HOC
ZYB904 | Macro | Aspiration | HOC | HO to CW Done | Yanbu |  | 24.0251 | 38.1887 | Nokia | New Site | New Location |  |  | Macro | Doable |  | Approved | Approved | IGATE |  | SNR000 | SNR_I | District Support | 2021-09-13 | 2021-09-13 | 2021-09-13 | 2021-09-13 | NA | NA | 2021-09-13 | 2021-09-13 | 2021-09-13 | 2021-09-13 | 2021-09-13 | 2021-09-13 | NA | NA |  | 2021-09-13 | 2021-09-13 | 2021-09-13 | 24.0256 | 38.1902 | 2021-09-15 | 2021-09-15 | 35M-MP-GF | 20X12 | 2021-09-14 | Non-Private | Gov | الهيئئة الملكية بينبع |  |  | 20X12 | GF | Fahad Aljohany | HOC
ZYB888 | Macro | Aspiration | HOC | HO to CW Done | Yanbu |  | 24.0098 | 38.2179 | Nokia | New Site | New Location |  |  | Macro | Doable |  | Approved | Approved | IGATE |  | SNR000 | SNR_I | District Support | 2021-09-13 | 2021-09-13 | 2021-09-13 | 2021-09-13 | NA | NA | 2021-09-13 | 2021-09-13 | 2021-09-13 | 2021-09-13 | 2021-09-13 | 2021-09-13 | NA | NA |  | 2021-09-13 | 2021-09-13 | 2021-09-13 | 24.0108 | 38.2177 | 2021-09-15 | 2021-09-15 | 35M-MP-GF | 20X15 | 2021-09-14 | Non-Private | Gov | الهيئئة الملكية بينبع |  |  | 20X15 | GF | Fahad Aljohany | HOC
ZYB889 | Macro | Aspiration | HOC | HO to CW Done | Yanbu |  | 24.0311 | 38.1696 | Nokia | New Site | New Location |  |  | Macro | Doable |  | Approved | Approved | IGATE |  | SNR000 | SNR_I | District Support | 2021-09-13 | 2021-09-13 | 2021-09-13 | 2021-09-13 | NA | NA | 2021-09-13 | 2021-09-13 | 2021-09-13 | 2021-09-13 | 2021-09-13 | 2021-09-13 | NA | NA |  | 2021-09-13 | 2021-09-13 | 2021-09-13 | 24.032 | 38.1703 | 2021-09-15 | 2021-09-15 | 35M-MP-GF | 20X12 | 2021-09-14 | Non-Private | Gov | الهيئئة الملكية بينبع |  |  | 20X12 | GF | Fahad Aljohany | HOC
ZYB896 | Macro | Aspiration | HOC | HO to CW Done | Yanbu |  | 24.0305 | 38.1381 | Nokia | New Site | New Location |  |  | Macro | Doable |  | Approved | Approved | IGATE |  | SNR000 | SNR_I | District Support | 2021-09-13 | 2021-09-13 | 2021-09-13 | 2021-09-13 | NA | NA | 2021-09-13 | 2021-09-13 | 2021-09-13 | 2021-09-13 | 2021-09-13 | 2021-09-13 | NA | NA |  | 2021-09-13 | 2021-09-13 | 2021-09-13 | 24.0282 | 38.1422 | 2021-09-15 | 2021-09-15 | 35M-MP-GF | 20X15 | 2021-09-14 | Non-Private | Gov | الهيئئة الملكية بينبع |  |  | 20X15 | GF | Fahad Aljohany | HOC
ZKH516 | Macro | Aspiration | Pending FBP | FBP Not Issued | Assir |  | 18.3523 | 42.7586 | Nokia | New Site | New Location |  |  | Macro | Doable |  | Approved | Approved | IGATE |  | SNR000 | SNR_I | District Support | 2021-09-13 | 2021-09-13 | 2021-09-13 | 2021-09-13 | NA | NA | 2021-10-06 | 2021-10-26 | 2021-10-26 | 2021-10-26 | 2021-11-02 | 2021-11-10 | NA | NA |  | 2021-11-15 |  | 2021-10-19 | 18.3535 | 42.7566 | 2021-11-04 | 2021-10-21 | 40m-LP-GF | 10X10 | 2021-11-01 | Non-Private | Baladiya | أمانة عسير |  |  | 10X10 | GF | Mohammed elshehry | HOC
ZMM846 | Macro | Aspiration | Pending FBP | FBP Not Issued | Madinah |  | 24.3944 | 39.6735 | Nokia | New Site | New Location |  |  | Macro | Doable |  | Approved | Approved | IGATE |  | SNR000 | SNR_I | District Support | 2021-09-08 | 2021-09-08 | 2021-09-08 | 2021-09-08 | NA | NA | 2021-09-27 | 2021-10-21 | 2021-10-21 | 2021-10-21 | 2021-10-27 | 2021-11-18 | NA | NA |  | 2021-11-18 |  | 2021-10-19 | 24.3947 | 39.6734 | 2021-10-31 | 2021-10-27 | 40m-LP-GF | 3.5X7 | 2021-10-25 | Non-Private | Baladiya | امانة المدينة المنورة |  |  | 3.5X7 | GF | Fahad Aljohany | HOC
ZYB885 | Macro | Aspiration | HOC | HO to CW Done | Yanbu |  | 24.0269 | 38.2006 | Nokia | New Site | New Location |  |  | Macro | Doable |  | Approved | Approved | IGATE |  | SNR000 | SNR_I | District Support | 2021-09-08 | 2021-09-09 | 2021-09-09 | 2021-09-09 | NA | NA | 2021-09-30 | 2021-09-30 | 2021-09-30 | 2021-09-30 | 2021-09-30 | 2021-09-30 | NA | NA |  | 2021-09-30 | 2021-09-30 | 2021-09-28 | 24.0273 | 38.2016 | 2021-10-04 | 2021-10-07 | 35M-MP-GF | 20X15 | 2021-09-30 | Non-Private | GOV | الهيئئة الملكية بينبع |  |  | 20X15 | GF | Fahad Aljohany | HOC
ZMM887
ZAB691
ZMC555
ZMC335
ZMC330
ZMC695
ZMC658
ZMC300
ZJZ071
ZTF319
ZBH589
ZTF563
ZAB392
ZAB365
ZTF465
ZTF288
ZMD491
ZMM126
ZYB775
ZMM846
ZKH516

## Sheet1 (hidden)
Site ID | Macro/Small | District | Project | SAQ Status | FSSR Lat. | FSSR Long. | SAF Date | TCC Date | Tower Type
ZMC686 | Macro | Makkah | Aspiration | Pending FBP | 21.3539 | 39.8916 | OK | OK | 35m - Clock Tower
ZMC696 | Macro | Makkah | Aspiration | Pending FBP | 21.3913 | 39.8076 | OK | OK | 35m-LP-GF
ZMC344 | Macro | Makkah | Aspiration | Pending LA | 21.4041 | 39.9 | OK | OK | 14.5m Concealed Pole
ZMC345 | Macro | Makkah | Aspiration | Pending LA | 21.3961 | 39.9072 | OK | OK | 14.5m Concealed Pole
ZMC346 | Macro | Makkah | Aspiration | Pending LA | 21.4249 | 39.8747 | OK | OK | WM-Pole-RT
ZMC347 | Macro | Makkah | Aspiration | Pending LA | 21.4222 | 39.8936 | OK | OK | 14.5m Concealed Pole
ZMC348 | Macro | Makkah | Aspiration | Pending LA | 21.3389 | 39.9676 | OK | OK | 14.5m Concealed Pole
ZMC323 | Macro | Makkah | Aspiration | Pending FBP | 21.3784 | 39.7945 | OK | OK | 9m-RT-Tower
PMK488 | Macro/Replacement | Makkah | Aspiration | Pending FBP | 21.4245 | 39.807 | OK | OK | WM-Pole-RT
ZMC510 | Macro | Makkah | Aspiration | Pending FBP | 21.355 | 39.8358 | OK | OK | 45m-E4-GF
ZMC400 | Macro | Makkah | Aspiration | Pending LA | 21.3512 | 39.5974 | OK | OK | 60m-E4-GF
ZMC512 | Macro | Makkah | Aspiration | Pending FBP | 21.3604 | 39.8275 | OK | OK | 45m-E4-GF
ZMC325 | Macro | Makkah | Aspiration | Pending FBP | 21.4617 | 39.7212 | OK | OK | 60m-E4-GF
ZMC541 | Macro/Replacement | Makkah | Aspiration | Pending FBP | 21.2828 | 39.6767 | OK | OK | 60m-E4-GF
ZMK657 | Macro | Makkah | Aspiration | Pending TCC | 22.8295 | 39.0275 | OK |  | 45m-E4-GF
ZMC925 | Macro | Makkah | Aspiration | Pending TCC | 21.4901 | 39.7388 | OK |  | 60m-E4-GF
ZMC499 | Macro | Makkah | Aspiration | Pending TCC | 21.3112 | 39.7042 | OK |  | 45m-E4-GF
ZMC497 | Macro | Makkah | Aspiration | Pending TCC | 21.2512 | 39.8284 | OK |  | 45m-E4-GF
ZMC494 | Macro/Replacement | Makkah | Aspiration | Pending TCC | 21.517 | 39.7833 | OK |  | 60m-E4-GF
ZKL011 | Macro | Makkah | Aspiration | Pending TCC | 22.0834 | 39.3149 | OK |  | 60m-E4-GF
ZMC660 | Macro/Redeployment | Makkah | Aspiration | Pending SAF | 21.3813 | 39.7223 |  |  | 60m-E4-GF
ZMC513 | Macro/Replacment | Makkah | Aspiration | Pending SAF | 21.416 | 39.8548 |  | OK | WM-Pole-RT
ZMC665 | Macro | Makkah | Aspiration | Pending TSSR | 21.5278 | 40.0423 |  |  | 60m-E4-GF
ZMK569 | Macro | Makkah | Aspiration | Pending TSSR | 21.4293 | 39.8299 |  |  | 35m-LP-GF
ZMC500 | Macro/Replacement | Makkah | Aspiration | Pending TSSR | 21.5389 | 39.9504 |  |  | 60m-E4-GF

## District Summary
[7 empty] | Non Private Owners |  |  |  |  | Private Owners
Overall Aspiration Project Summary | Aspiration Project | Total Scope | ISS | ISR Submitted | Approved By STC Design | Approved by SAQ | Letter Sub to Baladyah | IBP Received | LA Submitted | LA Sign by TAWAL | LA Approved | MOU Submitted | LA Issued by TAWAL | LA Sign by TAWAL | LA Signed by Owner | LA Approved | BP submitted | BP issued | HOC
| GAP | 0 | 0 | 0 | 0 | 0 |  | 7 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 11 | 0 | [18 empty] | PO Nomber | MOP | JOB
| Total | 275 | 275 | 275 | 275 | 275 | 192 | 185 | 185 | 185 | 185 | 57 | 57 | 57 | 57 | 57 | 261 | 250 | 268 | [18 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
| District | Scope | ISS | ISR | Approved By STC Design | Approved by SAQ | Letter Sub to Baladyah | IBP Received | LA Submitted | LA Sign by TAWAL | LA Approved | MOU Submitted | LA Issued by TAWAL | LA Sign by TAWAL | LA Signed by Owner | LA Approved | BP submitted | BP issued | HOC | [18 empty] | #N/A | #N/A | #N/A
| Assir | 65 | 65 | 65 | 65 | 65 | 44 | 44 | 44 | 44 | 44 | 20 | 20 | 20 | 20 | 20 | 63 | 61 | 65 | [18 empty] | #N/A | #N/A | #N/A
| Madinah | 79 | 79 | 79 | 79 | 79 | 55 | 55 | 55 | 55 | 55 | 16 | 16 | 16 | 16 | 16 | 79 | 76 | 79 | [18 empty] | #N/A | #N/A | #N/A
| Makkah | 81 | 81 | 81 | 81 | 81 | 52 | 45 | 45 | 45 | 45 | 13 | 13 | 13 | 13 | 13 | 73 | 68 | 74 | [18 empty] | #N/A | #N/A | #N/A
| Baha | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | 3 | [18 empty] | #N/A | #N/A | #N/A
| Taif | 41 | 41 | 41 | 41 | 41 | 33 | 33 | 33 | 33 | 33 | 7 | 7 | 7 | 7 | 7 | 38 | 37 | 41 | [18 empty] | #N/A | #N/A | #N/A
| Yanbu | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 5 | 6 | 6 | [18 empty] | #N/A | #N/A | #N/A
| Total | 275 | 275 | 275 | 275 | 275 | 192 | 185 | 185 | 185 | 185 | 57 | 57 | 57 | 57 | 57 | 261 | 250 | 268 | [18 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[26 empty] | 2020-07-09 | [11 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[32 empty] | 45m-E4-GF | [5 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[35 empty] | Non-Private |  |  | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[20 empty] | 2021-10-28 | 2021-11-02 |  |  |  |  | 2021-11-02 | [6 empty] | عبد الله العريفي | 504535657 | 80000 | 400 | جاري اعتماد العقد من المالك | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[30 empty] | 2020-09-21 | 2020-09-21 | [6 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[8 empty] | فندق ميدان | [11 empty] | 2020-08-17 | 2020-08-17 | 2020-08-17 | 2020-08-17 | [14 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[20 empty] | 2020-08-12 | 2020-08-12 | 2020-08-12 | 2020-08-12 | 2020-08-12 | 2020-08-12 |  |  | 2020-08-12 | 2020-08-12 | [8 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
[38 empty] | #N/A | #N/A | #N/A
PAB992 | [37 empty] | #N/A | #N/A | #N/A
ZNM057 | [37 empty] | #N/A | #N/A | #N/A
ZNM002 | [37 empty] | #N/A | #N/A | #N/A
ZAB792 | [37 empty] | #N/A | #N/A | #N/A
ZAB430 | [37 empty] | 93081 | M-NOK-0045386 | J-ZAB430-0000010
ZR5A026 | [37 empty] | #N/A | #N/A | #N/A
IAB014 | [37 empty] | #N/A | #N/A | #N/A
ZAB782 | [37 empty] | #N/A | #N/A | #N/A
ZAB213 | [26 empty] | 2021-01-20 | [10 empty] | #N/A | #N/A | #N/A
ZABA219 | [26 empty] | 2021-01-20 | [10 empty] | #N/A | #N/A | #N/A
ZNM022 | [26 empty] | 2021-01-20 | [10 empty] | #N/A | #N/A | #N/A
ZNM079 | [37 empty] | #N/A | #N/A | #N/A
ZKH729 | [37 empty] | #N/A | #N/A | #N/A
Z7D002 | [37 empty] | #N/A | #N/A | #N/A
ZNM005 | [37 empty] | #N/A | #N/A | #N/A
ZNM021 | [37 empty] | #N/A | #N/A | #N/A
IAB004 | [37 empty] | #N/A | #N/A | #N/A
IAB987 | [37 empty] | #N/A | #N/A | #N/A
WIFIKH1001
WIFIKH1033
ZMC610 | [35 empty] | هيئة تطوير المدينة/ امانة المدينة المنورة
ZMC627
ZMC658
ZMC693
ZMC695
ZMC709
ZMC870
ZMC876
ZMC894
ZMC981