## DataBase
323 | 323 | 323 | 323 | 323 | 319 | 323 | 59 | 59 | 323 | 323 | 323 | 74 | 74 | 323 | 321 | 4 | 323 | 34 | 34 | 319 | 34 | 34 | 323 | 253 | 253 | 253 | 253 | 33 | 33 | 33 | 33 | 33 | 33 | 29 | 29 | 29 | 29 | 29 | 29 | 3 | 3 | 32 | 32 | 1 | 39 | 38 | 2 | 4 | 88 | 33 | 35 | 0 | 0 | 317 | 0 | 116 | 323 | 42 | 319 | 319 | 261 | 72 | 98 | 127 | 321 | 320 | 289 | 316 | 293
323 | 323 | 323 | 323 | 323 | 319 | 323 | 323 | 323 | 323 | 323 | 323 | 301 | 301 | 323 | 321 | 4 | 323 | 323 | 323 | 319 | 318 | 315 | 323 | 323 | 323 | 323 | 323 | 314 | 309 | 304 | 301 | 294 | 289 | 313 | 209 | 203 | 202 | 199 | 160 | 179 | 178 | 172 | 145 | 94 | 95 | 95 | 139 | 94 | 94 | 45 | 43 | 181 | 139 | 317 | 196 | 323 | 323 | 42 | 319 | 319 | 261 | 321 | 321 | 321 | 321 | 323 | 289 | 321 | 293
Site ID | Macro/Small | Project | Region | District | Priority | City | Latitude | Longitude | Vendor | Scope Status | Same/New Location | Critical old Site Type | Critical New Site Type | Site type | Doable/Not Doable | Reason for Non Doable | SSO GAT Status | SSO Submit Date | SSO Approved Date | ISR GAT Status | ISR GAT Submit Date | ISR GAT Approved Date | IGATE/Non IGATE | Submitted in IGATE | Request Number in IGATE | Request Status | Owner in IGATE | ISS Date | ISR Submitted to RF | ISR Document (STC) | ISR Document (SAQ) | OA Submitted to TTC | OA Approved by TTC | IBP Submit | IBP | Baladiya Contract Issued | Baladiya Contract Submitted to Tawal | Baladiya Contract Signed By Tawal | Non Private Contract Signed By Non Private | Private Contract Sign Date (Tawal) | Private Contract Sign Date (Owner) | FBP Submit date | FBP Issue date | FSSR Date | FSSR Lat. | FSSR Long. | SAF Date | TCC Date | FE Site ID | FBP Tower High | FBP Area dimension | HO Submission date | ADHOC | NPTS Site Survey Status | Original HO Forecast | FC Date | FC Week | Actual | Private/Non-Private | Owner's Type (Gov/Amanah/Private) | Owner's Name | Owner Contract Information | Rent Value | Area | Site Type (GF/RT) | Stage | BM Status | Coordinator Name | Remarks
ZDM080 | Macro | Aspiration | Eastern | Dammam | 2019 Scope | المباحث العامة | 26.3325 | 49.9605 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-06-16 | 2019-06-17 | Approved | 2019-07-05 18:23 | 2019-07-06 18:23 | IGATE | 07/07/2019 18:23:26 | SNR1011112 | SNR_I | District Support | 2019-06-20 | 2019-07-04 | 2019-07-04 | 2019-07-04 | NA | NA | 2019-06-19 | [5 empty] | NA | NA | [12 empty] | Pending HOC | 2019-09-30 | 2019-11-25 | W4-Nov |  | Non-Private | Gov | General Investigation | NA | 0 | 0 | GF | IBP Not Issued | Above | M. Ramadan | تم المتابعه مع سلطان الاحمري من المباحث العامة - انتظار الرد
ZBH631 | Macro | Aspiration | Southern | Baha | 2020 Scope | العقيق | 20.2849 | 41.6612 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-10 | 2019-03-11 | Approved | 2019-05-19 20:05 | 2019-05-20 20:05 | IGATE | 21/05/2019 20:05:12 | SNR1010325 | SNR_U | District Director | 2019-03-14 | 2019-04-10 | 2019-05-19 | 2019-06-17 | NA | NA | NA | [19 empty] | Pending HOC | 2019-12-15 | 2019-10-28 | W4-Oct |  | Private | Private | Al-Aqiq Municipality | NA | 25,143.00 | 17X17 | GF | IBP Not Issued | Below BM | Ali Asiri | تم توقيع العقد - (تم تغيير مساحة الارض ويحتاج تعديل العقد ) - تم تحويل المعاملة الى ادارة التعديات وانتظار صدور امر الازالة, تم صدور خطاب رفض من البلدية , تم تقديم خيار آخر للRF
ZDM109 | Macro | Aspiration | Eastern | Dammam | 2020 Scope | غرب الدمام | 26.2024 | 49.9388 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-08 | 2019-03-09 | Approved | 2019-07-08 18:31 | 2019-07-09 18:31 | IGATE | 10/07/2019 18:30:34 | SNR1011234 | SNR_O | Technical Procurement Section Manager | 2019-03-12 | 2019-04-10 | 2019-04-10 | 2019-04-10 | NA | NA | 2019-06-19 | 2019-10-27 | 2019-10-27 | 2019-10-27 | 2019-10-30 |  | NA | NA | 2019-10-27 | 2019-10-27 | [8 empty] | 2019-10-30 | 2019-11-03 | Pending HOC | 2019-12-29 | 2019-10-28 | W4-Oct |  | Non-Private | Baladiya | Western Dammam | 138203336 | 0 | 0 | GF | HO to CW Done | Above | Ali | تم تسليم الموقع
ZDM139 | Macro | Aspiration | Eastern | Dammam | 2019 Scope | ميناء الملك عبد العزيز | 26.4268 | 50.1736 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-03-05 | 2019-03-06 | Approved | 2019-05-19 16:45 | 2019-05-20 16:45 | IGATE | 21/05/2019 16:44:54 | SNR1010311 | SNR_I | District Support | 2019-03-09 | 2019-04-10 | 2019-05-19 |  | NA | NA | 2019-04-15 | 2019-09-08 | [18 empty] | Pending HOC | 2019-09-30 | 2019-11-15 | W2-Nov |  | Non-Private | Gov | Seaport | 0 | 0 | 0 | GF | Contract Not Issued | Above | Ali | بانتظار ارسال خطاب رد موافقة على عرض الميناء
ZAQ013 | Macro | Aspiration | Eastern | Dammam | 2020 Scope | ارامكو بالمنطقة الشرقية | 25.8847 | 49.5999 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-13 | 2019-03-14 | Approved | 2019-05-19 19:06 | 2019-05-20 19:06 | IGATE | 21/05/2019 19:06:26 | SNR1010320 | SNR_I | District Support | 2019-03-17 | 2019-04-10 | 2019-04-10 | 2019-04-14 | NA | NA | 2019-04-14 | [19 empty] | Pending HOC | 2019-09-15 | 2019-11-10 | W2-Nov |  | Non-Private | Gov | Aramco | NA | 0 | 0 | GF | IBP Not Issued | Below BM | Ali | تم تقديم خطاب رد بانتظار الرد من ارامكو - انتظار الرد من أرامكو
ZDH002 | Macro | Aspiration | Eastern | Dammam | 2019 Scope | ارامكو بالمنطقة الشرقية | 26.2648 | 50.068 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-06-16 | 2019-06-17 | Approved | 2019-07-08 18:37 | 2019-07-09 18:37 | IGATE | 10/07/2019 18:37:03 | SNR1011235 | SNR_I | District Support | 2019-06-20 | 2019-07-04 | 2019-07-04 | 2019-07-04 | NA | NA | 2019-06-19 | [19 empty] | Pending HOC | 2019-09-30 | 2019-12-05 | W1-Dec |  | Non-Private | Gov | Aramco | NA | 0 | 0 | GF | IBP Not Issued | Below BM | Ali | تم تقديم خطاب رد بانتظار الرد من ارامكو - انتظار الرد من أرامكو
ZDH003 | Macro | Aspiration | Eastern | Dammam | 2019 Scope | ارامكو بالمنطقة الشرقية | 26.2568 | 50.0709 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-03-08 | 2019-03-09 | Approved | 2019-05-19 18:06 | 2019-05-20 18:06 | IGATE | 21/05/2019 18:05:30 | SNR1010319 | SNR_I | District Support | 2019-03-12 | 2019-04-10 | 2019-04-10 | 2019-04-22 | NA | NA | 2019-06-19 | [19 empty] | Pending HOC | 2019-09-30 | 2019-12-05 | W1-Dec |  | Non-Private | Gov | Aramco | NA | 0 | 0 | GF | IBP Not Issued | Below BM | Ali | تم تقديم خطاب رد بانتظار الرد من ارامكو - انتظار الرد من أرامكو
ZDM033 | Macro | Aspiration | Eastern | Dammam | 2019 Scope | الحرس الوطني | 26.3688 | 50.1598 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-04-27 | 2019-04-28 | Approved | 2019-07-05 18:34 | 2019-07-06 18:34 | IGATE | 07/07/2019 18:33:32 | SNR1011114 | SNR_I | District Support | 2019-05-01 | 2019-07-04 | 2019-07-04 | 2019-07-04 | NA | NA | 2019-05-05 | [19 empty] | Pending HOC | 2019-09-30 | 2019-11-20 | W3-Nov |  | Non-Private | Gov | NG | NA | 0 | 0 | GF | IBP Not Issued | Above | M. Ramadan | بانتظار محضر المعاينة من الحرس الوطني وتحتاج ما يقارب 3 اسابيع -مع التاكيد بتعديل الفقرة 11
ZND791 | Macro | Aspiration | Eastern | Dammam | 2019 Scope | المدينة السكنية بالحرس الوطني | 26.3681 | 50.169 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-04-27 | 2019-04-28 | Approved | 2019-07-08 17:34 | 2019-07-09 17:34 | IGATE | 10/07/2019 17:34:10 | SNR1011225 | SNR_I | District Support | 2019-05-01 | 2019-07-04 | 2019-07-04 | 2019-07-04 | NA | NA | 2019-05-05 | 2019-08-28 | [11 empty] | 2019-10-20 | [6 empty] | Pending HOC | 2019-09-30 | 2019-11-05 | W1-Nov |  | Non-Private | Gov | NG | NA | 0 | 0 | GF | Contract Not Issued | Above | M. Ramadan | يحتاج تقديم خطاب الى الحرس الوطني لاعادة صياغة الفقرة رقم 11 من محضر المعاينة
ZND017 | Macro | Aspiration | Eastern | Dammam | 2020 Scope | القطيف | 26.5985 | 50.0142 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-05 | 2019-03-06 | Approved | 2019-05-23 17:50 | 2019-05-24 17:50 | IGATE | 25/05/2019 17:50:24 | SNR1010400 | SNR_Q | GM Technical Procurement | 2019-03-09 | 2019-04-10 | 2019-04-10 | 2019-04-14 | NA | NA | 2019-04-14 | 2019-09-19 | 2019-09-19 | 2019-09-26 | 2019-10-10 | 2019-10-14 | NA | NA | 2019-09-29 | 2019-11-12 | 2019-07-02 | 26.5972 | 50.0143 | 2019-07-30 | 2019-09-15 | ZND117 |  |  | 2019-10-17 | 2019-10-17 | Pending HOC | 2019-11-15 | 2019-10-27 | W4-Oct | W2-Oct | Non-Private | Baladiya | Baladiya Qatif | NA | 70,000.00 | 10*10 | GF | HO to CW Done | Above | Ali | تم تسليم الموقع بدون رخصة كما تم الاتفاق مع توال
ZND237 | Macro | Aspiration | Eastern | Dammam | 2020 Scope | القطيف | 26.5252 | 49.98 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-15 | 2019-03-16 | Approved | 2019-05-23 15:14 | 2019-05-24 15:14 | IGATE | 25/05/2019 15:14:17 | SNR1010385 | SNR_Q | GM Technical Procurement | 2019-03-19 | 2019-04-10 | 2019-04-10 | 2019-04-10 | NA | NA | 2019-04-14 | 2019-09-19 | 2019-09-19 | 2019-09-26 | 2019-10-10 | 2019-10-14 | NA | NA | 2019-09-29 | 2019-11-12 | 2019-07-02 | 26.5263 | 49.9791 | 2019-09-17 | 2019-10-06 | ZND047 |  |  | 2019-10-17 | 2019-10-17 | Pending HOC | 2019-11-15 | 2019-10-27 | W4-Oct | W2-Oct | Non-Private | Baladiya | Baladiya Qatif | NA | 70,000.00 | 10*10 | GF | HO to CW Done | Above | Ali | تم تسليم الموقع بدون رخصة كما تم الاتفاق مع توال
ZDM163 | Macro/Replacement | Aspiration | Eastern | Dammam | 2020 Scope-Replacement | تاروت | 26.5687 | 50.0722 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-04-18 | 2019-04-19 | Approved | 2019-05-19 20:09 | 2019-05-20 20:09 | IGATE | 21/05/2019 20:09:14 | SNR1010326 | NOBODY | ACCEPTED | 2019-04-22 | 2019-04-30 | 2019-05-14 | 2019-05-19 | 2019-06-30 | 2019-08-05 | NA | NA | NA | NA | NA | NA | 2019-09-04 | 2019-09-11 | 2019-08-28 | 2019-08-28 | 2019-08-03 | 26.5678 | 50.0722 | 2019-08-20 | 2019-09-01 | 329-00-000 |  |  | 2019-09-11 | 2019-09-12 | FDED Not Approved | 2019-12-29 | Done | HOC Done |  | Private | Private | علي أحمد القطان | 0578373384 | 40,000.00 | 17X17 | GF | HO to CW Done | HO Done | Ali | تم تسليم الموقع
ZDM136 | Macro | Aspiration | Eastern | Dammam | 2019 Scope | شرق الدمام | 26.3867 | 50.1718 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-05 | 2019-03-06 | Approved | 2019-04-26 18:12 | 2019-04-27 18:12 | IGATE | 28/04/2019 18:12:24 | SNR1009791 | SNR_O | Technical Procurement Section Manager | 2019-03-09 | 2019-04-10 | 2019-04-10 | 2019-04-14 | NA | NA | 2019-04-15 | 2019-10-10 | 2019-10-10 | 2019-10-13 | 2019-10-14 |  | NA | NA | 2019-10-10 | 2019-10-10 |  |  |  | 2019-10-20 |  |  |  |  | 2019-10-15 | 2019-10-15 | Pending HOC | 2019-07-04 | 2019-10-22 | W3-Oct | W2-Oct | Non-Private | Baladiya | Eastern Dammam | NA | 0 | 0 | GF | HO to CW Done | Above | Ali | تم تسليم الموقع
ZDM101 | Macro | Aspiration | Eastern | Dammam | 2019 Scope | غرب الدمام | 26.3655 | 49.9707 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-05 | 2019-03-06 | Approved | 2019-04-26 16:54 | 2019-04-27 16:54 | IGATE | 28/04/2019 16:53:51 | SNR1009780 | SNR_O | Technical Procurement Section Manager | 2019-03-09 | 2019-04-10 | 2019-04-10 | 2019-04-14 | NA | NA | 2019-04-15 | 2019-10-17 | 2019-10-17 | 2019-10-20 | 2019-10-20 |  | NA | NA | 2019-10-20 | 2019-10-20 |  |  |  | 2019-10-20 |  |  |  |  | 2019-10-20 | 2019-10-20 | Pending HOC | 2019-07-04 | 2019-10-28 | W4-Oct | W3-Oct | Non-Private | Baladiya | Western Dammam | NA | 50,000.00 | 18.5 | GF | HO to CW Done | Above | Ali | تم تسليم الموقع
ZDM107 | Macro | Aspiration | Eastern | Dammam | 2019 Scope | غرب الدمام | 26.372 | 50.0538 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-05 | 2019-03-06 | Approved | 2019-04-26 17:13 | 2019-04-27 17:13 | IGATE | 28/04/2019 17:13:00 | SNR1009784 | SNR_F | District Director | 2019-03-09 | 2019-04-10 | 2019-04-10 | 2019-04-10 | NA | NA | 2019-04-15 | 2019-10-17 | 2019-10-17 | 2019-10-20 | 2019-10-20 |  | NA | NA | 2019-10-20 | 2019-10-20 |  |  |  | 2019-10-20 |  |  |  |  | 2019-10-20 | 2019-10-20 | Pending HOC | 2019-07-04 | 2019-10-28 | W4-Oct | W3-Oct | Non-Private | Baladiya | Western Dammam | NA | 50,000.00 | 18.5 | GF | HO to CW Done | Above | Ali | تم تسليم الموقع
ZDM119 | Macro | Aspiration | Eastern | Dammam | 2019 Scope | غرب الدمام | 26.4431 | 49.9775 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-05 | 2019-03-06 | Approved | 2019-04-26 17:20 | 2019-04-27 17:20 | IGATE | 28/04/2019 17:20:28 | SNR1009785 | SNR_O | Technical Procurement Section Manager | 2019-03-09 | 2019-04-10 | 2019-04-10 | 2019-04-10 | NA | NA | 2019-04-15 | 2019-10-27 | 2019-10-27 | 2019-10-27 | 2019-10-30 |  | NA | NA | 2019-10-27 | 2019-10-27 |  |  |  | 2019-10-20 |  |  |  |  | 2019-10-30 | 2019-11-03 | Pending HOC | 2019-07-04 | 2019-10-28 | W4-Oct |  | Non-Private | Baladiya | Western Dammam | NA | 0 | 0 | GF | HO to CW Done | Above | Ali | تم تسليم الموقع
ZDM121 | Macro | Aspiration | Eastern | Dammam | 2019 Scope | غرب الدمام | 26.4592 | 49.9881 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-05 | 2019-03-06 | Approved | 2019-04-26 17:45 | 2019-04-27 17:45 | IGATE | 28/04/2019 17:45:19 | SNR1009790 | SNR_O | Technical Procurement Section Manager | 2019-03-09 | 2019-04-10 | 2019-04-10 | 2019-04-14 | NA | NA | 2019-04-15 | 2019-10-27 | 2019-10-27 | 2019-10-27 | 2019-10-30 |  | NA | NA | 2019-10-27 | 2019-10-27 |  |  |  | 2019-10-20 |  |  |  |  | 2019-10-30 | 2019-11-03 | Pending HOC | 2019-07-04 | 2019-10-28 | W4-Oct |  | Non-Private | Baladiya | Western Dammam | NA | 0 | 0 | GF | HO to CW Done | Above | Ali | تم تسليم الموقع
ZND196 | Macro | Aspiration | Eastern | Dammam | 2020 Scope | غرب الدمام | 26.2202 | 49.931 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-14 | 2019-03-15 | Approved | 2019-05-23 18:03 | 2019-05-24 18:03 | IGATE | 25/05/2019 18:02:44 | SNR1010401 | SNR_O | Technical Procurement Section Manager | 2019-03-18 | 2019-04-10 | 2019-04-10 | 2019-04-14 | NA | NA | 2019-04-15 | 2019-10-10 | 2019-10-10 | 2019-10-13 | 2019-10-14 |  | NA | NA | 2019-10-10 | 2019-10-10 |  |  |  | 2019-10-20 |  |  |  |  | 2019-10-15 | 2019-10-15 | Pending HOC | 2019-11-15 | 2019-10-22 | W3-Oct | W2-Oct | Non-Private | Baladiya | Western Dammam | NA | 0 | 0 | GF | HO to CW Done | Above | Ali | تم تسليم الموقع
ZND271 | Macro | Aspiration | Eastern | Dammam | 2019 Scope | غرب الدمام | 26.4446 | 50.0288 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-08 | 2019-03-09 | Approved | 2019-04-26 18:35 | 2019-04-27 18:35 | IGATE | 28/04/2019 18:35:01 | SNR1009793 | SNR_O | Technical Procurement Section Manager | 2019-03-12 | 2019-04-10 | 2019-04-10 | 2019-04-10 | NA | NA | 2019-04-25 | 2019-10-17 | 2019-10-17 | 2019-10-20 | 2019-10-20 |  | NA | NA | 2019-10-20 | 2019-10-20 |  |  |  | 2019-10-20 |  |  |  |  | 2019-10-20 | 2019-10-20 | Pending HOC | 2019-07-20 | 2019-10-28 | W4-Oct | W3-Oct | Non-Private | Baladiya | Western Dammam | NA | 50,000.00 | 44.4 | GF | HO to CW Done | Above | Ali | تم تسليم الموقع
ZND370 | Macro | Aspiration | Eastern | Dammam | 2020 Scope | غرب الدمام | 26.1933 | 49.9236 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-10 | 2019-03-11 | Approved | 2019-05-25 11:44 | 2019-05-26 11:44 | IGATE | 27/05/2019 11:44:27 | SNR1010415 | SNR_O | Technical Procurement Section Manager | 2019-03-14 | 2019-04-10 | 2019-04-10 | 2019-04-10 | NA | NA | 2019-04-25 | 2019-10-10 | 2019-10-10 | 2019-10-13 | 2019-10-14 |  |  |  | 2019-10-10 | 2019-10-10 |  |  |  | 2019-10-20 |  |  |  |  | 2019-10-21 | 2019-10-21 | Pending HOC | 2019-12-29 | 2019-10-22 | W3-Oct | W3-Oct | Non-Private | Baladiya | Western Dammam | NA | 0 | 0 | GF | Priv. Contract Not Issued From TAWAL | Above | Ali | تم تسليم الموقع
ZND641 | Macro | Aspiration | Eastern | Dammam | 2019 Scope | شركة الاسمنت الخاصة | 26.3314 | 50.2047 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-06-29 | 2019-06-30 | Approved | 2019-07-28 16:24 | 2019-07-29 16:24 | IGATE | 30/07/2019 16:23:55 | SNR1011510 | SNR_I | District Support | 2019-07-03 | 2019-07-03 | 2019-08-04 | 2019-08-05 |  |  | NA | NA | NA | NA | NA | NA | [14 empty] | Pending HOC |  | 2019-12-05 | W1-Dec |  | Private | Private | Cement Company ( Private Company) | 0504818730 | 0 | 0 | GF | Priv. Contract Not Issued From TAWAL | Below BM | Ali | مصنع الاسمنت Long pro - تم عمل مسح مبدئي لمواقع بلدية وبانتظار موافقه RF
ZDM013 | Macro | Aspiration | Eastern | Dammam | 2019 Scope | مدن | 26.2761 | 49.9593 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-08-03 | 2019-08-04 | Approved | 2019-08-05 13:36 | 2019-08-06 13:36 | IGATE | 07/08/2019 13:36:27 | SNR1011608 | SNR_I | District Support | 2019-08-07 | 2019-08-07 | 2019-08-07 | 2019-09-03 | NA | NA | 2019-08-05 | [19 empty] | Pending HOC |  | 2019-12-05 | W1-Dec |  | Non-Private | Gov | Modon | NA | 0 | 0 | GF | IBP Not Issued | Above | Ali | مدن بانتظار الاجتماع - تم اعادة تقديم الطلب بالنظام وتحتاج دراسة سيتم تحديد الاجتماع بعد انتهاء الدراسة
ZND438 | Macro | Aspiration | Eastern | Dammam | 2019 Scope | بلدية القطيف | 26.5868 | 50.0456 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-06-29 | 2019-06-30 | Approved | 2019-07-20 13:18 | 2019-07-21 13:18 | IGATE | 22/07/2019 13:18:16 | SNR1011413 | SNR_F | District Director | 2019-07-03 | 2019-07-03 | 2019-07-28 | 2019-08-05 |  |  | 2019-09-04 | 2019-11-10 | 2019-11-10 | 2019-11-14 | 2019-11-14 |  | NA | NA | 2019-11-17 | [9 empty] | 2019-11-14 |  | Pending HOC |  | 2019-10-28 | W4-Oct |  | Non-Private | Baladiya | Qateef Baladiyah | NA | 0 | 0 | GF | FBP Not Issued | Above | Ali | انتظار طباعة العقد من البلدية
ZHB031 | Macro | Aspiration | Eastern | Hafr Batin | 2020 Scope | حفر الباطن | 28.4303 | 45.9968 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-14 | 2019-03-15 | Approved | 2019-05-19 17:43 | 2019-05-20 17:43 | IGATE | 21/05/2019 17:43:26 | SNR1010317 | SNR_O | Technical Procurement Section Manager | 2019-03-18 | 2019-04-10 | 2019-04-10 | 2019-04-14 | NA | NA | 2019-04-17 | 2019-10-09 | 2019-10-09 | 2019-10-13 | 2019-10-17 |  | NA | NA | [10 empty] | 2019-10-21 | 2019-10-21 | Pending HOC | 2019-10-15 | 2019-11-18 | W3-Nov | W3-Oct | Non-Private | Baladiya | Amanah Hafr Batin | NA | 0 | 0 | GF | FBP Not Applied | Above | Humaidy | تم تسليم الموقع بدون رخصة كما تم الاتفاق مع توال
ZJZ169 | Macro | Aspiration | Southern | Jizan | 2020 Scope | جازان | 16.8572 | 42.5939 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-10 | 2019-03-11 | Approved | 2019-05-25 09:05 | 2019-05-26 09:05 | IGATE | 27/05/2019 09:04:55 | SNR1010409 | SNR_O | Technical Procurement Section Manager | 2019-03-14 | 2019-04-10 | 2019-04-10 | 2019-04-10 | NA | NA | 2019-04-18 | 2019-09-23 | 2019-09-23 | 2019-10-30 | 2019-10-30 | [5 empty] | 2019-10-08 | 16.8572 | 42.5936 | 2019-10-20 | 2019-10-23 | ZJZA017 |  |  | 2019-10-30 | 2019-11-03 | Pending HOC | 2019-07-20 | 2019-11-14 | W2-Nov |  | Non-Private | Baladiya | Amanah Jizan | NA | 0 | 17*17 | GF | Priv. Contract Not Issued From TAWAL | Above | Fahad Allam | تم تسليم الموقع بدون رخصة كما تم الاتفاق مع توال | need JR if no more location in area
ZHA270 | Macro | Aspiration | Central | Hail | 2020 Scope | حائل | 27.4722 | 41.6706 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-17 | 2019-03-18 | Approved | 2019-05-20 10:53 | 2019-05-21 10:53 | IGATE | 22/05/2019 10:52:32 | SNR1010354 | SNR_Q | GM Technical Procurement | 2019-03-21 | 2019-04-10 | 2019-04-10 | 2019-04-14 | NA | NA | 2019-04-14 | 2019-09-04 | 2019-09-10 | 2019-09-11 | 2019-10-17 |  | NA | NA |  |  | 2019-09-11 | 27.4712 | 41.668 | 2019-09-26 | 2019-10-01 | ZHAA021 |  |  | 2019-10-20 | 2019-10-20 | Pending HOC | 2019-09-15 | 2019-10-28 | W4-Oct | W3-Oct | Non-Private | Baladiya | Amanh Hail | NA | 50,000.00 | 300M | GF | FBP Not Applied | Above | Abdulaziz | تم تسليم الموقع بدون رخصة كما تم الاتفاق مع توال
ZHB044 | Macro | Aspiration | Eastern | Hafr Batin | 2020 Scope | حفر الباطن | 28.3587 | 45.9882 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-14 | 2019-03-15 | Approved | 2019-05-23 15:03 | 2019-05-24 15:03 | IGATE | 25/05/2019 15:03:12 | SNR1010384 | SNR_I | District Support | 2019-03-18 | 2019-04-10 | 2019-04-10 | 2019-04-16 | NA | NA | 2019-04-29 | [19 empty] | Pending HOC | 2019-11-15 | 2019-12-20 | W3-Dec |  | Non-Private | Baladiya | Amanah Hafr Batin | NA | 0 | 0 | GF | IBP Not Issued | Above | Humaidy | بانتظار تحديد موقع جديد من البلدية حيث تم رفض القديم من RF
ZHB050 | Macro | Aspiration | Eastern | Hafr Batin | 2020 Scope | ملك خاص | 28.4541 | 46.0196 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-14 | 2019-03-15 | Approved | 2019-05-23 15:24 | 2019-05-24 15:24 | IGATE | 02/10/2019 18:27:04 | SNR1012001 | SNR_O | Technical Procurement Section Manager | 2019-03-18 | 2019-04-10 | 2019-04-10 | 2019-04-14 | NA | NA | NA | NA | NA | NA | NA | NA | 2019-10-20 | 2019-10-27 | 2019-10-27 | 2019-11-07 | [8 empty] | 2019-10-21 | 2019-10-21 | Pending HOC | 2019-11-15 | 2019-10-27 | W4-Oct | W3-Oct | Private | Private | عبيد الشمري | 557359239 | 25000 | 400M | GF | HO to CW Done | Above | Humaidy | تم تسليم الموقع بدون رخصة كما تم الاتفاق مع توال
ZHA308 | Macro | Aspiration | Central | Hail | 2020 Scope | حائل | 27.5673 | 41.6645 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-17 | 2019-03-18 | Approved | 2019-05-23 13:40 | 2019-05-24 13:40 | IGATE | 25/05/2019 13:40:24 | SNR1010375 | SNR_Q | GM Technical Procurement | 2019-03-21 | 2019-04-10 | 2019-05-25 | 2019-06-17 | NA | NA | 2019-04-14 | 2019-09-04 | 2019-09-10 | 2019-09-11 | 2019-10-17 |  | NA | NA |  |  | 2019-09-11 | 27.5699 | 41.663 | 2019-09-15 | 2019-09-26 | ZHAA009 |  |  | 2019-10-20 | 2019-10-20 | Pending HOC | 2019-09-15 | 2019-10-28 | W4-Oct | W3-Oct | Non-Private | Baladiya | Amanh Hail | NA | 50,000.00 | 300M | GF | FBP Not Applied | Above | Abdulaziz | تم تسليم الموقع بدون رخصة كما تم الاتفاق مع توال
ZHA348 | Macro | Aspiration | Central | Hail | 2020 Scope | حائل | 27.5037 | 41.6402 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-17 | 2019-03-18 | Approved | 2019-05-23 13:46 | 2019-05-24 13:46 | IGATE | 15/10/2019 11:52:00 | SNR1012107 | SNR_O | Technical Procurement Section Manager | 2019-03-21 | 2019-04-10 | 2019-04-10 | 2019-06-17 | NA | NA | 2019-04-30 | 2019-08-25 | 2019-09-02 | 2019-09-05 | 2019-10-17 |  | NA | NA |  |  | 2019-09-11 | 27.5055 | 41.6404 | 2019-09-15 | 2019-09-26 | ZHAA021 |  |  | 2019-10-20 | 2019-10-20 | Pending HOC | 2019-09-15 | 2019-10-28 | W4-Oct | W3-Oct | Non-Private | Baladiya | Amanh Hail | NA | 0 | 20*15 | GF | FBP Not Applied | Above | Abdulaziz | تم تسليم الموقع بدون رخصة كما تم الاتفاق مع توال
ZHB055 | Macro | Aspiration | Eastern | Hafr Batin | 2020 Scope | حفر الباطن | 28.4034 | 45.9385 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-05 | 2019-03-06 | Approved | 2019-05-25 15:40 | 2019-05-26 15:40 | IGATE | 27/05/2019 15:39:55 | SNR1010424 | SNR_Q | GM Technical Procurement | 2019-03-09 | 2019-04-10 | 2019-04-10 | 2019-04-14 | NA | NA | 2019-04-29 | 2019-08-26 | 2019-09-16 | 2019-09-17 | 2019-10-14 |  | NA | NA | 2019-08-26 |  | 2019-09-15 | 28.4023 | 45.9397 | 2019-10-08 | N | N |  |  | 2019-10-20 | 2019-10-20 | Pending HOC | 2019-11-15 | 2019-11-18 | W3-Nov | W3-Oct | Non-Private | Baladiya | Amanah Hafr Batin | NA | 50,000.00 | 10*10 | GF | FBP Not Issued | Below/… | Humaidy | تم تسليم الموقع بدون رخصة كما تم الاتفاق مع توال
ZHB899 | Macro | Aspiration | Eastern | Hafr Batin | 2020 Scope | حفر الباطن | 28.4096 | 46.0363 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-14 | 2019-03-15 | Approved | 2019-05-19 17:59 | 2019-05-20 17:59 | IGATE | 21/05/2019 17:59:19 | SNR1010318 | SNR_Q | GM Technical Procurement | 2019-03-18 | 2019-04-10 | 2019-04-10 | 2019-04-14 | NA | NA | 2019-04-17 | 2019-08-26 | 2019-09-16 | 2019-09-17 | 2019-10-06 | 2019-10-13 | NA | NA | 2019-08-26 |  | 2019-09-15 | 28.4106 | 46.0337 | 2019-09-17 | N | N |  |  | 2019-10-20 | 2019-10-20 | Pending HOC | 2019-10-15 | 2019-10-27 | W4-Oct | W3-Oct | Non-Private | Baladiya | Amanah Hafr Batin | NA | 50,000.00 | 10*10 | GF | FBP Not Issued | Below/… | Humaidy | تم تسليم الموقع بدون رخصة كما تم الاتفاق مع توال
ZHB037 | Macro | Aspiration | Eastern | Hafr Batin | 2020 Scope | حفر الباطن | 28.3937 | 45.9931 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-14 | 2019-03-15 | Approved | 2019-05-23 14:40 | 2019-05-24 14:40 | IGATE | 25/05/2019 14:39:49 | SNR1010380 | SNR_Q | GM Technical Procurement | 2019-03-18 | 2019-04-10 | 2019-04-10 | 2019-04-14 | NA | NA | 2019-05-20 | 2019-08-26 | 2019-09-16 | 2019-09-17 | 2019-10-14 |  | NA | NA | 2019-08-26 |  | 2019-09-15 | 28.3953 | 45.9917 | N | N | N |  |  | 2019-10-22 | 2019-10-22 | Pending HOC | 2019-11-15 | 2019-11-18 | W3-Nov |  | Non-Private | Baladiya | Amanah Hafr Batin | NA | 50,000.00 | 10*10 | GF | FBP Not Issued | Below/… | Humaidy | تم تسليم الموقع بدون رخصة كما تم الاتفاق مع توال
ZHB043 | Macro | Aspiration | Eastern | Hafr Batin | 2020 Scope | حفر الباطن | 28.3506 | 45.9898 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-14 | 2019-03-15 | Approved | 2019-08-04 19:45 | 2019-08-05 19:45 | IGATE | 06/08/2019 19:44:57 | SNR1011599 | SNR_O | Technical Procurement Section Manager | 2019-03-18 | 2019-04-10 | 2019-04-10 | 2019-04-14 | NA | NA | 2019-04-17 | 2019-10-09 | 2019-10-09 | 2019-10-13 | 2019-10-17 |  | NA | NA | [10 empty] | 2019-10-21 | 2019-10-21 | Pending HOC | 2019-10-15 | 2019-11-18 | W3-Nov | W3-Oct | Non-Private | Baladiya | Amanah Hafr Batin | NA | 0 | 0 | GF | FBP Not Applied | Above | Humaidy | تم تسليم الموقع بدون رخصة كما تم الاتفاق مع توال
ZHB053 | Macro | Aspiration | Eastern | Hafr Batin | 2020 Scope | حفر الباطن | 28.4444 | 46.0261 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-04-06 | 2019-04-07 | Approved | 2019-05-23 13:56 | 2019-05-24 13:56 | IGATE | 25/05/2019 13:56:19 | SNR1010377 | NOBODY | ACCEPTED | 2019-04-10 | 2019-04-10 | 2019-05-25 | 2019-06-17 | 2019-06-19 | 2019-08-05 | NA | NA | NA | NA | NA | NA | 2019-07-25 | 2019-08-04 | 2019-08-05 | 2019-08-26 | 2019-07-31 | 28.4448 | 46.0243 | 2019-08-20 | 2019-08-27 | ZHB003 |  |  | 2019-08-26 | 2019-08-27 | FDED Not Approved | 2019-11-15 | Done | HOC Done |  | Private | Private | مبارك العنزي | 0557786745 | 20,000.00 | 20x20 | GF | HO to CW Done | HO Done | Humaidy | تم تسليم الموقع
ZBK030 | Macro | Aspiration | Central | Qassim | 2020 Scope | البكيرية | 26.1435 | 43.5972 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-10 | 2019-03-11 | Approved | 2019-05-12 16:31 | 2019-05-13 16:31 | IGATE | 14/05/2019 16:31:26 | SNR1010242 | SNR_Q | GM Technical Procurement | 2019-03-14 | 2019-04-10 | 2019-04-10 | 2019-04-21 | NA | NA | 2019-04-16 | 2019-05-08 | 2019-07-04 | 2019-09-29 | 2019-10-06 | 2019-10-10 | NA | NA | 2019-10-06 | 2019-10-10 | 2019-09-11 | 26.145229° | 43.597761° | 2019-09-19 | 2019-10-03 | 606-00-000 |  |  | 2019-10-10 | 2019-10-10 | Pending HOC | 2019-11-15 | Done | HOC Done |  | Non-Private | Baladiya | Baladiah Albkareah | NA | 30,000.00 | 20*20 | GF | HO to CW Done | Below BM | A Sughair | تم تسليم الموقع
ZHB054 | Macro | Aspiration | Eastern | Hafr Batin | 2020 Scope | حفر الباطن | 28.4386 | 45.9264 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-04-06 | 2019-04-07 | Approved | 2019-05-25 15:34 | 2019-05-26 15:34 | IGATE | 27/05/2019 15:33:45 | SNR1010422 | NOBODY | ACCEPTED | 2019-04-10 | 2019-04-10 | 2019-06-17 | 2019-06-17 | 2019-06-17 | 2019-06-20 | NA | NA | NA | NA | NA | NA | 2019-06-20 | 2019-07-04 | 2019-07-09 | 2019-07-18 | 2019-07-23 | 28.4375 | 45.9281 | 2019-06-24 | 2019-07-30 | ZHB980 |  |  | 2019-07-21 | 2019-07-23 | FDED Not Approved | 2019-11-15 | Done | HOC Done |  | Private | Private | نواف الظفيري / أحمد العنزي / فلاح الرويلي | 0555835285 | 25,000.00 | 20 M * 20 M | GF | HO to CW Done | HO Done | Humaidy | تم تسليم الموقع
ZHB926 | Macro | Aspiration | Eastern | Hafr Batin | 2020 Scope | حفر الباطن | 28.4275 | 45.9381 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-05 | 2019-03-06 | Approved | 2019-05-14 14:15 | 2019-05-15 14:15 | IGATE | 16/05/2019 14:14:49 | SNR1010282 | NOBODY | ACCEPTED | 2019-03-09 | 2019-04-10 | 2019-04-10 | 2019-04-10 | 2019-04-24 | 2019-07-16 | NA | NA | NA | NA | NA | NA | 2019-07-11 | 2019-07-18 | 2019-07-16 | 2019-07-18 | 2019-07-17 | 28.4276 | 45.939 | 2019-07-21 | 2019-07-23 | ZHB980 |  |  | 2019-07-21 | 2019-07-23 | FDED Not Approved | 2019-10-15 | Done | HOC Done |  | Private | Private | عليوي جربوع العنزي | 0507148519 | 25,000.00 | 20*20 | GF | HO to CW Done | HO Done | Humaidy | تم تسليم الموقع
ZAB444 | Macro | Aspiration | Southern | Baha | 2020 Scope | بلقرن | 19.5913 | 41.8797 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-08 | 2019-03-09 | Approved | 2019-05-02 14:15 | 2019-05-03 14:15 | IGATE | 04/05/2019 14:15:11 | SNR1010042 | SNR_O | Technical Procurement Section Manager | 2019-03-12 | 2019-04-10 | 2019-04-10 | 2019-04-10 | NA | NA | 2019-04-15 | 2019-09-30 | 2019-10-01 | 2019-10-01 | 2019-10-14 | 2019-10-21 | NA | NA | 2019-10-15 | 2019-10-20 | 2019-10-06 | 19.6005 | 41.8737 | 2019-10-17 | 2019-10-06 | MW037 |  |  | 2019-10-17 | 2019-10-17 | Pending HOC | 2019-08-15 | 2019-10-23 | W3-Oct | W2-Oct | Non-Private | Baladiya | Baladiya Belqarn | NA | 0 | 400m | GF | HO to CW Done | Below BM | Ali Asiri | تم تسليم الموقع
ZHB027 | Macro | Aspiration | Eastern | Hafr Batin | 2020 Scope | الذيبية | 28.1231 | 45.6595 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-14 | 2019-03-15 | Approved | 2019-05-19 19:12 | 2019-05-20 19:12 | IGATE | 29/10/2019 17:17:58 | SNR1012256 | SNR_D | Vendor SA | 2019-03-18 | 2019-04-10 | 2019-04-10 | 2019-04-14 | NA | NA | 2019-04-24 | 2019-09-30 | 2019-09-30 | 2019-10-02 | 2019-11-11 |  |  |  | 2019-11-11 |  |  |  |  | 2019-10-20 |  |  |  |  | 2019-11-13 |  | Pending HOC | 2019-10-15 | 2019-10-27 | W4-Oct |  | Non-Private | Baladiya | Baladiya Thebeyya | NA | 0 | 3.7*12 | GF | Priv. Contract Not Issued From TAWAL | Above | Humaidy | بانتظار توقيع العقد من المشتريات
ZHB028 | Macro | Aspiration | Eastern | Hafr Batin | 2020 Scope | الذيبية | 28.116 | 45.6681 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-14 | 2019-03-15 | Approved | 2019-07-06 10:48 | 2019-07-07 10:48 | IGATE | 08/07/2019 10:48:10 | SNR1011132 | SNR_K | Procurement Department Employee | 2019-03-18 | 2019-04-10 | 2019-04-10 | 2019-04-10 | NA | NA | 2019-04-24 | 2019-09-30 | 2019-09-30 | 2019-10-02 | 2019-11-11 |  |  |  | 2019-11-11 |  |  |  |  | 2019-10-20 |  |  |  |  | 2019-11-13 |  | Pending HOC | 2019-10-15 | 2019-10-27 | W4-Oct |  | Non-Private | Baladiya | Baladiya Thebeyya | NA | 0 | 35m | GF | Priv. Contract Not Issued From TAWAL | Above | Humaidy | بانتظار توقيع العقد من المشتريات
ZNR028 | Macro | Aspiration | Eastern | Hafr Batin | 2020 Scope | النعيرية | 27.4588 | 48.5155 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-15 | 2019-03-16 | Approved | 2019-05-19 19:37 | 2019-05-20 19:37 | IGATE | 17/10/2019 09:29:19 | SNR1012128 | SNR_M | Procurement Department Employee | 2019-03-19 | 2019-04-10 | 2019-04-10 | 2019-04-14 | NA | NA | 2019-04-18 | 2019-07-29 | 2019-08-28 | 2019-11-07 | 2019-11-11 |  |  |  | 2019-11-11 | [9 empty] | 2019-11-13 |  | Pending HOC | 2019-10-15 | 2019-11-25 | W4-Nov |  | Non-Private | Baladiya | Baladiya Neariyya | NA | 0 | 0 | GF | Priv. Contract Not Issued From TAWAL | Above | Faris | تم تقديم ISR جديد بسعر اقل وبانتظار موافقة RF
ZHB936 | Macro | Aspiration | Eastern | Hafr Batin | 2020 Scope | القيصومة | 28.3091 | 46.1297 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-05 | 2019-03-06 | Approved | 2019-05-20 16:26 | 2019-05-21 16:26 | IGATE | 22/05/2019 16:25:31 | SNR1010365 | SNR_O | Technical Procurement Section Manager | 2019-03-09 | 2019-04-10 | 2019-05-14 | 2019-05-13 | NA | NA | 2019-04-24 | 2019-11-09 | 2019-11-09 | 2019-11-09 | 2019-11-11 |  |  |  | 2019-11-11 |  |  |  |  | 2019-10-20 |  |  |  |  | 2019-11-13 |  | Pending HOC | 2019-11-15 | 2019-12-05 | W1-Dec |  | Non-Private | Baladiya | Baladiya Qaisomah | NA | 0 | 0 | GF | Priv. Contract Not Issued From TAWAL | Above | Humaidy | تحت التخطيط بالبلدية بانتظار موافقتهم - يحتاج ما يقارب 3 اسابيع لاصدار العقد
ZNR029 | Macro | Aspiration | Eastern | Hafr Batin | 2020 Scope | النعيرية | 27.4678 | 48.5258 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-15 | 2019-03-16 | Approved | 2019-05-23 16:02 | 2019-05-24 16:02 | IGATE | 25/05/2019 16:01:45 | SNR1010387 | SNR_O | Technical Procurement Section Manager | 2019-03-19 | 2019-04-10 | 2019-04-10 | 2019-04-10 | NA | NA | NA | NA | NA | NA | NA | NA | 2019-10-17 | 2019-10-22 | 2019-10-22 | [9 empty] | 2019-10-22 | 2019-10-22 | Pending HOC | 2019-10-15 | 2019-11-05 | W1-Nov |  | Private | Private | Baladiya Neariyya | 0504430343/0566678342 | 0 | 0 | GF | FBP Not Issued | Above | Faris | تم تسليم الموقع بدون رخصة كما تم الاتفاق مع توال
ZHB023 | Macro | Aspiration | Eastern | Hafr Batin | 2019 Scope | حفر الباطن | 28.4497 | 45.9631 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-06-30 | 2019-07-01 | Approved | 2019-08-03 18:46 | 2019-08-04 18:46 | IGATE | 02/10/2019 18:41:31 | SNR1012002 | SNR_O | Technical Procurement Section Manager | 2019-07-04 | 2019-07-04 | 2019-08-20 | 2019-09-03 |  |  | NA | NA | NA | NA | NA | NA | 2019-10-14 | 2019-10-22 | 2019-10-15 | [9 empty] | 2019-10-22 | 2019-10-22 | Pending HOC |  | 2019-10-27 | W4-Oct |  | Private | Private | لميعه بنت جريد بن علي الظفيري | NA | 0 | 0 | GF | FBP Not Issued | Above | Humaidy | تم تسليم الموقع بدون رخصة كما تم الاتفاق مع توال
ZHF245 | Macro | Aspiration | Eastern | Hofof | 2020 Scope | الاحساء | 25.3067 | 49.5127 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-08 | 2019-03-09 | Approved | 2019-05-23 14:26 | 2019-05-24 14:26 | IGATE | 25/05/2019 14:25:55 | SNR1010378 | SNR_I | District Support | 2019-03-12 | 2019-04-10 | 2019-04-10 | 2019-04-14 | NA | NA | 2019-04-16 | [19 empty] | Pending HOC | 2019-09-15 | 2019-12-15 | W3-Dec |  | Non-Private | Baladiya | Amanah Ahsa | NA | 0 | 0 | GF | IBP Not Issued | Above | Salah | تحت التخطيط بالبلدية بانتظار موافقتهم - يحتاج ما يقارب 2 اسبوع لاصدار العقد
ZHF255 | Macro | Aspiration | Eastern | Hofof | 2020 Scope | الاحساء | 25.3407 | 49.5393 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-13 | 2019-03-14 | Approved | 2019-05-23 17:25 | 2019-05-24 17:25 | IGATE | 25/05/2019 17:24:51 | SNR1010397 | SNR_I | District Support | 2019-03-17 | 2019-04-10 | 2019-04-10 | 2019-04-14 | NA | NA | 2019-04-16 | [19 empty] | Pending HOC | 2019-09-15 | 2019-12-20 | W3-Dec |  | Non-Private | Baladiya | Amanah Ahsa | NA | 0 | 0 | GF | IBP Not Issued | Above | Salah | بانتظار البلدية لتقديم موقع جديد حيث تم رفض الموقع المقترح من RF
ZHF257 | Macro | Aspiration | Eastern | Hofof | 2020 Scope | الاحساء | 25.2984 | 49.59 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-13 | 2019-03-14 | Approved | 2019-05-23 17:31 | 2019-05-24 17:31 | IGATE | 25/05/2019 17:30:40 | SNR1010398 | SNR_I | District Support | 2019-03-17 | 2019-04-10 | 2019-04-10 | 2019-04-16 | NA | NA | 2019-06-18 | [19 empty] | Pending HOC | 2019-11-15 | 2019-12-15 | W3-Dec |  | Non-Private | Baladiya | Amanah Ahsa | NA | 0 | 0 | GF | IBP Not Issued | Above | Salah | تحت التخطيط بالبلدية بانتظار موافقتهم - يحتاج ما يقارب 2 اسبوع لاصدار العقد
ZHF292 | Macro | Aspiration | Eastern | Hofof | 2020 Scope | الاحساء | 25.4689 | 49.5387 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-08 | 2019-03-09 | Approved | 2019-05-02 14:50 | 2019-05-03 14:50 | IGATE | 04/05/2019 14:50:21 | SNR1010044 | SNR_O | Technical Procurement Section Manager | 2019-03-12 | 2019-04-10 | 2019-04-10 | 2019-04-14 | NA | NA | 2019-04-16 | 2019-10-10 | 2019-10-10 | 2019-10-13 | 2019-10-14 |  | NA | NA | 2019-10-15 | [9 empty] | 2019-10-21 | 2019-10-21 | Pending HOC | 2019-09-15 | 2019-12-12 | W2-Dec | W3-Oct | Non-Private | Baladiya | Amanah Ahsa | NA | 0 | 0 | GF | FBP Not Issued | Above | Salah | تم تسليم الموقع بدون رخصة كما تم الاتفاق مع توال
ZHF293 | Macro | Aspiration | Eastern | Hofof | 2020 Scope | الاحساء | 25.4695 | 49.5498 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-08 | 2019-03-09 | Approved | 2019-05-19 17:32 | 2019-05-20 17:32 | IGATE | 21/05/2019 17:32:25 | SNR1010316 | SNR_O | Technical Procurement Section Manager | 2019-03-12 | 2019-04-10 | 2019-04-10 | 2019-04-14 | NA | NA | 2019-04-16 | 2019-10-10 | 2019-10-10 | 2019-10-13 | 2019-10-14 |  | NA | NA | 2019-10-15 | [9 empty] | 2019-10-21 | 2019-10-21 | Pending HOC | 2019-09-15 | 2019-12-12 | W2-Dec | W3-Oct | Non-Private | Baladiya | Amanah Ahsa | NA | 0 | 0 | GF | FBP Not Issued | Above | Salah | تم تسليم الموقع بدون رخصة كما تم الاتفاق مع توال
ZHF303 | Macro | Aspiration | Eastern | Hofof | 2020 Scope | الاحساء | 25.3045 | 49.5328 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-13 | 2019-03-14 | Approved | 2019-05-02 15:10 | 2019-05-03 15:10 | IGATE | 04/05/2019 15:09:33 | SNR1010045 | SNR_O | Technical Procurement Section Manager | 2019-03-17 | 2019-04-10 | 2019-04-10 | 2019-04-10 | NA | NA | 2019-04-16 | 2019-10-10 | 2019-10-10 | 2019-10-13 | 2019-10-14 |  | NA | NA | 2019-10-15 | [9 empty] | 2019-10-21 | 2019-10-21 | Pending HOC | 2019-10-15 | 2019-12-12 | W2-Dec | W3-Oct | Non-Private | Baladiya | Amanah Ahsa | NA | 0 | 0 | GF | FBP Not Issued | Above | Salah | تم تسليم الموقع بدون رخصة كما تم الاتفاق مع توال
ZHF767 | Macro | Aspiration | Eastern | Hofof | 2020 Scope | الاحساء | 25.4405 | 49.5616 | Huawei | Removed from Scope | New Location | NA | NA | Macro | Not Doable | under remove form Scope | Approved | 2019-03-13 | 2019-03-14 | Approved | 2019-05-03 11:40 | 2019-05-04 11:40 | IGATE | 05/05/2019 11:40:13 | SNR1010062 | NOBODY | REJECTED | 2019-03-17 | 2019-04-10 | 2019-04-10 | 2019-04-14 | NA | NA | 2019-06-18 | [20 empty] | 2019-11-15 | 2019-12-15 | W3-Dec |  | Non-Private | Baladiya | Amanah Ahsa | NA | 0 | 0 | GF | IBP Not Issued | Above | Salah | Removed from Scope
ZHF780 | Macro | Aspiration | Eastern | Hofof | 2020 Scope | الاحساء | 25.4397 | 49.5879 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-15 | 2019-03-16 | Approved | 2019-05-02 15:27 | 2019-05-03 15:27 | IGATE | 04/05/2019 15:26:49 | SNR1010047 | SNR_I | District Support | 2019-03-19 | 2019-04-10 | 2019-04-10 | 2019-04-14 | NA | NA | 2019-04-16 | [19 empty] | Pending HOC | 2019-10-15 | 2019-12-15 | W3-Dec |  | Non-Private | Baladiya | Amanah Ahsa | NA | 0 | 0 | GF | IBP Not Issued | Above | Salah | تحت التخطيط بالبلدية بانتظار موافقتهم - يحتاج ما يقارب 2 اسبوع لاصدار العقد
ZHF248 | Macro | Aspiration | Eastern | Hofof | 2020 Scope | الاحساء | 25.2994 | 49.7182 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-13 | 2019-03-14 | Approved | 2019-05-19 17:22 | 2019-05-20 17:22 | IGATE | 21/05/2019 17:21:47 | SNR1010315 | NOBODY | ACCEPTED | 2019-03-17 | 2019-04-10 | 2019-04-10 | 2019-04-10 | 2019-04-24 | 2019-06-20 | NA | NA | NA | NA | NA | NA | 2019-06-20 | 2019-07-02 | 2019-07-02 | 2019-10-22 | 2019-06-25 | 25.2997 | 49.7201 | 2019-06-24 | 2019-08-29 | ZHF205 |  |  | 2019-10-17 | 2019-10-17 | Pending HOC | 2019-09-15 | 2019-10-20 | W3-Oct | W2-Oct | Private | Private | ميدان الفروسيه بالاحساء | 0504921821 | 30,000.00 | 20 M * 20 M | GF | HO to CW Done | Below BM | Salah | تم تسليم الموقع بدون رخصة كما تم الاتفاق مع توال
ZJL003 | Macro | Aspiration | Central | Riyadh District | 2020 Scope | جلاجل | 25.7063 | 45.4632 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-06 | 2019-03-07 | Approved | 2019-05-20 11:08 | 2019-05-21 11:08 | IGATE | 22/05/2019 11:07:35 | SNR1010355 | NOBODY | ACCEPTED | 2019-03-10 | 2019-04-10 | 2019-04-10 | 2019-04-10 | NA | NA | 2019-04-14 | 2019-07-02 | 2019-07-02 | 2019-07-03 | 2019-07-11 | 2019-07-21 | NA | NA | 2019-07-14 | 2019-07-14 | 2019-07-03 | 25.706440° | 45.462950° | 2019-07-10 | 2019-07-17 | 686-45-000 |  |  | 2019-07-16 | 2019-07-18 | FDED Not Approved | 2019-10-15 | Done | HOC Done |  | Non-Private | Baladiya | Baladiyah Jalajl | NA | 24,750.00 | 15*15 | GF | HO to CW Done | HO Done | Ghamdi | تم تسليم الموقع
ZJL004 | Macro | Aspiration | Central | Riyadh District | 2020 Scope | جلاجل | 25.6822 | 45.452 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-06 | 2019-03-07 | Approved | 2019-05-20 11:17 | 2019-05-21 11:17 | IGATE | 22/05/2019 11:16:45 | SNR1010356 | NOBODY | ACCEPTED | 2019-03-10 | 2019-04-10 | 2019-04-10 | 2019-04-10 | NA | NA | 2019-04-14 | 2019-07-02 | 2019-07-02 | 2019-07-03 | 2019-07-11 | 2019-07-21 | NA | NA | 2019-07-14 | 2019-07-14 | 2019-07-03 | 25.682370° | 45.452800° | 2019-07-10 | 2019-08-04 | ZJLA999 |  |  | 2019-07-16 | 2019-07-18 | FDED Not Approved | 2019-10-15 | Done | HOC Done |  | Non-Private | Baladiya | Baladiyah Jalajl | NA | 29,250.00 | 15*15 | GF | HO to CW Done | HO Done | Ghamdi | تم تسليم الموقع
ZBS341 | Macro | Aspiration | Southern | Baha | 2020 Scope | بيشة | 19.8968 | 42.5988 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-08 | 2019-03-09 | Approved | 2019-06-11 11:29 | 2019-06-12 11:29 | IGATE | 13/06/2019 11:29:16 | SNR1010512 | SNR_O | Technical Procurement Section Manager | 2019-03-12 | 2019-04-10 | 2019-04-10 | 2019-04-14 | NA | NA | 2019-04-23 | 2019-07-07 | 2019-07-07 | 2019-09-30 | 2019-10-21 | 2019-10-27 | NA | NA |  |  | 2019-10-08 | 19.897 | 42.5988 | 2019-10-20 | 2019-10-24 | Z90014 |  |  | 2019-10-21 | 2019-10-21 | Pending HOC | 2019-07-20 | 2019-10-23 | W3-Oct | W3-Oct | Non-Private | Baladiya | Bisha Municipality | NA | 30,000.00 | 20X20 | GF | FBP Not Applied | Below BM | Ali Asiri | تم تسليم الموقع بدون رخصة كما تم الاتفاق مع توال
ZTB402 | Macro | Aspiration | Northern | Tabuk | 2020 Scope | حرس الحدود بمنطقة تبوك | 28.0282 | 34.6315 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-04-18 | 2019-04-19 | Approved | 2019-06-11 10:41 | 2019-06-12 10:41 | IGATE | 13/06/2019 10:40:39 | SNR1010511 | SNR_I | District Support | 2019-04-22 | 2019-06-17 | 2019-06-17 | 2019-06-17 | NA | NA | 2019-04-18 | [19 empty] | Pending HOC | 2019-12-18 | 2019-11-20 | W3-Nov |  | Non-Private | Gov | Border Guard in Tabuk | NA | 0 | 0 | GF | IBP Not Issued | Above | Hatem | بانتظار اصدار العقد من حرس الحدود
ZHF279 | Macro | Aspiration | Eastern | Hofof | 2020 Scope | الحرس الوطني | 25.4751 | 49.51 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-04-06 | 2019-04-07 | Approved | 2019-07-08 18:24 | 2019-07-09 18:24 | IGATE | 10/07/2019 18:23:58 | SNR1011232 | SNR_I | District Support | 2019-04-10 | 2019-07-04 | 2019-07-04 | 2019-07-04 | NA | NA | 2019-05-05 | [19 empty] | Pending HOC | 2019-11-15 | 2019-11-20 | W3-Nov |  | Non-Private | Gov | NG | NA | 0 | 0 | GF | IBP Not Issued | Above | M. Ramadan | بانتظار محضر المعاينة من الحرس الوطني وتحتاج ما يقارب 3 اسابيع -مع التاكيد بتعديل الفقرة 11
ZHF294 | Macro | Aspiration | Eastern | Hofof | 2020 Scope | الحرس الوطني | 25.4535 | 49.5039 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-04-06 | 2019-04-07 | Approved | 2019-07-08 18:21 | 2019-07-09 18:21 | IGATE | 10/07/2019 18:21:02 | SNR1011231 | SNR_I | District Support | 2019-04-10 | 2019-07-04 | 2019-07-04 | 2019-07-04 | NA | NA | 2019-05-05 | [19 empty] | Pending HOC | 2019-11-15 | 2019-11-20 | W3-Nov |  | Non-Private | Gov | NG | NA | 0 | 0 | GF | IBP Not Issued | Above | M. Ramadan | بانتظار محضر المعاينة من الحرس الوطني وتحتاج ما يقارب 3 اسابيع -مع التاكيد بتعديل الفقرة 11
ZAQ046 | Macro | Aspiration | Eastern | Dammam | 2019 Scope | أرامكو | 25.932131 | 49.662954 | Huawei | Critical Site | New Location | SHARING/MOBILY | GF | Macro | Doable |  | Approved | 2019-06-30 | 2019-07-01 | Approved | 2019-07-09 10:43 | 2019-07-10 10:43 | IGATE | 11/07/2019 10:43:05 | SNR1011248 | SNR_I | District Support | 2019-07-04 | 2019-07-04 | 2019-07-04 | 2019-07-04 | NA | NA | 2019-07-01 | [19 empty] | FBP Not submitted |  | 2019-12-12 | W2-Dec |  | Non-Private | Gov | أرامكو | NA | 0 | 0 | GF | IBP Not Issued |  | Ali
ZDM189 | Macro | Aspiration | Eastern | Dammam | 2019 Scope | غرب الدمام | 26.4139 | 50.0589 | Huawei | Critical Site | To Remove as SAFE | SHARING/MOBILY | GF | Macro | Doable |  | Approved | 2019-06-09 | 2019-06-10 | Approved | 2019-06-15 11:12 | 2019-06-16 11:12 | IGATE | 17/06/2019 11:11:38 | SNR1010561 | SNR_I | District Support | 2019-06-13 | 2019-06-13 | 2019-06-17 | 2019-06-21 | NA | NA | 2019-06-26 | [19 empty] | FBP Not submitted |  | 2019-11-05 | W1-Nov |  | Non-Private | Baladiya | West Dammam Baladiyah | NA | 0 | 0 | GF | IBP Not Issued |  | Ali | انتظار طباعة العقد من البلدية
ZDM190 | Macro | Aspiration | Eastern | Dammam | 2019 Scope | غرب الدمام | 26.410673 | 50.026671 | Huawei | Critical Site | New Location | SHARING/MOBILY | GF | Macro | Doable |  | Approved | 2019-06-09 | 2019-06-10 | Approved | 2019-06-15 11:18 | 2019-06-16 11:18 | IGATE | 17/06/2019 11:18:19 | SNR1010562 | SNR_I | District Support | 2019-06-13 | 2019-06-13 | 2019-06-17 | 2019-06-21 | NA | NA | 2019-06-26 | [19 empty] | No Dependency |  | 2019-11-05 | W1-Nov |  | Non-Private | Baladiya | West Dammam Baladiyah | NA | 0 | 0 | GF | IBP Not Issued |  | Ali | انتظار طباعة العقد من البلدية
ZDM191 | Macro | Aspiration | Eastern | Dammam | 2019 Scope | حرس وطني | 26.356820 | 50.179010 | Huawei | Critical Site | New Location | SHARING/MOBILY | GF | Macro | Doable |  | Approved | 2019-06-30 | 2019-07-01 | Approved | 2019-07-09 15:50 | 2019-07-10 15:50 | IGATE | 11/07/2019 15:50:04 | SNR1011275 | SNR_I | District Support | 2019-07-04 | 2019-07-04 | 2019-07-04 | 2019-07-04 | NA | NA | 2019-07-28 | [19 empty] | FBP Not submitted |  | 2019-12-12 | W2-Dec |  | Non-Private | Gov | NG | NA | 0 | 0 | GF | IBP Not Issued |  | Naser
ZHB057 | Macro | Aspiration | Eastern | Hafr Batin | 2019 Scope | حفر الباطن | 28.385277 | 45.997500 | Huawei | Critical Site | New Location | SHARING/MOBILY | GF | Macro | Doable |  | Approved | 2019-06-09 | 2019-06-10 | Approved | 2019-06-15 11:55 | 2019-06-16 11:55 | IGATE | 17/06/2019 11:54:51 | SNR1010567 | SNR_I | District Support | 2019-06-13 | 2019-06-13 | 2019-06-17 | 2019-06-21 | NA | NA | 2019-06-26 | [19 empty] | FBP Not submitted |  | 2019-11-18 | W3-Nov |  | Non-Private | Baladiya | Hafr Al Batin Baladiyah | NA | 0 | 0 | GF | IBP Not Issued |  | Humaidy
ZHB061 | Macro | Aspiration | Eastern | Hafr Batin | 2019 Scope | حفر الباطن | 28.275540 | 45.948800 | Huawei | Critical Site | New Location | SHARING/MOBILY | GF | Macro | Doable |  | Approved | 2019-06-09 | 2019-06-10 | Approved | 2019-06-15 12:12 | 2019-06-16 12:12 | IGATE | 17/06/2019 12:11:43 | SNR1010570 | SNR_O | Technical Procurement Section Manager | 2019-06-13 | 2019-06-13 | 2019-06-17 | 2019-06-21 | NA | NA | 2019-06-30 | 2019-09-16 | 2019-09-16 | 2019-09-17 |  |  |  |  | 2019-08-26 |  | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | No Dependency |  | 2019-11-18 | W3-Nov |  | Non-Private | Baladiya | Hafr Al Batin Baladiyah | NA | 0 | 0 | GF | Contract Not Signed by TAWAL | Above | Humaidy
ZHB064 | Macro | Aspiration | Eastern | Hafr Batin | 2019 Scope | حفر الباطن | 28.3782 | 45.9811 | Huawei | Critical Site | To Remove as SAFE | SHARING/MOBILY | GF | Macro | Doable |  | Approved | 2019-06-12 | 2019-06-13 | Approved | 2019-06-30 11:54 | 2019-07-01 11:54 | IGATE | 02/07/2019 11:54:01 | SNR1010926 | NOBODY | REJECTED | 2019-06-16 | 2019-06-16 | 2019-06-20 | 2019-06-20 | 2019-07-03 | 2019-08-28 | NA | NA | NA | NA | NA | NA | 2019-08-28 | 2019-09-08 | 2019-09-11 |  | 2019-09-07 | 28.3789 | 45.9862 | 2019-09-29 | 2019-10-06 | ZHB005 |  |  |  |  | FBP Not submitted |  | 2019-11-18 | W3-Nov |  | Private | Private |  | NA | 0.00 | 20x20 | GF | FBP Not Issued |  | Humaidy
ZHF341 | Macro | Aspiration | Eastern | Hofof | 2019 Scope | أرامكو | 24.110910 | 49.208219 | Huawei | Critical Site | New Location | SHARING/MOBILY | GF | Macro | Doable |  | Approved | 2019-06-30 | 2019-07-01 | Approved | 2019-07-09 11:05 | 2019-07-10 11:05 | IGATE | 11/07/2019 11:04:57 | SNR1011251 | SNR_I | District Support | 2019-07-04 | 2019-07-04 | 2019-07-04 | 2019-07-04 | NA | NA | 2019-07-01 | [19 empty] | FBP Not submitted |  | 2019-12-12 | W2-Dec |  | Non-Private | Gov | أرامكو | NA | 0 | 0 | GF | IBP Not Issued |  | Salah
ZHF342 | Macro | Aspiration | Eastern | Hofof | 2019 Scope | الهفوف | 25.407500 | 49.468333 | Huawei | Critical Site | New Location | SHARING/MOBILY | GF | Macro | Doable |  | Approved | 2019-06-12 | 2019-06-13 | Approved | 2019-06-15 12:29 | 2019-06-16 12:29 | IGATE | 17/06/2019 12:29:23 | SNR1010577 | SNR_I | District Support | 2019-06-16 | 2019-06-16 | 2019-06-20 | 2019-06-24 | NA | NA | 2019-06-26 | [19 empty] | No Dependency |  | 2019-12-12 | W2-Dec |  | Non-Private | Baladiya | Al Ehsa Amanah | NA | 0 | 0 | GF | IBP Not Issued |  | Salah
ZHF344 | Macro | Aspiration | Eastern | Hofof | 2019 Scope | وزارة البيئة والزراعة | 25.461000 | 49.562100 | Huawei | Critical Site | New Location | SHARING/MOBILY | GF | Macro | Doable |  | Approved | 2019-08-02 | 2019-08-03 | Approved | 2019-08-04 20:06 | 2019-08-05 20:06 | IGATE | 06/08/2019 20:05:54 | SNR1011600 | SNR_I | District Support | 2019-08-06 | [5 empty] | 2019-06-25 | [19 empty] | ISR not Approved |  | 2019-12-12 | W2-Dec |  | Non-Private | Baladiya |  | 0 | 0 | 0 | GF | ISR Not Sub to RF |  | Salah
ZHF346 | Macro | Aspiration | Eastern | Hofof | 2019 Scope | الهفوف | 25.6215 | 49.5621 | Huawei | Critical Site | To Remove as SAFE | SHARING/MOBILY | GF | Macro | Doable |  | Approved | 2019-06-12 | 2019-06-13 | Approved | 2019-06-22 10:57 | 2019-06-23 10:57 | IGATE | 24/06/2019 10:56:56 | SNR1010773 | SNR_I | District Support | 2019-06-16 | 2019-06-16 | 2019-06-20 | 2019-06-24 | NA | NA | 2019-06-30 | [19 empty] | FBP Not submitted |  | 2019-12-12 | W2-Dec |  | Non-Private | Baladiya | Al Ehsa Amanah | NA | 0 | 0 | GF | IBP Not Issued |  | Salah
ZHF349 | Macro | Aspiration | Eastern | Hofof | 2019 Scope | الهفوف | 25.3383 | 49.6057 | Huawei | Critical Site | To Remove as SAFE | SHARING/MOBILY | GF | Macro | Doable |  | Approved | 2019-06-12 | 2019-06-13 | Approved | 2019-06-15 15:50 | 2019-06-16 15:50 | IGATE | 17/06/2019 15:50:12 | SNR1010606 | SNR_I | District Support | 2019-06-16 | 2019-06-16 | 2019-06-20 | 2019-06-24 |  |  | NA | NA | NA | NA | NA | NA | [14 empty] | No Dependency |  | 2019-12-12 | W2-Dec |  | Private | Private | نادي هجر - سامي القنيان | 0505922615 | 50,000.00 | 20*20 | GF | Priv. Contract Not Issued From TAWAL |  | Salah
ZHF350 | Macro | Aspiration | Eastern | Hofof | 2019 Scope | الهفوف | 25.341480 | 49.723390 | Huawei | Critical Site | New Location | SHARING/MOBILY | GF | Macro | Doable |  | Approved | 2019-06-11 | 2019-06-12 | Approved | 2019-06-15 15:57 | 2019-06-16 15:57 | IGATE | 17/06/2019 15:57:07 | SNR1010607 | SNR_I | District Support | 2019-06-15 | 2019-06-15 | 2019-06-19 | 2019-06-23 | NA | NA | 2019-06-30 | [19 empty] | No Dependency |  | 2019-12-12 | W2-Dec |  | Non-Private | Gov | STC | 0506945819 | 0 | 0 | GF | IBP Not Issued |  | Salah
ZKU061 | Macro | Aspiration | Eastern | Dammam | 2019 Scope | محطة الكهرباء | 25.830622 | 50.132686 | Huawei | Critical Site | New Location | SHARING/MOBILY | GF | Macro | Doable |  | Approved | 2019-06-30 | 2019-07-01 | Approved | 2019-07-09 11:01 | 2019-07-10 11:01 | IGATE | 11/07/2019 11:00:32 | SNR1011250 | SNR_I | District Support | 2019-07-04 | 2019-07-04 | 2019-07-04 | 2019-07-04 | NA | NA | 2019-06-26 | [19 empty] | FBP Not submitted |  | 2019-12-12 | W2-Dec |  | Non-Private | Gov | Aramco | NA | 0 | 0 | GF | IBP Not Issued |  | Ali
ZBS186 | Macro | Aspiration | Southern | Baha | 2020 Scope | الباحة | 20.104 | 42.5988 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-08 | 2019-03-09 | Approved | 2019-05-14 13:59 | 2019-05-15 13:59 | IGATE | 16/05/2019 13:59:14 | SNR1010281 | NOBODY | ACCEPTED | 2019-03-12 | 2019-04-10 | 2019-04-10 | 2019-04-10 | 2019-04-16 | 2019-04-30 | NA | NA | NA | NA | NA | NA | 2019-07-18 | 2019-07-18 | 2019-07-31 | 2019-07-31 | 2019-07-06 | 20.1047 | 42.5983 | 2019-07-08 | 2019-07-10 | ZBSA004 |  |  | 2019-08-07 | 2019-08-07 | FDED Not Approved | 2019-07-20 | Done | HOC Done |  | Private | Private | عبد الله الغامدي | 0580058880 | 25,000.00 | 20X20 | GF | HO to CW Done | HO Done | Done | تم تسليم الموقع
ZJZ076 | Macro | Aspiration | Southern | Jizan | 2020 Scope | جازان | 16.6098 | 42.9298 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-10 | 2019-03-11 | Approved | 2019-05-19 19:47 | 2019-05-20 19:47 | IGATE | 21/05/2019 19:46:43 | SNR1010324 | REQUESTER | REQUESTER | 2019-03-14 | 2019-04-10 | 2019-04-10 | 2019-04-10 | 2019-04-14 | 2019-05-16 | 2019-04-23 | [19 empty] | Pending HOC | 2019-06-03 | 2019-11-14 | W2-Nov |  | Non-Private | Baladiya | عبدالعزيز شعلي | 0532584440 | 0 | 0 | GF | IBP Not Issued | Below BM | Fahad Allam | RF not doable | need JR if no more location in area
ZNN721 | Macro | Aspiration | Southern | Najran | 2020 Scope | نجران | 17.5786 | 44.451 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-14 | 2019-03-15 | Approved | 2019-06-29 12:00 | 2019-06-30 12:00 | IGATE | 01/07/2019 11:59:31 | SNR1010891 | NOBODY | ACCEPTED | 2019-03-18 | 2019-04-10 | 2019-04-10 | 2019-04-10 | 2019-04-02 | 2019-04-30 | NA | NA | NA | NA | NA | NA | 2019-07-03 | 2019-07-03 | 2019-07-23 | 2019-07-31 | 2019-07-06 | 17.5794 | 44.4502 | 2019-07-08 | 2019-07-10 | ZNNA007 |  |  | 2019-08-01 | 2019-08-07 | FDED Not Approved | 2019-06-03 | Done | HOC Done |  | Private | Private | حسن عبدالرحمن ابوساق | 0504561646 | 20,000.00 | 20X20 | GF | HO to CW Done | HO Done | Done | تم تسليم الموقع
ZJZ167 | Macro | Aspiration | Southern | Jizan | 2020 Scope | جازان | 16.874 | 42.5826 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-16 | 2019-03-17 | Approved | 2019-05-02 13:01 | 2019-05-03 13:01 | IGATE | 04/05/2019 13:01:09 | SNR1010037 | SNR_O | Technical Procurement Section Manager | 2019-03-20 | 2019-04-10 | 2019-04-10 | 2019-04-14 | NA | NA | 2019-04-28 | 2019-09-23 | 2019-09-23 | 2019-10-30 | 2019-10-30 | [6 empty] | 16.8736 | 42.5816 | 2019-10-20 | 2019-10-23 | ZJZA017 |  |  | 2019-10-30 | 2019-11-03 | Pending HOC | 2019-07-20 | 2019-11-14 | W2-Nov |  | Non-Private | Baladiya | Amanah Jizan | NA | 0 | 17*17 | GF | Priv. Contract Not Issued From TAWAL | Above | Fahad Allam | تم تسليم الموقع بدون رخصة كما تم الاتفاق مع توال | need JR if no more location in area
ZRN026 | Macro | Aspiration | Central | Riyadh District | 2020 Scope | نادي الابل/بلدية الرماح | 25.6332 | 46.82 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-04-18 | 2019-04-19 | Approved | 2019-06-16 17:35 | 2019-06-17 17:35 | IGATE | 18/06/2019 17:35:26 | SNR1010675 | SNR_I | District Support | 2019-04-22 | 2019-06-16 | 2019-06-20 | 2019-06-24 | NA | NA | 2019-05-07 | [12 empty] | 2019-10-20 | [6 empty] | Pending HOC | 2019-09-15 | 2019-10-28 | W4-Oct |  | Non-Private | Gov | Camel Club | 0504101110 | 0 | 0 | GF | IBP Not Issued | Above | Ghamdi | بانتظار اصدار العقد من نادي الابل - حسب افادة راشد العجمي يحتاج من اسبوعين الى شهر
ZNN668 | Macro | Aspiration | Southern | Najran | 2020 Scope | نجران | 17.5461 | 44.2767 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-15 | 2019-03-16 | Approved | 2019-05-02 13:52 | 2019-05-03 13:52 | IGATE | 04/05/2019 13:52:05 | SNR1010040 | NOBODY | ACCEPTED | 2019-03-19 | 2019-04-10 | 2019-04-10 | 2019-04-14 | 2019-06-17 | 2019-06-20 | NA | NA | NA | NA | NA | NA | 2019-06-20 | 2019-07-02 | 2019-07-02 | 2019-08-28 | 2019-07-01 | 17.5465 | 44.2791 | 2019-07-03 | 2019-07-05 | MW2151 |  |  | 2019-08-28 | 2019-08-28 | FDED Not Approved | 2019-06-03 | Done | HOC Done |  | Private | Private | ياسين علي سالم ال ساري | 0500568080 | 20,000.00 | 20x20 | GF | HO to CW Done | HO Done | Done | تم تسليم الموقع
ZNN768 | Macro | Aspiration | Southern | Najran | 2020 Scope | نجران | 17.489 | 44.1712 | Huawei | New Site | New Location | NA | NA | Macro | Not Doable | No Deed Area | Approved | 2019-04-18 | 2019-04-19 | Approved | 2019-08-04 19:16 | 2019-08-05 19:16 | IGATE | 06/08/2019 19:16:11 | SNR1011596 | NOBODY | REJECTED | 2019-04-22 | 2019-09-03 | 2019-09-03 | 2019-09-03 | NA | NA | 2019-04-16 | [19 empty] | Pending HOC | 2019-10-15 | 2019-12-12 | W2-Dec |  | Non-Private | Baladiya | Amanah Najran | 0556899918 | 0 | 0 | GF | IBP Not Issued | Above | Nawaf | تم اصدار العقود
ZNN670 | Macro | Aspiration | Southern | Najran | 2020 Scope | نجران | 17.5851 | 44.2232 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-16 | 2019-03-17 | Approved | 2019-07-01 11:02 | 2019-07-02 11:02 | IGATE | 03/07/2019 11:02:16 | SNR1010974 | SNR_I | District Support | 2019-03-20 | 2019-04-10 | 2019-04-10 | 2019-04-10 | NA | NA | 2019-04-16 | [19 empty] | Pending HOC | 2019-07-20 | 2019-12-12 | W2-Dec |  | Non-Private | Baladiya | Amanah Najran | NA | 0 | 0 | GF | IBP Not Issued | Above | Nawaf | موقع جديد بانتظار ال RF
ZNN700 | Macro | Aspiration | Southern | Najran | 2020 Scope | نجران | 17.4561 | 44.1028 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-14 | 2019-03-15 | Approved | 2019-07-01 11:08 | 2019-07-02 11:08 | IGATE | 03/07/2019 11:08:16 | SNR1010976 | NOBODY | ACCEPTED | 2019-03-18 | 2019-04-10 | 2019-04-10 | 2019-04-10 | 2019-08-05 | 2019-08-05 | NA | NA | NA | NA | NA | NA | 2019-08-28 | 2019-09-04 | 2019-09-08 | 2019-10-16 | 2019-08-27 | 17.4551 | 44.1062 | 2019-08-29 | 2019-08-31 | ZNNA968 |  |  | 2019-10-16 | 2019-10-20 | Pending HOC | 2019-07-20 | 2019-10-17 | W2-Oct | W2-Oct | Private | Private | صالح سالم حميسي | 0504566330 | 20,000.00 | 20X20 | GF | HO to CW Done | Below BM | Nawaf | تم تسليم الموقع
ZNN680 | Macro | Aspiration | Southern | Najran | 2020 Scope | نجران | 17.5477 | 44.2484 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-14 | 2019-03-15 | Approved | 2019-05-25 09:36 | 2019-05-26 09:36 | IGATE | 28/10/2019 11:08:02 | SNR1012221 | SNR_K | Procurement Department Employee | 2019-03-18 | 2019-04-10 | 2019-04-10 | 2019-04-10 | NA | NA | 2019-04-16 | [19 empty] | Pending HOC | 2019-07-20 | 2019-12-12 | W2-Dec |  | Private | Private | Private | NA | 0 | 0 | GF | IBP Not Issued | Above | Nawaf | تحت العقد - تحت التثمين
ZNN741 | Macro | Aspiration | Southern | Najran | 2020 Scope | نجران | 17.5794 | 44.2284 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-14 | 2019-03-15 | Approved | 2019-06-15 16:31 | 2019-06-16 16:31 | IGATE | 17/06/2019 16:31:18 | SNR1010613 | SNR_O | Technical Procurement Section Manager | 2019-03-18 | 2019-04-10 | 2019-04-10 | 2019-04-10 | NA | NA | 2019-04-16 | 2019-10-10 | 2019-10-10 | 2019-10-10 | 2019-10-14 |  | NA | NA | 2019-10-15 | 2019-11-17 | 2019-10-17 | 17.5778 | 44.2293 | 2019-10-20 | 2019-10-22 | 715-13-000 |  |  | 2019-10-21 | 2019-10-21 | Pending HOC | 2019-07-20 | 2019-10-28 | W4-Oct | W3-Oct | Non-Private | Baladiya | Amanah Najran | NA | 0 | 0 | GF | HO to CW Done | Above | Nawaf | تم تسليم الموقع بدون رخصة كما تم الاتفاق مع توال
ZNN662 | Macro | Aspiration | Southern | Najran | 2019 Scope | نجران | 17.5777 | 44.3821 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-07-10 | 2019-07-11 | Approved | 2019-08-04 19:02 | 2019-08-05 19:02 | IGATE | 23/10/2019 17:13:05 | SNR1012175 | SNR_L | Real Estate Evaluator | 2019-07-14 | 2019-07-14 | 2019-09-03 | 2019-09-03 | NA | NA | 2019-08-05 | [9 empty] | 2019-10-17 | 17.58 | 44.3808 | 2019-10-17 | [6 empty] | FDED Not Approved |  | 2019-12-12 | W2-Dec |  | Private | Private | Private | 0555364015 | 0 | 0 | GF | IBP Not Issued | Above | Nawaf | تحت العقد - تحت التثمين
ZJZ364 | Macro | Aspiration | Southern | Jizan | 2020 Scope | الدرب | 17.7709 | 42.3241 | Huawei | New Site | New Location | NA | NA | Macro | Not Doable | No Deed Area | Approved | 2019-04-18 | 2019-04-19 | Approved | 2019-08-04 19:26 | 2019-08-05 19:26 | IGATE | 06/08/2019 19:25:33 | SNR1011597 | NOBODY | REJECTED | 2019-04-22 | 2019-09-03 | 2019-09-03 | 2019-09-03 | NA | NA | 2019-04-15 | [19 empty] | Pending HOC | 2019-07-20 | 2019-11-14 | W2-Nov |  | Non-Private | Baladiya | Baladiya Darb | 0505751959 | 0 | 0 | GF | IBP Not Issued | Above | Fahad Allam | no deed
ZRN027 | Macro | Aspiration | Central | Riyadh District | 2020 Scope | نادي الابل/بلدية الرماح | 25.6438 | 46.8299 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-04-18 | 2019-04-19 | Approved | 2019-06-16 17:52 | 2019-06-17 17:52 | IGATE | 18/06/2019 17:52:30 | SNR1010676 | SNR_I | District Support | 2019-04-22 | 2019-05-25 | 2019-05-25 | 2019-05-29 | NA | NA | 2019-05-07 | [12 empty] | 2019-10-20 | [6 empty] | Pending HOC | 2019-09-15 | 2019-10-28 | W4-Oct |  | Non-Private | Gov | Camel Club | 0504101110 | 0 | 0 | GF | IBP Not Issued | Above | Ghamdi | بانتظار اصدار العقد من نادي الابل - حسب افادة راشد العجمي يحتاج من اسبوعين الى شهر
ZBH639 | Macro | Aspiration | Southern | Baha | 2020 Scope | العقيق | 20.2645 | 41.6548 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-10 | 2019-03-11 | Approved | 2019-05-23 12:57 | 2019-05-24 12:57 | IGATE | 16/10/2019 11:26:59 | SNR1012115 | SNR_O | Technical Procurement Section Manager | 2019-03-14 | 2019-04-10 | 2019-05-25 |  | NA | NA | 2019-07-11 | 2019-07-11 | NA | NA | NA | NA | 2019-11-09 |  | 2019-11-09 |  | 2019-10-17 | 20.2647 | 41.654 | 2019-10-16 | 2019-11-10 | 712-11-000 | 45M | 400M | 2019-11-13 |  | Pending HOC | 2019-12-15 | 2019-11-14 | W2-Nov |  | Private | Private | Al Aqeq Baladiyah | 0 | 0 | 0 | GF | Priv. Contract Not Signed by Owner | Above | Ali Asiri | تم توقيع العقد المبدئي وتم رفعها بالاي قيت لاصدار العقد
ZBH590 | Macro | Aspiration | Southern | Baha | 2020 Scope | المخواه | 19.7442 | 41.4418 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-10 | 2019-03-11 | Approved | 2019-05-02 14:24 | 2019-05-03 14:24 | IGATE | 04/05/2019 14:23:47 | SNR1010043 | NOBODY | ACCEPTED | 2019-03-14 | 2019-04-10 | 2019-04-10 | 2019-04-10 | NA | NA | 2019-04-15 | 2019-04-15 | 2019-06-16 | 2019-06-16 | 2019-06-20 | 2019-06-30 | NA | NA | 2019-06-20 | 2019-07-10 | 2019-07-01 | 19.7443 | 41.4418 | 2019-07-03 | 2019-07-05 | ZBHA006 |  |  | 2019-07-10 | 2019-07-11 | CW Issue (Underground Utilities, etc,..) | 2019-06-03 | Done | HOC Done |  | Non-Private | Baladiya | Baladiya Mekhwah | NA | 34,800.00 | 20x20 | GF | HO to CW Done | HO Done | Done | تم تسليم الموقع
ZBH640 | Macro | Aspiration | Southern | Baha | 2020 Scope | المخواه | 19.7793 | 41.4295 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-10 | 2019-03-11 | Approved | 2019-05-02 12:34 | 2019-05-03 12:34 | IGATE | 04/05/2019 12:34:24 | SNR1010035 | NOBODY | ACCEPTED | 2019-03-14 | 2019-04-10 | 2019-04-10 | 2019-04-14 | NA | NA | 2019-04-15 | 2019-04-15 | 2019-04-18 | 2019-06-26 | 2019-07-14 | 2019-07-24 | NA | NA | 2019-07-14 | 2019-07-15 | 2019-07-01 | 19.7791 | 41.4293 | 2019-07-03 | 2019-07-05 | 712-31-000 |  |  | 2019-07-15 | 2019-07-18 | FDED Not Approved | 2019-06-03 | Done | HOC Done |  | Non-Private | Baladiya | Baladiya Mekhwah | NA | 34,800.00 | 20X20 | GF | HO to CW Done | HO Done | Done | تم تسليم الموقع
ZNM043 | Macro | Aspiration | Southern | Baha | 2020 Scope | النماص | 19.2474 | 42.0665 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-08 | 2019-03-09 | Approved | 2019-05-25 09:26 | 2019-05-26 09:26 | IGATE | 27/05/2019 09:26:14 | SNR1010411 | SNR_I | District Support | 2019-03-12 | 2019-04-10 | 2019-04-10 | 2019-09-03 | NA | NA | 2019-04-15 | [19 empty] | Pending HOC | 2019-07-20 | 2019-12-12 | W2-Dec |  | Non-Private | Gov | MOA | NA | 0 | 0 | GF | IBP Not Issued | Below BM | Ali Asiri | تم زيارة الموقع من قبل لجنة الزراعة وتم تحويل المعاملة للتقدير من المالية ، تحتاج اسبوعين
ZJZ075 | Macro | Aspiration | Southern | Jizan | 2020 Scope | أحد المسارحة | 16.6996 | 42.9414 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-08 | 2019-03-09 | Approved | 2019-05-02 13:34 | 2019-05-03 13:34 | IGATE | 04/05/2019 13:34:22 | SNR1010039 | REQUESTER | REQUESTER | 2019-03-12 | 2019-04-10 | 2019-04-10 | 2019-04-14 | 2019-04-24 |  | 2019-09-16 | [19 empty] | Pending HOC | 2019-07-20 | 2019-11-28 | W4-Nov |  | Non-Private | Baladiya | علي عسيري | 0506788182 | 40,000.00 | 20X20 | GF | IBP Not Issued | Above | Fahad Allam | كل المنطقة تتبع للبلدية
ZRN028 | Macro | Aspiration | Central | Riyadh District | 2020 Scope | نادي الابل/بلدية الرماح | 25.6133 | 46.8249 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-04-18 | 2019-04-19 | Approved | 2019-06-16 18:03 | 2019-06-17 18:03 | IGATE | 18/06/2019 18:02:59 | SNR1010677 | SNR_I | District Support | 2019-04-22 | 2019-06-16 | 2019-06-20 | 2019-06-24 | NA | NA | 2019-05-07 | [12 empty] | 2019-10-20 | [6 empty] | Pending HOC | 2019-09-15 | 2019-10-28 | W4-Oct |  | Non-Private | Gov | Camel Club | 0504101110 | 0 | 0 | GF | IBP Not Issued | Above | Ghamdi | بانتظار اصدار العقد من نادي الابل - حسب افادة راشد العجمي يحتاج من اسبوعين الى شهر
ZBS340 | Macro | Aspiration | Southern | Baha | 2020 Scope | بيشة | 20.1595 | 42.6255 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-08 | 2019-03-09 | Approved | 2019-07-01 10:53 | 2019-07-02 10:53 | IGATE | 03/07/2019 10:53:02 | SNR1010971 | NOBODY | ACCEPTED | 2019-03-12 | 2019-04-10 | 2019-04-10 | 2019-04-10 | 2019-07-03 | 2019-08-28 | NA | NA | NA | NA | NA | NA | 2019-08-28 | 2019-09-24 | 2019-09-12 | 2019-09-18 | 2019-09-18 | 20.1557 | 42.6277 | 2019-09-20 | 2019-09-22 | ZBSA004 |  |  | 2019-09-18 | 2019-09-19 | Pending HOC | 2019-12-15 | Done | HOC Done |  | Private | Private | محمد العتيبي | 0506757034 | 0.00 | 20x20 | GF | HO to CW Done | Below BM | Done | تم تسليم الموقع
ZHF296 | Macro | Aspiration | Eastern | Hofof | 2020 Scope | الحرس الوطني | 25.4666 | 49.5189 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-04-06 | 2019-04-07 | Approved | 2019-07-20 13:37 | 2019-07-21 13:37 | IGATE | 22/07/2019 13:36:50 | SNR1011415 | SNR_I | District Support | 2019-04-10 | 2019-07-04 | 2019-07-28 | 2019-08-05 | NA | NA | 2019-05-05 | [19 empty] | Pending HOC | 2019-11-15 | 2019-11-20 | W3-Nov |  | Non-Private | Gov | NG | NA | 0 | 0 | GF | IBP Not Issued | Above | M. Ramadan | بانتظار محضر المعاينة من الحرس الوطني وتحتاج ما يقارب 3 اسابيع -مع التاكيد بتعديل الفقرة 11
ZBS115 | Macro | Aspiration | Southern | Baha | 2020 Scope | ثنية وتبالة | 20.0243 | 42.2389 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-08 | 2019-03-09 | Approved | 2019-05-02 17:49 | 2019-05-03 17:49 | IGATE | 04/05/2019 17:49:01 | SNR1010058 | SNR_O | Technical Procurement Section Manager | 2019-03-12 | 2019-04-10 | 2019-04-10 | 2019-04-10 | NA | NA | 2019-04-16 | 2019-04-16 | 2019-04-21 | 2019-09-30 | 2019-10-10 | 2019-10-14 | NA | NA | 2019-10-12 | 2019-10-27 | 2019-10-08 | 20.0247 | 42.2389 | 2019-10-17 | 2019-10-21 | Z9C005 |  |  | 2019-10-20 | 2019-10-20 | Pending HOC | 2019-06-03 | 2019-10-17 | W2-Oct | W3-Oct | Non-Private | Baladiya | Baladiya Thenya W Tebala | NA | 40,000.00 | 15X15 | GF | HO to CW Done | Below BM | Ali Asiri | تم تسليم الموقع
ZNN665 | Macro | Aspiration | Southern | Najran | 2020 Scope | حبونا | 17.83 | 44.0364 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-15 | 2019-03-16 | Approved | 2019-05-02 13:10 | 2019-05-03 13:10 | IGATE | 04/05/2019 13:10:00 | SNR1010038 | SNR_U | District Director | 2019-03-19 | 2019-04-10 | 2019-04-10 | 2019-04-24 | NA | NA | 2019-04-28 | 2019-05-21 | 2019-08-28 | 2019-08-28 | 2019-09-04 | 2019-09-15 | NA | NA | 2019-08-28 | 2019-08-28 | 2019-07-01 | 17.830115° | 44.036053° | 2019-07-03 | 2019-07-05 | ZNN991 |  |  | 2019-09-15 | 2019-09-16 | Pending HOC | 2019-09-15 | Done | HOC Done |  | Non-Private | Baladiya | Baladiya Habona | NA | 25,000.00 | 15X15 | GF | HO to CW Done | HO Done | Done | تم تسليم الموقع
ZAB391 | Macro | Aspiration | Southern | Baha | 2020 Scope | رجال المع | 18.0735 | 42.2224 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-08 | 2019-03-09 | Approved | 2019-05-02 14:07 | 2019-05-03 14:07 | IGATE | 04/05/2019 14:06:51 | SNR1010041 | NOBODY | ACCEPTED | 2019-03-12 | 2019-04-10 | 2019-04-10 | 2019-04-10 | NA | NA | 2019-04-16 | 2019-04-17 | 2019-08-28 | 2019-09-08 | 2019-09-26 | 2019-10-01 | NA | NA | 2019-09-11 | 2019-10-01 | 2019-09-02 | 18.0737 | 42.2227 | 2019-09-04 | 2019-09-06 | ZABA965 |  |  | 2019-10-01 | 2019-10-02 | Pending HOC | 2019-06-03 | Done | HOC Done |  | Non-Private | Baladiya | Baladiya Rejal Almaa | NA | 25,000.00 | 20X20 | GF | HO to CW Done | Below BM | Ali Asiri | تم تسليم الموقع
ZSR042 | Macro | Aspiration | Southern | Najran | 2020 Scope | شرورة | 17.5017 | 47.0808 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-14 | 2019-03-15 | Approved | 2019-07-01 11:13 | 2019-07-02 11:13 | IGATE | 03/07/2019 11:12:59 | SNR1010977 | SNR_Q | GM Technical Procurement | 2019-03-18 | 2019-04-10 | 2019-04-10 | 2019-04-14 | NA | NA | 2019-04-23 | 2019-07-17 | 2019-09-26 | 2019-09-29 | 2019-10-17 | 2019-10-17 | NA | NA | 2019-07-30 |  | 2019-10-08 | 17.5016 | 47.081 | 2019-10-10 | 2019-10-12 | ZSRA001 |  |  | 2019-10-20 | 2019-10-20 | Pending HOC | 2019-06-14 | 2019-10-23 | W3-Oct | W3-Oct | Non-Private | Baladiya | Baladiya Sharorah | NA | 40,000.00 | 15*15 | GF | FBP Not Issued | Below/… | Nawaf | تم تسليم الموقع بدون رخصة كما تم الاتفاق مع توال
ZSR045 | Macro | Aspiration | Southern | Najran | 2020 Scope | شرورة | 17.4894 | 47.0766 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-14 | 2019-03-15 | Approved | 2019-07-01 11:18 | 2019-07-02 11:18 | IGATE | 03/07/2019 11:18:09 | SNR1010978 | SNR_V | Technical Procurement Section Manager | 2019-03-18 | 2019-04-10 | 2019-04-10 | 2019-04-10 | 2019-07-03 | 2019-08-28 | 2019-04-23 | 2019-07-17 | 2019-09-26 | 2019-09-29 | 2019-10-14 | 2019-10-17 | NA | NA | 2019-07-30 |  | 2019-08-27 | 17.4909 | 47.074 | 2019-08-29 | 2019-08-31 | 798-00-000 |  |  | 2019-10-17 | 2019-10-17 | Pending HOC | 2019-08-15 | 2019-10-23 | W3-Oct | W2-Oct | Non-Private | Baladiya | Baladiya Sharorah | NA | 0.00 | 20X15 | GF | FBP Not Issued | Below/… | Nawaf | تم تسليم الموقع بدون رخصة كما تم الاتفاق مع توال
ZBH587 | Macro | Aspiration | Southern | Baha | 2020 Scope | مركز شمرخ | 20.4343 | 41.2711 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-04-18 | 2019-04-19 | Approved | 2019-07-09 10:40 | 2019-07-10 10:40 | IGATE | 11/07/2019 10:39:40 | SNR1011247 | SNR_I | District Support | 2019-04-22 | 2019-07-04 | 2019-07-04 | 2019-07-04 | NA | NA | 2019-05-23 | [19 empty] | Pending HOC | 2019-12-15 | 2019-12-12 | W2-Dec |  | Non-Private | Gov | Military Center Shamrakh | NA | 0 | 0 | GF | IBP Not Issued | Above | Ali Asiri | شمرخ - انتظار العقد منهم
ZJZ068 | Macro | Aspiration | Southern | Jizan | 2020 Scope | جازان | 16.8139 | 42.9084 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-04-18 | 2019-04-19 | Approved | 2019-05-10 16:33 | 2019-05-11 16:33 | IGATE | 12/05/2019 16:32:54 | SNR1010222 | NOBODY | ACCEPTED | 2019-04-22 | 2019-04-23 | 2019-05-19 | 2019-05-23 | NA | NA | 2019-04-14 | 2019-06-13 | 2019-04-23 | 2019-05-28 | 2019-06-20 | 2019-06-30 | NA | NA | 2019-07-03 | 2019-07-03 | 2019-07-01 | 16.8144 | 42.9068 | 2019-07-03 | 2019-07-05 | 718-00-000 | 60 |  | 2019-07-03 | 2019-07-07 | FDED Not Approved | 2019-06-11 | Done | HOC Done |  | Non-Private | Gov | Armed Forces in Jazan Region | NA | 30,000.00 | 20X20 | GF | HO to CW Done | HO Done | Done | تم تسليم الموقع
ZJZ170 | Macro | Aspiration | Southern | Jizan | 2020 Scope | الهيئة الملكية بالجبيل وينبع | 17.3128 | 42.3657 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-06-30 | 2019-07-01 | Approved | 2019-07-16 19:29 | 2019-07-17 19:29 | IGATE | 18/07/2019 19:28:32 | SNR1011393 | SNR_I | District Support | 2019-07-04 | 2019-07-04 | 2019-07-04 | 2019-07-04 | NA | NA | 2019-06-19 | [19 empty] | Pending HOC | 2019-12-21 | 2019-12-05 | W1-Dec |  | Non-Private | Gov | RC Jazan | NA | 0 | 0 | GF | IBP Not Issued | Below BM | Fahad Allam | RC- Jazan(Long process), arrangging meeting
ZJZ221 | Macro | Aspiration | Southern | Jizan | 2020 Scope | الهيئة الملكية بالجبيل وينبع | 17.2899 | 42.386 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-06-30 | 2019-07-01 | Approved | 2019-07-08 17:47 | 2019-07-09 17:47 | IGATE | 10/07/2019 17:47:00 | SNR1011229 | SNR_I | District Support | 2019-07-04 | 2019-07-04 | 2019-07-04 | 2019-07-04 | NA | NA | 2019-06-19 | [19 empty] | Pending HOC | 2019-12-21 | 2019-12-05 | W1-Dec |  | Non-Private | Gov | RC Jazan | NA | 0 | 0 | GF | IBP Not Issued | Below BM | Fahad Allam | RC- Jazan(Long process), arrangging meeting
ZJZ356 | Macro | Aspiration | Southern | Jizan | 2020 Scope | الهيئة الملكية بالجبيل وينبع | 17.2874 | 42.3435 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-06-30 | 2019-07-01 | Approved | 2019-07-08 17:44 | 2019-07-09 17:44 | IGATE | 10/07/2019 17:44:14 | SNR1011228 | SNR_I | District Support | 2019-07-04 | 2019-07-04 | 2019-07-04 | 2019-07-04 | NA | NA | 2019-06-19 | [19 empty] | Pending HOC | 2019-12-21 | 2019-12-05 | W1-Dec |  | Non-Private | Gov | RC Jazan | NA | 0 | 0 | GF | IBP Not Issued | Below BM | Fahad Allam | RC- Jazan(Long process), arrangging meeting
ZJZ530 | Macro | Aspiration | Southern | Jizan | 2020 Scope | الهيئة الملكية بالجبيل وينبع | 17.2797 | 42.356 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-06-30 | 2019-07-01 | Approved | 2019-07-08 17:41 | 2019-07-09 17:41 | IGATE | 10/07/2019 17:41:12 | SNR1011227 | SNR_I | District Support | 2019-07-04 | 2019-07-04 | 2019-07-04 | 2019-07-04 | NA | NA | 2019-06-19 | [19 empty] | Pending HOC | 2019-12-21 | 2019-12-05 | W1-Dec |  | Non-Private | Gov | RC Jazan | NA | 0 | 0 | GF | IBP Not Issued | Below BM | Fahad Allam | RC- Jazan(Long process), arrangging meeting
ZJZ531 | Macro | Aspiration | Southern | Jizan | 2020 Scope | الهيئة الملكية بالجبيل وينبع | 17.3461 | 42.3835 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-06-30 | 2019-07-01 | Approved | 2019-08-21 | 2019-08-21 | IGATE | #N/A | #N/A | #N/A | #N/A | 2019-07-04 | 2019-07-04 |  |  | NA | NA | 2019-06-19 | [19 empty] | Pending HOC | 2019-12-21 | 2019-12-05 | W1-Dec |  | Non-Private | Gov | RC Jazan | NA | NA | NA | GF | #N/A | Below BM | Fahad Allam | RC- Jazan(Long process), arrangging meeting
ZRR027 | Macro | Aspiration | Northern | Arrar | 2020 Scope | اسكان قوى الامن بعرعر | 30.9622 | 41.0265 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-04-18 | 2019-04-19 | Approved | 2019-06-24 18:43 | 2019-06-25 18:43 | IGATE | 26/06/2019 18:43:20 | SNR1010858 | NOBODY | ACCEPTED | 2019-04-22 | 2019-06-24 | 2019-06-28 | 2019-07-02 | NA | NA | 2019-04-29 | 2019-07-09 | 2019-07-30 | 2019-09-01 | 2019-09-04 | 2019-09-16 | NA | NA | 2019-08-29 | 2019-08-29 | 2019-08-28 | 30.960693° | 41.026979° | 2019-08-29 | 2019-09-15 | ZRRA003 |  |  | 2019-09-16 | 2019-09-17 | FDED Not Approved | 2019-12-24 | Done | HOC Done |  | Non-Private | Gov | Housing security forces in Arar | NA | 30,000.00 | 10X10 | GF | HO to CW Done | HO Done | Sultan | تم تسليم الموقع
ZNN763 | Macro | Aspiration | Southern | Najran | 2020 Scope | وزارة الاسكان في منطقة نجران | 17.638 | 44.4971 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-03-14 | 2019-03-15 | Approved | 2019-06-17 16:33 | 2019-06-18 16:33 | IGATE | 19/06/2019 16:32:31 | SNR1010700 | SNR_O | Technical Procurement Section Manager | 2019-03-18 | 2019-04-10 | 2019-04-10 | 2019-04-10 | NA | NA | 2019-06-19 | 2019-10-10 | 2019-10-10 | 2019-10-10 | 2019-10-17 |  | NA | NA | 2019-10-15 | 2019-11-17 | 2019-10-16 | 17.638 | 44.4971 | 2019-10-16 | 2019-10-22 | ZNNA985 |  |  | 2019-10-21 | 2019-10-21 | Pending HOC | 2019-08-15 | 2019-10-28 | W4-Oct | W3-Oct | Non-Private | Baladiya | Najran Amanah | NA | 0 | 0 | GF | HO to CW Done | Below BM | Nawaf | تم تسليم الموقع بدون رخصة كما تم الاتفاق مع توال
ZTB002 | Macro | Aspiration | Northern | Tabuk | 2020 Scope | مدينة الملك عبدالعزيز العسكرية | 28.3734 | 36.5702 | Huawei | Removed from Scope | New Location | NA | NA | Macro | Long process |  | Approved | 2019-03-17 | 2019-03-18 | Approved | 2019-05-20 11:24 | 2019-05-21 11:24 | IGATE | #N/A | #N/A | #N/A | #N/A | 2019-03-21 | 2019-04-10 | 2019-04-10 | 2019-05-13 | NA | NA | 2019-04-17 | [20 empty] | 2019-11-15 | Out | Out |  | Non-Private | Gov | King Abdulaziz Military City for Operation and Maintenance | NA | 0 | 20*20 | GF | #N/A | Above | Hatem | Removed from Scope
ZBR082 | Macro | Aspiration | Central | Qassim | 2020 Scope | القصيم | 26.3941 | 43.9046 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-04-06 | 2019-04-07 | Approved | 2019-08-18 |  | IGATE | 29/10/2019 17:21:41 | SNR1012257 | REQUESTER | REQUESTER | 2019-04-10 |  |  |  | NA | NA | 2019-04-15 | [19 empty] | Pending HOC | 2019-09-15 | 2019-11-14 | W2-Nov |  | Non-Private | Baladiya | Amanh AlQasim | NA | NA | NA | GF | ISR Not Sub to RF | Above | A Sughair | تم اصدار العقد من الامانة بسعر مرتفع (60الف )
ZBR117 | Macro | Aspiration | Central | Qassim | 2020 Scope | القصيم | 26.373 | 43.8605 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-04-06 | 2019-04-07 | Approved | 2019-05-23 13:20 | 2019-05-24 13:20 | IGATE | 05/11/2019 15:26:35 | SNR1012315 | SNR_I | District Support | 2019-04-10 | 2019-04-10 | 2019-04-10 | 2019-04-14 |  |  | NA | NA | NA | NA | NA | NA | [14 empty] | Pending HOC | 2019-09-15 | 2019-11-14 | W2-Nov |  | Private | Private | Amanh AlQasim | NA | 0 | 0 | GF | Priv. Contract Not Issued From TAWAL | Above | A Sughair | تم توقيع العقد المبدئي وبانتظار رفعها بالاي قيت لاصدار العقد
ZBR120 | Macro | Aspiration | Central | Qassim | 2020 Scope | القصيم | 26.3886 | 43.986 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-12 | 2019-03-13 | Approved | 2019-06-16 17:27 | 2019-06-17 17:27 | IGATE | 02/10/2019 10:19:00 | SNR1011990 | SNR_F | District Director | 2019-03-16 | 2019-04-10 | 2019-04-14 | 2019-04-18 | NA | NA | 2019-04-15 | 2019-07-14 | 2019-07-30 | 2019-09-17 | [16 empty] | Pending HOC | 2019-09-15 | 2019-11-05 | W1-Nov |  | Non-Private | Baladiya | Amanh AlQasim | 0555147965 | 65,000.00 | 289m | GF | Contract Not Signed by TAWAL | Above | A Sughair | بانتظار توقيع العقد من المشتريات
ZBR134 | Macro | Aspiration | Central | Qassim | 2020 Scope | بريدة | 26.4126 | 43.9243 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-14 | 2019-03-15 | Approved | 2019-05-11 15:00 | 2019-05-12 15:00 | IGATE | 13/05/2019 14:59:49 | SNR1010230 | NOBODY | ACCEPTED | 2019-03-18 | 2019-04-10 | 2019-04-10 | 2019-04-28 | 2019-05-14 | 2019-07-07 | NA | NA | NA | NA | NA | NA | 2019-07-07 | 2019-07-18 | 2019-07-18 | 2019-10-16 | 2019-07-09 | 26.412720° | 43.924634° | 2019-07-17 | 2019-09-02 | 615-41-000 |  |  | 2019-10-16 | 2019-10-20 | Pending HOC | 2019-09-15 | 2019-10-21 | W3-Oct | W2-Oct | Private | Private | خالد عجلان العجلان | 0543835338 | 40,000.00 | 20*20 | RT | HO to CW Done | Below BM | A Sughair | تم تسليم الموقع
ZBR146 | Macro | Aspiration | Central | Qassim | 2020 Scope | القصيم | 26.302 | 44.0378 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-16 | 2019-03-17 | Approved | 2019-05-23 13:30 | 2019-05-24 13:30 | IGATE | 25/05/2019 13:30:08 | SNR1010374 | SNR_O | Technical Procurement Section Manager | 2019-03-20 | 2019-04-10 | 2019-04-10 | 2019-04-14 |  |  | NA | NA | NA | NA | NA | NA | 2019-10-15 | 2019-10-15 | 2019-10-15 |  | 2019-10-15 | 26.3023 | 44.0391 | 2019-10-16 | 2019-10-17 | 601-11-000 |  |  | 2019-10-20 | 2019-10-20 | Pending HOC | 2019-09-15 | 2019-11-05 | W1-Nov | W3-Oct | Private | Private | Ahmed Bin Abdullah Al Kafari | 0555151224 | 25,000.00 | 225m2 | RT | FBP Not Issued | Above | A Sughair | تم تسليم الموقع بدون رخصة كما تم الاتفاق مع توال
ZBR149 | Macro | Aspiration | Central | Qassim | 2020 Scope | معهد طيران القوات البرية بالقصيم | 26.3095 | 43.7578 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-04-06 | 2019-04-07 | Approved | 2019-05-25 15:26 | 2019-05-26 15:26 | IGATE | 27/05/2019 15:25:59 | SNR1010421 | NOBODY | ACCEPTED | 2019-04-10 | 2019-05-12 | 2019-06-17 | 2019-06-17 | NA | NA | 2019-04-30 | 2019-06-18 | 2019-06-18 | 2019-06-18 | 2019-06-20 | 2019-06-30 | NA | NA | 2019-06-20 | 2019-06-30 | 2019-06-17 | 26.309973° | 43.758174° | 2019-06-19 | 2019-07-03 | ZBRA052 |  |  | 2019-06-30 | 2019-07-01 | No Dependency | 2019-11-15 | Done | HOC Done |  | Non-Private | Gov | Ground Military Forces | NA | 36,000.00 | 15x15 | GF | HO to CW Done | HO Done | A Sughair | تم تسليم الموقع
ZBR178 | Macro | Aspiration | Central | Qassim | 2020 Scope | الحرس الوطني | 26.3272 | 43.7781 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-05-15 | 2019-05-16 | Approved | 2019-07-05 18:20 | 2019-07-06 18:20 | IGATE | 07/07/2019 18:19:55 | SNR1011111 | SNR_I | District Support | 2019-05-19 | 2019-07-04 | 2019-07-04 | 2019-07-04 | NA | NA | 2019-05-05 | [19 empty] | Pending HOC | 2019-12-14 | 2019-11-14 | W2-Nov |  | Non-Private | Gov | NG | NA | 0 | 0 | GF | IBP Not Issued | Above | A Sughair | بانتظار محضر المعاينة من الحرس الوطني وتحتاج ما يقارب 3 اسابيع -مع التاكيد بتعديل الفقرة 11
ZBR883 | Macro | Aspiration | Central | Qassim | 2020 Scope | ملك خاص | 26.365 | 44.0211 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-03-16 | 2019-03-17 | Approved | 2019-05-18 15:31 | 2019-05-19 15:31 | IGATE | 20/05/2019 15:30:31 | SNR1010303 | NOBODY | ACCEPTED | 2019-03-20 | 2019-04-10 | 2019-04-10 | 2019-04-28 | 2019-05-14 | 2019-06-20 | NA | NA | NA | NA | NA | NA | 2019-06-20 | 2019-06-25 | 2019-06-25 |  | 2019-06-25 | 26.364950° | 44.021920° | 2019-06-26 | NA | NA |  |  |  |  | Pending HOC | 2019-10-15 | 2019-10-31 | W4-Oct |  | Private | Private | عبدالرحمن فوزان المطرودي/علي سلمان | 0555146966 | 40,000.00 | 20*20 | GF | FBP Not Issued | Below BM | A Sughair | بانتظار اصدار الرخصة - نحتاج صك الالكتروني من المالك
ZHA295 | Macro | Aspiration | Central | Hail | 2020 Scope | حائل | 27.5209 | 41.7185 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-17 | 2019-03-18 | Approved | 2019-06-09 18:58 | 2019-06-10 18:58 | IGATE | 02/10/2019 10:10:03 | SNR1011988 | SNR_I | District Support | 2019-03-21 | 2019-04-10 | 2019-04-10 | 2019-04-14 | 2019-04-24 |  | 2019-09-10 | [19 empty] | Pending HOC | 2019-07-20 | 2019-11-25 | W4-Nov |  | Non-Private | Baladiya | Hail | 0555150377 | 25,000.00 | 20x20 | GF | IBP Not Issued | Above | Abdulaziz | بانتظار توقيع العقد من المشتريات - افادة دعم المنطقة سيتم تخفيض سعر العقد
ZTB430 | Macro | Aspiration | Northern | Tabuk | 2020 Scope | وزارة الاسكان | 28.4843 | 36.4648 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-04-06 | 2019-04-07 | Approved | 2019-06-10 12:21 | 2019-06-11 12:21 | IGATE | 12/06/2019 12:21:21 | SNR1010488 | SNR_I | District Support | 2019-04-10 | 2019-06-17 | 2019-06-17 | 2019-06-21 | NA | NA | 2019-04-16 | [19 empty] | Pending HOC | 2019-10-15 | 2019-12-15 | W3-Dec |  | Non-Private | Gov | MOH in Tabuk | NA | 0 | 0 | GF | IBP Not Issued | Above | Hatem | بانتظار رد من وزارة الاسكان
ZHA320 | Macro | Aspiration | Central | Hail | 2020 Scope | حائل | 27.5832 | 41.7152 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-17 | 2019-03-18 | Approved | 2019-07-28 16:26 | 2019-07-29 16:26 | IGATE | 30/07/2019 16:26:29 | SNR1011511 | SNR_I | District Support | 2019-03-21 | 2019-04-10 | 2019-04-10 | 2019-04-14 | 2019-04-23 |  | 2019-08-20 | [19 empty] | Pending HOC | 2019-08-15 | 2019-11-25 | W4-Nov |  | Non-Private | Baladiya | Hail | NA | 0 | 0 | GF / RT | IBP Not Issued | Above | Abdulaziz | بانتظار توقيع العقد من المشتريات - افادة دعم المنطقة سيتم تخفيض سعر العقد
ZHA324 | Macro | Aspiration | Central | Hail | 2020 Scope | حائل | 27.4615 | 41.6404 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-04-06 | 2019-04-07 | Approved | 2019-07-05 18:56 | 2019-07-06 18:56 | IGATE | 07/07/2019 18:55:43 | SNR1011116 | SNR_Q | GM Technical Procurement | 2019-04-10 | 2019-06-20 | 2019-06-20 | 2019-06-20 | NA | NA | 2019-07-11 | 2019-09-02 | 2019-09-02 | 2019-09-05 | 2019-10-17 |  | NA | NA |  |  | 2019-09-12 | 27.4622 | 41.6416 | 2019-09-15 | 2019-09-26 | ZHAA021 |  |  | 2019-10-20 | 2019-10-20 | Pending HOC | 2019-12-15 | 2019-10-28 | W4-Oct | W3-Oct | Non-Private | Baladiya | Amanh Hail | NA | 30,000.00 | 4*14 | GF | FBP Not Applied | Above | Abdulaziz | تم تسليم الموقع بدون رخصة كما تم الاتفاق مع توال
ZHA330 | Macro | Aspiration | Central | Hail | 2020 Scope | وزارة الاسكان بمنطفة حائل | 27.507 | 41.7666 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-03-17 | 2019-03-18 | Approved | 2019-07-23 14:41 | 2019-07-24 14:41 | IGATE | 25/07/2019 14:41:03 | SNR1011463 | SNR_I | District Support | 2019-03-21 | 2019-07-28 | 2019-07-28 | 2019-08-05 | NA | NA | 2019-04-14 | [19 empty] | Pending HOC | 2019-10-15 | 2019-11-28 | W4-Nov |  | Non-Private | Gov | MOH in Hail | NA | 0 | 0 | GF | IBP Not Issued | Above | Abdulaziz | بانتظار رد من وزارة الاسكان
ZNN676 | Macro/Replacement | Aspiration | Southern | Najran | 2019 Scope-Replacement | حرس الحدود | 18.8947 | 51.1707 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-06-13 | 2019-06-14 | Approved | 2019-06-11 11:42 | 2019-06-12 11:42 | IGATE | 13/06/2019 11:42:12 | SNR1010514 | SNR_I | District Support | 2019-06-17 | 2019-06-18 | 2019-06-18 | 2019-06-18 | NA | NA | 2019-06-18 | [12 empty] | 2019-10-20 | [6 empty] | Pending HOC | 2020-01-04 | 2019-10-28 | W4-Oct |  | Non-Private | Gov | NG | NA | 0 | 0 | GF | IBP Not Issued | Above | Nawaf | خرخير - انتظار العقد لدى المالية | Yousof to visit حرس الحدود بالرياض
ZHA475 | Macro | Aspiration | Central | Hail | 2020 Scope | حائل | 27.5306 | 41.7672 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-17 | 2019-03-18 | Approved | 2019-07-09 15:48 | 2019-07-10 15:48 | IGATE | 11/07/2019 15:47:31 | SNR1011274 | SNR_O | Technical Procurement Section Manager | 2019-03-21 | 2019-04-10 | 2019-04-10 | 2019-04-10 | NA | NA | 2019-04-30 | 2019-09-04 | 2019-09-10 | 2019-09-26 | 2019-10-17 |  | NA | NA |  |  | 2019-09-11 | 27.5342 | 41.765 | 2019-09-19 | 2019-10-14 | ZHAA018 |  |  | 2019-10-20 | 2019-10-20 | Pending HOC | 2019-09-15 | 2019-10-28 | W4-Oct | W3-Oct | Non-Private | Baladiya | Amanh Hail | NA | 0 | 300M | GF | FBP Not Applied | Above | Abdulaziz | تم تسليم الموقع بدون رخصة كما تم الاتفاق مع توال
ZHA489 | Macro | Aspiration | Central | Hail | 2020 Scope | حائل | 27.4079 | 41.7178 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-17 | 2019-03-18 | Approved | 2019-05-23 14:30 | 2019-05-24 14:30 | IGATE | 25/05/2019 14:30:26 | SNR1010379 | SNR_Q | GM Technical Procurement | 2019-03-21 | 2019-04-10 | 2019-04-10 | 2019-04-14 | NA | NA | 2019-04-30 | 2019-08-25 | 2019-09-02 | 2019-09-05 | 2019-10-17 |  | NA | NA |  |  | 2019-09-11 | 27.4077 | 41.7157 | 2019-09-15 | 2019-10-03 | ZHAA021 |  |  | 2019-10-20 | 2019-10-20 | Pending HOC | 2019-09-15 | 2019-10-28 | W4-Oct | W3-Oct | Non-Private | Baladiya | Amanh Hail | NA | 45,000.00 | 15*20 | GF | FBP Not Applied | Above | Abdulaziz | تم تسليم الموقع بدون رخصة كما تم الاتفاق مع توال
ZHA893 | Macro | Aspiration | Central | Hail | 2020 Scope | ملك خاص | 27.4977 | 41.6994 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-17 | 2019-03-18 | Approved | 2019-05-20 10:46 | 2019-05-21 10:46 | IGATE | 02/10/2019 10:30:51 | SNR1011992 | SNR_O | Technical Procurement Section Manager | 2019-03-21 | 2019-04-10 | 2019-04-10 | 2019-04-10 | 2019-04-03 | 2019-05-16 | NA | NA | NA | NA | NA | NA | 2019-10-20 | 2019-10-06 | 2019-10-20 | 2019-10-29 | 2019-10-01 | 27.4976 | 41.6993 | 2019-10-06 | NA | NA |  |  | 2019-10-20 | 2019-10-20 | Pending HOC | 2019-07-20 | 2019-10-21 | W3-Oct | W3-Oct | Private | Private | نايف الجربوع | 0552277405 | 50,000.00 | 0 | RT | HO to CW Done | Below BM | Abdulaziz | تم تسليم الموقع
ZMC554 | Macro | Aspiration | Southern | Baha | 2020 Scope | تحفيظ القرأن في محافظة المظيلف | 19.5439 | 41.0385 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-03-10 | 2019-03-11 | Approved | 2019-05-25 09:18 | 2019-05-26 09:18 | IGATE | 27/05/2019 09:17:56 | SNR1010410 | SNR_B | RF Team Leader | 2019-03-14 | 2019-04-10 | 2019-04-10 | 2019-04-10 | NA | NA | 2019-06-18 | [19 empty] | Pending HOC | 2019-11-15 | 2019-11-14 | W2-Nov |  | Private | Private | Private | 0504303088 | 50,000.00 | 20X20 | GF | IBP Not Issued | Above | Ali Asiri | تم الاتفاق مع ال RF ، وتم رفعه على الاي جيت | try with RF for Candidate E Private with 60 M HT
ZHA926 | Macro | Aspiration | Central | Hail | 2020 Scope | حائل | 27.4682 | 41.6812 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-17 | 2019-03-18 | Approved | 2019-07-08 18:27 | 2019-07-09 18:27 | IGATE | 10/07/2019 18:26:51 | SNR1011233 | SNR_Q | GM Technical Procurement | 2019-03-21 | 2019-04-10 | 2019-04-10 | 2019-05-23 | NA | NA | 2019-06-19 | 2019-09-04 | 2019-09-10 | 2019-09-11 | 2019-10-17 |  | NA | NA |  |  | 2019-09-11 | 27.4657 | 41.6806 | 2019-09-19 | 2019-09-26 | ZHAA002 |  |  | 2019-10-20 | 2019-10-20 | Pending HOC | 2019-08-15 | 2019-10-28 | W4-Oct | W3-Oct | Non-Private | Baladiya | Amanh Hail | NA | 50,000.00 | 300M | GF | FBP Not Applied | Above | Abdulaziz | تم تسليم الموقع بدون رخصة كما تم الاتفاق مع توال
ZHF784 | Macro | Aspiration | Eastern | Hofof | 2019 Scope | أمانة الإحساء | 25.3501 | 49.541 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-07-19 | 2019-07-20 | Approved | 2019-07-08 18:17 | 2019-07-09 18:17 | IGATE | 10/07/2019 18:17:14 | SNR1011230 | SNR_I | District Support | 2019-07-23 | 2019-07-23 | 2019-07-23 | 2019-07-23 | NA | NA | 2019-07-21 | [19 empty] | Pending HOC |  | 2019-12-15 | W3-Dec |  | Non-Private | Baladiya | AlAhsa Amana | 13 5825000 | 0 | 0 | GF | IBP Not Issued | Above | Salah | تحت التخطيط بالبلدية بانتظار موافقتهم - يحتاج ما يقارب 2 اسبوع لاصدار العقد
ZHF202 | Macro | Aspiration | Eastern | Hofof | 2019 Scope | حرس وطني | 25.4335 | 49.5111 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-06-30 | 2019-07-01 | Approved | 2019-07-20 13:43 | 2019-07-21 13:43 | IGATE | 22/07/2019 13:43:16 | SNR1011416 | SNR_I | District Support | 2019-07-04 | 2019-07-04 | 2019-07-28 | 2019-08-05 | NA | NA | 2019-08-05 | [19 empty] | Pending HOC |  | 2019-11-20 | W3-Nov |  | Non-Private | Gov | NG | NA | 0 | 0 | GF | IBP Not Issued | Above | Naser | بانتظار محضر المعاينة من الحرس الوطني وتحتاج ما يقارب 3 اسابيع -مع التاكيد بتعديل الفقرة 11
ZHF203 | Macro | Aspiration | Eastern | Hofof | 2019 Scope | حرس وطني | 25.463 | 49.5071 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-06-30 | 2019-07-01 | Approved | 2019-07-05 18:39 | 2019-07-06 18:39 | IGATE | 07/07/2019 18:39:12 | SNR1011115 | SNR_I | District Support | 2019-07-04 | 2019-07-04 | 2019-07-04 | 2019-07-04 | NA | NA | 2019-07-11 | [19 empty] | Pending HOC |  | 2019-11-20 | W3-Nov |  | Non-Private | Gov | NG | NA | 0 | 0 | GF | IBP Not Issued | Above | Naser | بانتظار محضر المعاينة من الحرس الوطني وتحتاج ما يقارب 3 اسابيع -مع التاكيد بتعديل الفقرة 11
ZTB128 | Macro | Aspiration | Northern | Tabuk | 2020 Scope | المدينة العسكرية بتبوك | 28.3443 | 36.58 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-04-06 | 2019-04-07 | Approved | 2019-05-20 16:54 | 2019-05-21 16:54 | IGATE | 22/05/2019 16:53:52 | SNR1010366 | SNR_U | District Director | 2019-04-10 | 2019-05-14 | 2019-05-14 | 2019-05-13 | NA | NA | 2019-04-17 | 2019-05-29 | 2019-06-16 | 2019-06-18 | 2019-06-20 | 2019-06-30 | NA | NA | 2019-07-01 | 2019-07-03 | 2019-07-15 | 28.345 | 36.5816 | 2019-06-27 | 2019-07-11 | ZTBA013 | 35 |  | 2019-07-03 | 2019-07-08 | Pending RFI | 2019-11-15 | Done | HOC Done |  | Non-Private | Gov | Military city of Tabuk | NA | 22,500.00 | 15*15 | GF | HO to CW Done | HO Done | Hatem | تم تسليم الموقع
ZTB132 | Macro | Aspiration | Northern | Tabuk | 2020 Scope | تبوك | 28.36 | 36.4763 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-04-06 | 2019-04-07 | Approved | 2019-05-23 17:01 | 2019-05-24 17:01 | IGATE | 25/05/2019 17:00:41 | SNR1010394 | SNR_I | District Support | 2019-04-10 | 2019-04-23 | 2019-05-25 | 2019-05-29 | NA | NA | 2019-06-19 | [19 empty] | Pending HOC | 2019-10-15 | 2019-12-19 | W3-Dec |  | Non-Private | Baladiya | Amanah Tabuk | NA | 0 | 0 | GF | IBP Not Issued | Above | Hatem | تم الاجتماع مع الامانة وتم الاتفاق لاصدار العقود خلال اسبوعين
ZTB135 | Macro | Aspiration | Northern | Tabuk | 2020 Scope | قاعدة الملك فيصل الجوية | 28.3946 | 36.6153 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-04-06 | 2019-04-07 | Approved | 2019-05-23 16:11 | 2019-05-24 16:11 | IGATE | 25/05/2019 16:10:56 | SNR1010389 | NOBODY | ACCEPTED | 2019-04-10 | 2019-05-14 | 2019-05-19 | 2019-05-20 | NA | NA | 2019-04-17 | 2019-05-13 | 2019-05-27 | 2019-05-27 | 2019-07-03 | 2019-07-13 | NA | NA | 2019-06-20 | 2019-07-10 | 2019-07-01 | 28.39683° | 36.615 | 2019-06-25 | 2019-07-11 | ZTBA004 |  |  | 2019-07-10 | 2019-07-11 | FDED Not Approved | 2019-11-15 | Done | HOC Done |  | Non-Private | Gov | King Faisal Air force Base | NA | 25,000.00 | 15x15 | GF | HO to CW Done | HO Done | Hatem | تم تسليم الموقع
ZTB036 | Macro | Aspiration | Northern | Tabuk | 2020 Scope | جامعة تبوك | 28.3889 | 36.4883 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-03-16 | 2019-03-17 | Approved | 2019-05-02 16:03 | 2019-05-03 16:03 | IGATE | 04/05/2019 16:02:37 | SNR1010051 | SNR_O | Technical Procurement Section Manager | 2019-03-20 | 2019-04-10 | 2019-04-10 | 2019-04-28 | NA | NA | 2019-04-16 | 2019-10-01 | 2019-10-01 | 2019-10-01 | 2019-10-30 | 2019-11-10 | NA | NA | 2019-10-30 | 2019-11-10 |  |  |  | 2019-10-20 |  |  |  |  | 2019-10-30 | 2019-11-03 | Pending HOC | 2019-10-15 | 2019-10-21 | W3-Oct |  | Non-Private | Gov | Tabuk university | NA | 0 | 15*15 | GF | HO to CW Done | Above | Hatem | تم تسليم الموقع بدون رخصة كما تم الاتفاق مع توال
ZTB390 | Macro | Aspiration | Northern | Tabuk | 2020 Scope | ملك خاص | 28.4133 | 36.4476 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-17 | 2019-03-18 | Approved | 2019-05-02 17:09 | 2019-05-03 17:09 | IGATE | 04/05/2019 17:09:13 | SNR1010057 | SNR_Q | GM Technical Procurement | 2019-03-21 | 2019-04-10 | 2019-04-10 | 2019-04-14 | 2019-07-11 | 2019-08-05 | NA | NA | NA | NA | NA | NA | 2019-07-28 | 2019-08-05 | 2019-08-05 | 2019-09-15 | 2019-08-21 | 28.412933° | 36.448997° | 2019-08-22 | 2019-08-26 | ZTBA012 |  |  | 2019-09-15 | 2019-09-15 | FDED Not Approved | 2019-09-15 | Done | HOC Done |  | Private | Private | منصور عبدالله غضيان | 0555361165 | 30,000.00 | 20*20 | GF | HO to CW Done | HO Done | Hatem | تم تسليم الموقع
ZTB397 | Macro | Aspiration | Northern | Tabuk | 2020 Scope | ملك خاص | 28.4705 | 36.5592 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-17 | 2019-03-18 | Approved | 2019-05-20 11:41 | 2019-05-21 11:41 | IGATE | 22/05/2019 11:41:28 | SNR1010358 | NOBODY | ACCEPTED | 2019-03-21 | 2019-04-10 | 2019-05-19 | 2019-06-17 | 2019-06-17 | 2019-06-20 | NA | NA | NA | NA | NA | NA | 2019-06-20 | 2019-06-25 | 2019-07-01 | 2019-07-17 | 2019-06-25 | 28.4714 | 36.5609 | 2019-06-30 | 2019-07-11 | ZTBA005 |  |  | 2019-07-18 | 2019-07-18 | No Dependency | 2019-08-15 | Done | HOC Done |  | Private | Private | فهد الحربي | NA | 0.00 | 15*15 | GF | HO to CW Done | HO Done | Hatem | تم تسليم الموقع
ZTB399 | Macro | Aspiration | Northern | Tabuk | 2020 Scope | تبوك | 28.4357 | 36.5323 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-17 | 2019-03-18 | Approved | 2019-05-02 16:20 | 2019-05-03 16:20 | IGATE | 04/05/2019 16:20:18 | SNR1010053 | SNR_I | District Support | 2019-03-21 | 2019-04-10 | 2019-04-10 | 2019-04-14 | NA | NA | 2019-04-15 | [19 empty] | Pending HOC | 2019-10-15 | 2019-12-19 | W3-Dec |  | Non-Private | Baladiya | Amanah Tabuk | NA | 0 | 0 | GF | IBP Not Issued | Above | Hatem | تم الاجتماع مع الامانة وتم الاتفاق لاصدار العقود خلال اسبوعين
ZTB400 | Macro | Aspiration | Northern | Tabuk | 2020 Scope | تبوك | 28.464 | 36.566 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-17 | 2019-03-18 | Approved | 2019-05-20 11:54 | 2019-05-21 11:54 | IGATE | 22/05/2019 11:54:16 | SNR1010359 | SNR_I | District Support | 2019-03-21 | 2019-04-10 | 2019-05-19 | 2019-05-23 | NA | NA | 2019-04-15 | [19 empty] | Pending HOC | 2019-10-15 | 2019-12-19 | W3-Dec |  | Non-Private | Baladiya | Amanah Tabuk | NA | 0 | 0 | GF | IBP Not Issued | Above | Hatem | تم الاجتماع مع الامانة وتم الاتفاق لاصدار العقود خلال اسبوعين
ZTB111 | Macro | Aspiration | Northern | Tabuk | 2020 Scope | جامعة تبوك | 28.3857 | 36.4636 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-03-16 | 2019-03-17 | Approved | 2019-05-23 16:06 | 2019-05-24 16:06 | IGATE | 25/05/2019 16:06:21 | SNR1010388 | SNR_O | Technical Procurement Section Manager | 2019-03-20 | 2019-04-10 | 2019-05-25 | 2019-06-17 | NA | NA | 2019-04-16 | 2019-10-01 | 2019-10-01 | 2019-10-01 | 2019-10-30 | 2019-11-10 | NA | NA | 2019-10-30 | 2019-11-10 |  |  |  | 2019-10-20 |  |  |  |  | 2019-10-30 | 2019-11-03 | Pending HOC | 2019-10-15 | 2019-10-21 | W3-Oct |  | Non-Private | Gov | Tabuk university | NA | 0 | 15*15 | GF | HO to CW Done | Above | Hatem | تم تسليم الموقع بدون رخصة كما تم الاتفاق مع توال
ZTB431 | Macro | Aspiration | Northern | Tabuk | 2020 Scope | تبوك | 28.4041 | 36.5319 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-17 | 2019-03-18 | Approved | 2019-05-23 17:08 | 2019-05-24 17:08 | IGATE | 25/05/2019 17:08:26 | SNR1010395 | SNR_I | District Support | 2019-03-21 | 2019-04-10 | 2019-05-25 | 2019-05-29 | NA | NA | 2019-06-19 | [19 empty] | Pending HOC | 2019-08-15 | 2019-12-19 | W3-Dec |  | Non-Private | Baladiya | Amanah Tabuk | NA | 0 | 0 | GF | IBP Not Issued | Above | Hatem | تم الاجتماع مع الامانة وتم الاتفاق لاصدار العقود خلال اسبوعين
ZTB432 | Macro | Aspiration | Northern | Tabuk | 2020 Scope | تبوك | 28.4476 | 36.5065 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-17 | 2019-03-18 | Approved | 2019-07-20 13:10 | 2019-07-21 13:10 | IGATE | 22/07/2019 13:09:50 | SNR1011412 | SNR_B | RF Team Leader | 2019-03-21 | 2019-04-10 | 2019-04-10 | 2019-04-14 | 2019-04-25 |  | NA | NA | NA | NA | NA | NA | [14 empty] | Pending HOC | 2019-08-15 | 2019-12-10 | W2-Dec |  | Private | Private | وكيل شرعي : جرير عبد الرحمن الاسمري | 0569454122 | 0 | 0 | GF | Priv. Contract Not Issued From TAWAL | Below BM | Hatem | تم رفض الموقع المقترح من المالك وRF - وجاري تقديم ISR جديد
ZTB433 | Macro | Aspiration | Northern | Tabuk | 2020 Scope | سعادة أمين أمانة تبوك | 28.3717 | 36.5486 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-17 | 2019-03-18 | Approved | 2019-08-21 | 2019-08-21 | IGATE | 07/08/2019 17:35:27 | SNR1011614 | SNR_I | District Support | 2019-03-21 | 2019-04-10 | 2019-04-10 | 2019-09-03 | NA | NA | 2019-06-19 | [19 empty] | Pending HOC | 2019-08-15 | 2019-12-19 | W3-Dec |  | Non-Private | Baladiya | Amanah Tabuk | 0504787540 | 0 | 0 | GF | IBP Not Issued | Above | Hatem | تم الاجتماع مع الامانة وتم الاتفاق لاصدار العقود خلال اسبوعين
ZTB434 | Macro | Aspiration | Northern | Tabuk | 2020 Scope | تبوك | 28.4321 | 36.5116 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-17 | 2019-03-18 | Approved | 2019-05-11 15:22 | 2019-05-12 15:22 | IGATE | 13/05/2019 15:22:00 | SNR1010232 | NOBODY | ACCEPTED | 2019-03-21 | 2019-04-10 | 2019-04-10 | 2019-04-14 | 2019-05-20 | 2019-05-20 | NA | NA | NA | NA | NA | NA | 2019-07-11 | 2019-07-18 | 2019-07-24 | 2019-08-26 | 2019-07-18 | 28.4327 | 36.5108 | 2019-07-29 | 2019-08-05 | ZTBA012 |  |  | 2019-08-27 | 2019-08-27 | FDED Not Approved | 2019-08-15 | Done | HOC Done |  | Private | Private | خالد دعيع العنزي | 0545176200 | 30,000.00 | All RT | RT | HO to CW Done | HO Done | Hatem | تم تسليم الموقع
ZTB872 | Macro | Aspiration | Northern | Tabuk | 2020 Scope | قاعدة الملك فيصل الجوية | 28.3629 | 36.6279 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-04-06 | 2019-04-07 | Approved | 2019-05-23 17:18 | 2019-05-24 17:18 | IGATE | 25/05/2019 17:17:54 | SNR1010396 | SNR_I | District Support | 2019-04-10 | 2019-05-01 | 2019-05-25 | 2019-05-29 | NA | NA | 2019-04-17 | 2019-05-13 | [18 empty] | Pending HOC | 2019-12-22 | 2019-11-20 | W3-Nov |  | Non-Private | Gov | King Faisal Air force Base | NA | 0 | 0 | GF | Contract Not Issued | Above | Hatem | RF رفض الموقع المقدم من القاعدة الجوية
ZUZ039 | Macro | Aspiration | Central | Qassim | 2020 Scope | عنيزة | 26.0246 | 43.9654 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-16 | 2019-03-17 | Approved | 2019-05-20 14:31 | 2019-05-21 14:31 | IGATE | 22/05/2019 14:31:22 | SNR1010362 | SNR_U | District Director | 2019-03-20 | 2019-04-10 | 2019-04-10 | 2019-04-10 |  |  | NA | NA | NA | NA | NA | NA | [7 empty] | 2019-10-20 | [6 empty] | Pending HOC | 2019-09-15 | 2019-11-25 | W4-Nov |  | Private | Private | Private | NA | 30,000.00 | 20*20 | GF | Priv. Contract Not Issued From TAWAL | Below BM | A Sughair | تم رفض تسليم الموقع من البلدية - تم عمل ISR جديد بانتظار موافقة RF
ZUZ044 | Macro | Aspiration | Central | Qassim | 2020 Scope | ملك خاص | 26.0889 | 44.0194 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-16 | 2019-03-17 | Approved | 2019-05-02 17:01 | 2019-05-03 17:01 | IGATE | 04/05/2019 17:00:30 | SNR1010056 | NOBODY | ACCEPTED | 2019-03-20 | 2019-04-10 | 2019-04-28 | 2019-04-28 | 2019-05-13 | 2019-06-20 | NA | NA | NA | NA | NA | NA | 2019-06-20 | 2019-06-25 | 2019-06-25 | 2019-07-22 | 2019-06-25 | 26.087860° | 44.017506° | 2019-06-30 | 2019-07-15 | ZUZA001 |  |  | 2019-07-23 | 2019-07-29 | FDED Not Approved | 2019-10-15 | Done | HOC Done |  | Private | Private | عبيد مطر المطيري | 0505138340 | 35,000.00 | 20*20 | RT | HO to CW Done | HO Done | A Sughair | تم تسليم الموقع
ZUZ053 | Macro | Aspiration | Central | Qassim | 2020 Scope | ملك خاص | 26.102 | 44.0188 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-04-07 | 2019-04-08 | Approved | 2019-05-12 15:53 | 2019-05-13 15:53 | IGATE | 14/05/2019 15:53:21 | SNR1010239 | NOBODY | ACCEPTED | 2019-04-11 | 2019-04-11 | 2019-05-19 | 2019-05-20 | 2019-05-20 | 2019-06-20 | NA | NA | NA | NA | NA | NA | 2019-06-20 | 2019-06-25 | 2019-06-25 | 2019-07-29 | 2019-06-25 | 26.100836° | 44.018894° | 2019-06-30 | 2019-07-10 | ZUZA008 |  |  | 2019-07-30 | 2019-07-30 | No Dependency | 2019-08-15 | Done | HOC Done |  | Private | Private | ابراهيم عبدالله ابراهيم الصليخان /مضاوي حمد السلوم | 0561919944 | 20,000.00 | 20*20 | GF | HO to CW Done | HO Done | A Sughair | تم تسليم الموقع
ZAR022 | Macro | Aspiration | Central | Qassim | 2020 Scope | ملك خاص | 25.8312 | 43.5691 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-16 | 2019-03-17 | Approved | 2019-05-18 15:58 | 2019-05-19 15:58 | IGATE | 20/05/2019 15:57:45 | SNR1010304 | NOBODY | ACCEPTED | 2019-03-20 | 2019-04-10 | 2019-04-10 | 2019-05-06 | 2019-05-20 | 2019-06-20 | NA | NA | NA | NA | NA | NA | 2019-06-20 | 2019-06-25 | 2019-06-25 |  | 2019-06-25 | 25.831937° | 43.565736° | 2019-06-30 | NA | NA |  |  | 2019-10-17 | 2019-10-17 | Pending HOC | 2019-08-15 | 2019-10-21 | W3-Oct | W2-Oct | Private | Private | ابراهيم عليان صالح العليان / حامد سعود العتيبي | 0561010001 | 30,000.00 | 20*20 | GF | FBP Not Issued | Below BM | A Sughair | تم تسليم الموقع بدون رخصة كما تم الاتفاق مع توال
ZAS032 | Macro | Aspiration | Central | Riyadh District | 2020 Scope | روضة سدير | 25.6244 | 45.5811 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-06 | 2019-03-07 | Approved | 2019-05-12 16:07 | 2019-05-13 16:07 | IGATE | 14/05/2019 16:07:08 | SNR1010240 | SNR_U | District Director | 2019-03-10 | 2019-04-10 | 2019-04-10 | 2019-04-10 | 2019-04-22 | 2019-06-20 | NA | NA | NA | NA | NA | NA | 2019-06-20 | 2019-07-04 | 2019-07-08 | 2019-07-10 | 2019-06-25 | 25.624339° | 45.579970° | 2019-06-30 | 2019-07-11 | 686-00-000 |  |  | 2019-07-10 | 2019-07-11 | No Dependency | 2019-09-15 | Done | HOC Done |  | Private | Private | عبدالعزيز عبد المحسن | 0504299632 | 30,000.00 | 20*20 | GF | HO to CW Done | HO Done | Ghamdi | تم تسليم الموقع
ZAZ011 | Macro | Aspiration | Central | Riyadh District | 2020 Scope | ملك خاص | 26.2641 | 44.8088 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-07 | 2019-03-08 | Approved | 2019-05-11 16:20 | 2019-05-12 16:20 | IGATE | 13/05/2019 16:19:46 | SNR1010236 | SNR_Q | GM Technical Procurement | 2019-03-11 | 2019-04-10 | 2019-04-10 | 2019-04-10 | 2019-04-02 | 2019-04-28 | NA | NA | NA | NA | NA | NA | 2019-05-13 | 2019-05-15 | 2019-05-27 | 2019-07-14 | 2019-05-09 | 26.264030° | 44.810130° | 2019-06-13 | 2019-07-14 | 609-00-000 |  |  | 2019-07-21 | 2019-07-23 | No Dependency | 2019-06-05 | Done | HOC Done |  | Private | Private | احمد سليمان عبيد | 0505154298 | 25,000.00 | 20*20 | GF | HO to CW Done | HO Done | Ghamdi | تم تسليم الموقع
ZAZ013 | Macro | Aspiration | Central | Riyadh District | 2020 Scope | الزلفي | 26.3146 | 44.8532 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-17 | 2019-03-18 | Approved | 2019-05-23 12:50 | 2019-05-24 12:50 | IGATE | 25/05/2019 12:50:11 | SNR1010370 | SNR_I | District Support | 2019-03-21 | 2019-04-10 | 2019-05-25 | 2019-05-29 | NA | NA | 2019-05-01 | [19 empty] | Pending HOC | 2019-12-15 | 2019-11-10 | W2-Nov |  | Non-Private | Baladiya | Baladiah Zulfi | NA | 0 | 0 | GF | IBP Not Issued | Below BM | Ghamdi | تم الاتفاق مع المؤسسة العامة وتم عمل اليوم ISR بانتظار موافقة RF
ZAZ028 | Macro | Aspiration | Central | Riyadh District | 2020 Scope | الزلفي | 26.3073 | 44.9166 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-04-18 | 2019-04-19 | Approved | 2019-05-12 16:18 | 2019-05-13 16:18 | IGATE | 14/05/2019 16:17:42 | SNR1010241 | NOBODY | ACCEPTED | 2019-04-22 | 2019-04-28 | 2019-05-19 | 2019-05-20 | NA | NA | 2019-04-14 | 2019-04-22 | 2019-04-22 | 2019-09-01 | 2019-09-15 | 2019-09-15 | NA | NA | 2019-09-15 | 2019-09-17 | 2019-06-22 | 26.307583° | 44.917548° | 2019-06-25 | 2019-09-03 | ZAZA988 |  |  | 2019-09-17 | 2019-09-17 | Pending HOC | 2019-08-15 | Done | HOC Done |  | Non-Private | Baladiya | Baladiah Zulfi | NA | 25,000.00 | 15*15 | GF | HO to CW Done | Below BM | Ghamdi | تم تسليم الموقع
ZAZ029 | Macro | Aspiration | Central | Riyadh District | 2020 Scope | الزلفي | 26.3201 | 44.8832 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-07 | 2019-03-08 | Approved | 2019-05-11 13:23 | 2019-05-12 13:23 | IGATE | 13/05/2019 13:22:32 | SNR1010227 | NOBODY | ACCEPTED | 2019-03-11 | 2019-04-10 | 2019-04-10 | 2019-04-10 | NA | NA | 2019-04-14 | 2019-04-18 | 2019-04-18 | 2019-04-22 | 2019-06-20 | 2019-06-30 | NA | NA | 2019-06-20 | 2019-07-23 | 2019-06-22 | 26.320049° | 44.883150° | 2019-06-24 | 2019-07-24 | ZAZA988 |  |  | 2019-07-24 | 2019-07-29 | No Dependency | 2019-08-15 | Done | HOC Done |  | Non-Private | Baladiya | Baladiah Zulfi | NA | 25,000.00 | 15*15 | GF | HO to CW Done | HO Done | Ghamdi | تم تسليم الموقع
ZBD018 | Macro | Aspiration | Central | Qassim | 2020 Scope | ملك خاص | 25.9739 | 43.7119 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-10 | 2019-03-11 | Approved | 2019-05-11 16:42 | 2019-05-12 16:42 | IGATE | 13/05/2019 16:41:54 | SNR1010238 | NOBODY | ACCEPTED | 2019-03-14 | 2019-04-10 | 2019-04-10 | 2019-04-18 | 2019-04-15 | 2019-04-28 | NA | NA | NA | NA | NA | NA | 2019-05-13 | 2019-05-14 | 2019-05-17 | 2019-05-22 | 2019-05-26 | 25.972485° | 43.710975° | 2019-06-13 | 2019-06-17 | ZBDA001 |  |  | 2019-06-17 | 2019-06-19 | No Dependency | 2019-06-14 | Done | HOC Done |  | Private | Private | متعب بن حمد بن محمد بن بتلاء | 0561334545 | 18,000.00 | 20*20 | GF | HO to CW Done | HO Done | A Sughair | تم تسليم الموقع
ZBK026 | Macro | Aspiration | Central | Qassim | 2020 Scope | ملك خاص | 26.1681 | 43.6042 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-10 | 2019-03-11 | Approved | 2019-05-11 16:28 | 2019-05-12 16:28 | IGATE | 13/05/2019 16:27:30 | SNR1010237 | NOBODY | ACCEPTED | 2019-03-14 | 2019-04-10 | 2019-04-10 | 2019-04-14 | 2019-04-22 | 2019-06-20 | NA | NA | NA | NA | NA | NA | 2019-06-20 | 2019-06-25 | 2019-06-25 | 2019-07-22 | 2019-06-25 | 26.168822° | 43.603444° | 2019-06-26 | 2019-07-10 | 606-00-000 |  |  | 2019-07-23 | 2019-07-23 | FDED Not Approved | 2019-08-15 | Done | HOC Done |  | Private | Private | عبدالرحمن عبدالله القبيشي | 0554494100 | 20,000.00 | 20*20 | GF | HO to CW Done | HO Done | A Sughair | تم تسليم الموقع
ZTB384 | Macro | Aspiration | Northern | Tabuk | 2020 Scope | جامعة تبوك | 28.4113 | 36.4818 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-03-16 | 2019-03-17 | Approved | 2019-05-02 16:12 | 2019-05-03 16:12 | IGATE | 04/05/2019 16:11:42 | SNR1010052 | SNR_O | Technical Procurement Section Manager | 2019-03-20 | 2019-04-10 | 2019-04-10 | 2019-04-14 | NA | NA | 2019-04-16 | 2019-10-01 | 2019-10-01 | 2019-10-01 | 2019-10-30 | 2019-11-10 | NA | NA | 2019-10-30 | 2019-11-10 |  |  |  | 2019-10-20 |  |  |  |  | 2019-10-30 | 2019-11-03 | Pending HOC | 2019-10-15 | 2019-10-21 | W3-Oct |  | Non-Private | Gov | Tabuk university | NA | 0 | 15*15 | GF | HO to CW Done | Above | Hatem | تم تسليم الموقع بدون رخصة كما تم الاتفاق مع توال
ZDB084 | Macro | Aspiration | Northern | Tabuk | 2020 Scope | ضباء | 27.2919 | 35.7574 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-17 | 2019-03-18 | Approved | 2019-05-20 10:38 | 2019-05-21 10:38 | IGATE | 22/05/2019 10:37:57 | SNR1010352 | SNR_I | District Support | 2019-03-21 | 2019-04-10 | 2019-04-10 | 2019-04-14 | NA | NA | 2019-04-15 | [19 empty] | Pending HOC | 2019-10-15 | 2019-12-19 | W3-Dec |  | Non-Private | Baladiya | Baladiya Deba | NA | 0 | 0 | GF | IBP Not Issued | Above | Hatem | تم الاجتماع مع الامانة وتم الاتفاق لاصدار العقود خلال اسبوعين
ZRR031 | Macro | Aspiration | Northern | Arrar | 2020 Scope | الكلية التقنية بعرعر | 31.0264 | 40.9032 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-04-18 | 2019-04-19 | Approved | 2019-05-25 11:49 | 2019-05-26 11:49 | IGATE | 27/05/2019 11:49:23 | SNR1010416 | SNR_I | District Support | 2019-04-22 | 2019-05-12 | 2019-06-17 | 2019-06-17 | NA | NA | 2019-04-29 | 2019-05-13 | [18 empty] | Pending HOC | 2019-10-15 | 2019-11-10 | W2-Nov |  | Non-Private | Gov | Technical College in Arrar | NA | 0 | 15*15 | GF | Contract Not Issued | Above | Sultan | تم الاتفاق مع المؤسسة العامة وتم عمل اليوم ISR بانتظار موافقة RF
ZHA302 | Macro | Aspiration | Central | Hail | 2020 Scope | ملك خاص | 27.8473 | 41.7329 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-17 | 2019-03-18 | Approved | 2019-05-13 15:32 | 2019-05-14 15:32 | IGATE | 15/05/2019 15:31:30 | SNR1010268 | NOBODY | ACCEPTED | 2019-03-21 | 2019-04-10 | 2019-04-10 | 2019-04-14 | 2019-04-16 | 2019-04-30 | NA | NA | NA | NA | NA | NA | 2019-05-19 | 2019-05-20 | 2019-05-27 | 2019-06-16 | 2019-05-21 | 27.8479 | 41.7334 | 2019-06-13 | 2019-06-17 | 2019-06-13 |  |  | 2019-06-17 | 2019-06-18 | No Dependency | 2019-06-08 | Done | HOC Done |  | Private | Private | ممدوح الرمالي | 541019089 | 25,000.00 | 20*20 | GF | HO to CW Done | HO Done | Abdulaziz | تم تسليم الموقع
ZHA334 | Macro | Aspiration | Central | Hail | 2020 Scope | الخطة | 27.8292 | 41.7196 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-17 | 2019-03-18 | Approved | 2019-05-18 17:05 | 2019-05-19 17:05 | IGATE | 20/05/2019 17:04:44 | SNR1010305 | NOBODY | ACCEPTED | 2019-03-21 | 2019-04-10 | 2019-04-10 | 2019-04-10 | 2019-04-03 | 2019-04-28 | NA | NA | NA | NA | NA | NA | 2019-04-28 | 2019-05-01 | 2019-05-17 | 2019-06-16 | 2019-06-13 | 27.8297 | 41.7201 | 2019-05-13 | 2019-06-17 | 611-14-000 | 45 | 400m | 2019-06-17 | 2019-06-18 | No Dependency | 2019-06-05 | Done | HOC Done |  | Private | Private | خويلد دراج الشمري | 0504977502 | 25,000.00 | 20*20 | GF | HO to CW Done | HO Done | Abdulaziz | تم تسليم الموقع
ZHA904 | Macro | Aspiration | Central | Hail | 2020 Scope | جامعه حائل | 27.6691 | 41.7124 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-04-06 | 2019-04-07 | Approved | 2019-05-25 11:30 | 2019-05-26 11:30 | IGATE | 15/10/2019 11:47:14 | SNR1012106 | SNR_O | Technical Procurement Section Manager | 2019-04-10 | 2019-05-20 | 2019-06-17 | 2019-06-17 | NA | NA | 2019-04-15 | 2019-09-15 | 2019-09-15 | 2019-09-15 | 2019-10-24 | 2019-11-10 | NA | NA | 2019-10-24 | 2019-11-10 | 2019-10-01 | 27.6713 | 41.7092 | 2019-10-03 | 2019-10-23 | Z43013 |  |  | 2019-10-24 | 2019-10-24 | Pending HOC | 2019-10-15 | 2019-10-21 | W3-Oct |  | Non-Private | Gov | University of Hail | NA | 40,000.00 | 440 | GF | HO to CW Done | Above | Abdulaziz | تم تسليم الموقع بدون رخصة كما تم الاتفاق مع توال
ZHF277 | Macro | Aspiration | Eastern | Hofof | 2019 Scope | الهفوف | 25.4047 | 49.5484 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-06-30 | 2019-07-01 | Approved | 2019-07-06 10:52 | 2019-07-07 10:52 | IGATE | 08/07/2019 10:51:44 | SNR1011133 | SNR_I | District Support | 2019-07-04 | 2019-07-04 | 2019-07-04 | 2019-07-04 | NA | NA | 2019-07-11 | [19 empty] | Pending HOC |  | 2019-12-15 | W3-Dec |  | Non-Private | Baladiya | AlAhsa Amana | 0502910009 | 0 | 0 | GF | IBP Not Issued | Above | Salah | تحت التخطيط بالبلدية بانتظار موافقتهم - يحتاج ما يقارب 2 اسبوع لاصدار العقد
ZMA043 | Macro | Aspiration | Central | Riyadh District | 2020 Scope | المجمعة | 25.9129 | 45.3519 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-16 | 2019-03-17 | Approved | 2019-05-23 17:45 | 2019-05-24 17:45 | IGATE | 25/05/2019 17:45:19 | SNR1010399 | NOBODY | ACCEPTED | 2019-03-20 | 2019-04-10 | 2019-04-10 | 2019-04-14 | NA | NA | 2019-04-14 | 2019-04-25 | 2019-04-25 | 2019-05-27 | 2019-06-20 | 2019-06-30 | NA | NA | 2019-06-20 | 2019-07-29 | 2019-06-23 | 25.910141° | 45.352017° | 2019-06-24 | 2019-06-30 | 610-00-000 |  |  | 2019-07-30 | 2019-07-30 | FDED Not Approved | 2019-08-15 | Done | HOC Done |  | Non-Private | Baladiya | Baladiyah Almajmah | NA | 36,000.00 | 17*17 | GF | HO to CW Done | HO Done | Ghamdi | تم تسليم الموقع
ZMA047 | Macro | Aspiration | Central | Riyadh District | 2020 Scope | المجمعة | 25.9048 | 45.4028 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-09 | 2019-03-10 | Approved | 2019-05-12 16:57 | 2019-05-13 16:57 | IGATE | 14/05/2019 16:57:20 | SNR1010243 | NOBODY | ACCEPTED | 2019-03-13 | 2019-04-10 | 2019-04-10 | 2019-04-10 | NA | NA | 2019-04-14 | 2019-04-25 | 2019-04-25 | 2019-07-30 | 2019-08-28 | 2019-08-29 | NA | NA | 2019-06-20 | 2019-07-29 | 2019-06-22 | 25.905175° | 45.403365° | 2019-06-24 | 2019-06-30 | ZMAA042 |  |  | 2019-08-28 | 2019-08-29 | FDED Not Approved | 2019-08-15 | Done | HOC Done |  | Non-Private | Baladiya | Baladiyah Almajmah | NA | 34,000.00 | 15x15 | GF | HO to CW Done | HO Done | Ghamdi | تم تسليم الموقع
ZMA049 | Macro | Aspiration | Central | Riyadh District | 2020 Scope | المجمعة | 25.9264 | 45.3994 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-12 | 2019-03-13 | Approved | 2019-05-12 17:11 | 2019-05-13 17:11 | IGATE | 14/05/2019 17:11:23 | SNR1010244 | NOBODY | ACCEPTED | 2019-03-16 | 2019-04-10 | 2019-05-14 | 2019-05-13 | 2019-05-14 | 2019-06-20 | NA | NA | NA | NA | NA | NA | 2019-06-20 | 2019-06-25 | 2019-07-03 | 2019-07-03 | 2019-07-03 | 25.924400° | 45.399370° | 2019-06-30 | 2019-07-02 | ZMAA034 | 35 |  | 2019-07-03 | 2019-07-07 | No Dependency | 2019-08-15 | Done | HOC Done |  | Private | Private | مرزوق حمد | 0503027404 | 30,000.00 | 20*20 | GF | HO to CW Done | HO Done | Ghamdi | تم تسليم الموقع
ZMA050 | Macro | Aspiration | Central | Riyadh District | 2020 Scope | ملك خاص | 25.9232 | 45.3875 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-09 | 2019-03-10 | Approved | 2019-05-13 12:48 | 2019-05-14 12:48 | IGATE | 15/05/2019 12:48:10 | SNR1010263 | NOBODY | ACCEPTED | 2019-03-13 | 2019-04-10 | 2019-04-10 | 2019-04-10 | 2019-04-02 | 2019-04-28 | NA | NA | NA | NA | NA | NA | 2019-04-28 | 2019-04-29 | 2019-05-19 | 2019-06-26 | 2019-05-09 | 25.922975° | 45.386924° | 2019-06-13 | 2019-06-17 | 610-00-000 |  |  | 2019-06-26 | 2019-06-27 | FDED Not Approved | 2019-06-07 | Done | HOC Done |  | Private | Private | سلطانة بنت احمد العمار | 0555261358 | 23,000.00 | 20*20 | RT | HO to CW Done | HO Done | Ghamdi | تم تسليم الموقع
ZNB017 | Macro | Aspiration | Central | Qassim | 2020 Scope | القصيم | 25.8117 | 42.9609 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-04-18 | 2019-04-19 | Submitted | 2019-08-18 |  | IGATE | #N/A | #N/A | #N/A | #N/A | 2019-04-22 |  |  |  | NA | NA | [20 empty] | Pending HOC | 2019-12-15 | 2019-10-23 | W3-Oct |  | Non-Private | Baladiya | Amanh AlQasim | NA | NA | NA | GF | ,ISR IN GAT | Above | A Sughair | trying to get access to Compound to found location
ZQN001 | Macro | Aspiration | Central | Qassim | Removed | الاسياح | 26.7676 | 44.1995 | Huawei | Removed from Scope | New Location |  |  | Macro | Doable |  | Approved | 2019-04-18 | 2019-04-19 | Submitted | 2019-08-22 |  | IGATE | #N/A | #N/A | #N/A | #N/A | 2019-04-22 | 2019-06-16 |  |  |  |  | NA | NA | NA | NA | NA | NA | [15 empty] | 2019-12-15 | Out | Out |  | Private | Private | محمد الفهيد | NA | NA | NA | GF | ,ISR IN GAT |  | A Sughair | Out
ZQU032 | Macro | Aspiration | Northern | Northern Border | 2020 Scope | القريات | 31.2537 | 37.4307 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-04-18 | 2019-04-19 | Approved | 2019-08-05 13:11 | 2019-08-06 13:11 | IGATE | 07/08/2019 13:11:21 | SNR1011604 | SNR_V | Technical Procurement Section Manager | 2019-04-22 | 2019-09-03 | 2019-09-03 | 2019-09-03 | NA | NA | NA | NA | NA | NA | NA | NA | 2019-09-04 | 2019-09-05 | 2019-09-04 | 2019-09-05 | 2019-08-28 | 31.256036° | 37.431813° | 2019-08-29 | 2019-09-02 | ZQUA994 |  |  | 2019-09-05 | 2019-09-05 | FDED Not Approved | 2019-10-15 | Done | HOC Done |  | Private | Private | ناصر الشراري | 0503125160 | 25,000.00 | 20*20 | GF | HO to CW Done | HO Done | Sultan | تم تسليم الموقع
ZQU037 | Macro | Aspiration | Northern | Northern Border | 2020 Scope | القريات | 31.3487 | 37.3941 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-17 | 2019-03-18 | Approved | 2019-05-23 16:17 | 2019-05-24 16:17 | IGATE | 25/05/2019 16:16:36 | SNR1010390 | SNR_I | District Support | 2019-03-21 | 2019-04-10 | 2019-04-10 | 2019-04-14 | NA | NA | 2019-04-16 | [19 empty] | Pending HOC | 2019-10-15 | 2019-12-05 | W1-Dec |  | Non-Private | Baladiya | Baladiyah Qurayat | NA | 0 | 0 | GF | IBP Not Issued | Above | Sultan | بانتظار موافقة RF للمواقع الجديدة
ZQU039 | Macro | Aspiration | Northern | Northern Border | 2020 Scope | ملك خاص | 31.3648 | 37.2907 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-14 | 2019-03-15 | Approved | 2019-05-03 11:17 | 2019-05-04 11:17 | IGATE | 05/05/2019 11:16:36 | SNR1010060 | NOBODY | ACCEPTED | 2019-03-18 | 2019-04-10 | 2019-04-10 | 2019-04-14 | 2019-05-14 | 2019-06-20 | NA | NA | NA | NA | NA | NA | 2019-06-20 | 2019-06-30 | 2019-07-01 | 2019-07-28 | 2019-06-25 | 31.3624 | 37.2909 | 2019-06-30 | 2019-07-10 | 411-00-000 |  |  | 2019-07-28 | 2019-07-29 | No Dependency | 2019-08-15 | Done | HOC Done |  | Private | Private | معاشي صبيح العنزي | 0555390617 | 30,000.00 | 20*20 | GF | HO to CW Done | HO Done | Sultan | تم تسليم الموقع
ZQU041 | Macro | Aspiration | Northern | Northern Border | 2020 Scope | ملك خاص | 31.3306 | 37.3661 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-17 | 2019-03-18 | Approved | 2019-05-26 16:48 | 2019-05-27 16:48 | IGATE | 17/10/2019 14:57:02 | SNR1012142 | SNR_O | Technical Procurement Section Manager | 2019-03-21 | 2019-04-10 | 2019-04-10 | 2019-04-14 | 2019-06-12 | 2019-09-11 | NA | NA | NA | NA | NA | NA | 2019-09-17 | 2019-09-24 | 2019-09-15 | 2019-11-03 | 2019-09-01 | 31.330777° | 37.365896° | 2019-09-01 | 2019-09-02 | 411-00-000 |  |  | 2019-10-17 | 2019-10-17 | Pending HOC | 2019-09-15 | 2019-12-05 | W1-Dec | W2-Oct | Private | Private | عوض بن حضيري العنزي | 0503392539 | 20,000.00 | All Roof top | RT | HO to CW Done | Below BM | Sultan | تم تسليم الموقع بدون رخصة كما تم الاتفاق مع توال
ZQU970 | Macro | Aspiration | Northern | Northern Border | 2020 Scope | القريات | 31.3521 | 37.3337 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-17 | 2019-03-18 | Approved | 2019-05-23 16:21 | 2019-05-24 16:21 | IGATE | 25/05/2019 16:20:56 | SNR1010391 | SNR_I | District Support | 2019-03-21 | 2019-04-10 | 2019-04-10 | 2019-04-14 | NA | NA | 2019-04-16 | [19 empty] | Pending HOC | 2019-10-15 | 2019-12-05 | W1-Dec |  | Non-Private | Baladiya | Baladiyah Qurayat | NA | 0 | 0 | GF | IBP Not Issued | Above | Sultan | بانتظار موافقة RF للمواقع الجديدة
ZQW020 | Macro | Aspiration | Central | Qassim | 2020 Scope | ملك خاص | 26.0796 | 43.6028 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-10 | 2019-03-11 | Approved | 2019-05-23 16:31 | 2019-05-24 16:31 | IGATE | 25/05/2019 16:30:34 | SNR1010392 | NOBODY | ACCEPTED | 2019-03-14 | 2019-04-10 | 2019-04-10 | 2019-04-10 | 2019-04-22 | 2019-08-05 | NA | NA | NA | NA | NA | NA | 2019-07-28 | 2019-08-20 | 2019-08-01 | 2019-08-20 | 2019-08-01 | 26.080139° | 43.603929° | 2019-08-20 | 2019-08-22 | 612-00-000 |  |  | 2019-08-22 | 2019-08-25 | FDED Not Approved | 2019-07-20 | Done | HOC Done |  | Private | Private | عبدالعزيز المهوس | 0553550777 | 23,000.00 | 20*20 | GF | HO to CW Done | HO Done | A Sughair | تم تسليم الموقع
ZQW025 | Macro | Aspiration | Central | Qassim | 2020 Scope | ملك خاص | 26.0668 | 43.5371 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-10 | 2019-03-11 | Approved | 2019-05-13 13:41 | 2019-05-14 13:41 | IGATE | 15/05/2019 13:40:36 | SNR1010264 | NOBODY | ACCEPTED | 2019-03-14 | 2019-04-10 | 2019-04-10 | 2019-04-10 | 2019-04-02 | 2019-06-20 | NA | NA | NA | NA | NA | NA | 2019-06-20 | 2019-06-25 | 2019-06-25 | 2019-07-23 | 2019-06-25 | 26.067015° | 43.536506° | 2019-06-26 | 2019-07-10 | 605-00-000 |  |  | 2019-07-24 | 2019-07-24 | FDED Not Approved | 2019-06-06 | Done | HOC Done |  | Private | Private | الوكيل/ صالح ناصر الخميس | 0504154056 | 20,000.00 | 20*20 | GF | HO to CW Done | HO Done | A Sughair | تم تسليم الموقع
ZQW937 | Macro | Aspiration | Central | Qassim | 2020 Scope | رياض الخبرا | 26.0532 | 43.5701 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-04-18 | 2019-04-19 | Approved | 2019-06-23 09:39 | 2019-06-24 09:39 | IGATE | 25/06/2019 09:39:20 | SNR1010788 | NOBODY | ACCEPTED | 2019-04-22 | 2019-04-28 | 2019-05-02 | 2019-05-06 | NA | NA | 2019-04-15 | 2019-06-12 | 2019-05-12 | 2019-05-27 | 2019-07-18 | 2019-07-28 | NA | NA | 2019-08-05 | 2019-09-15 | 2019-09-10 | 26.054068° | 43.570580° | 2019-09-09 | 2019-09-10 | 605-00-000 |  |  | 2019-09-15 | 2019-09-16 | FDED Not Approved | 2019-10-15 | Done | HOC Done |  | Non-Private | Baladiya | Baladiyah Riyadh Alkoubra | NA | 20,250.00 | ok | GF | HO to CW Done | HO Done | A Sughair | تم تسليم الموقع
ZRF023 | Macro | Aspiration | Northern | Arrar | 2020 Scope | رفحاء | 29.596 | 43.5529 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-17 | 2019-03-18 | Approved | 2019-05-13 15:04 | 2019-05-14 15:04 | IGATE | 15/05/2019 15:03:37 | SNR1010267 | NOBODY | ACCEPTED | 2019-03-21 | 2019-04-10 | 2019-04-10 | 2019-04-14 | 2019-05-14 | 2019-06-20 | NA | NA | NA | NA | NA | NA | 2019-06-20 | 2019-06-30 | 2019-07-01 | 2019-07-17 | 2019-06-25 | 29.5962 | 43.5519 | 2019-06-30 | 2019-07-10 | 484-00-000 |  |  | 2019-07-18 | 2019-07-24 | Pending RFI | 2019-08-15 | Done | HOC Done |  | Private | Private | نشمي الشمري | 0539999909 | 25,000.00 | 20*20 | GF | HO to CW Done | HO Done | Sultan | تم تسليم الموقع
ZHF315 | Macro | Aspiration | Eastern | Hofof | 2020 Scope | أمانة الإحساء | 25.3195 | 49.5655 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-07-24 | 2019-07-25 | Approved | 2019-07-23 14:51 | 2019-07-24 14:51 | IGATE | 25/07/2019 14:51:25 | SNR1011465 | SNR_I | District Support | 2019-07-28 | 2019-07-28 | 2019-07-28 | 2019-08-05 | NA | NA | 2019-08-05 | [19 empty] | FBP Not submitted |  | 2019-12-15 | W3-Dec |  | Non-Private | Baladiya | AlAhsa Amana | NA | 0 | 0 | GF | IBP Not Issued | Above | Salah | تحت التخطيط بالبلدية بانتظار موافقتهم - يحتاج ما يقارب 2 اسبوع لاصدار العقد
ZHF316 | Macro | Aspiration | Eastern | Hofof | 2019 Scope | الهفوف | 25.3118 | 49.5789 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-06-30 | 2019-07-01 | Approved | 2019-07-06 10:58 | 2019-07-07 10:58 | IGATE | 08/07/2019 10:57:31 | SNR1011135 | SNR_O | Technical Procurement Section Manager | 2019-07-04 | 2019-07-04 | 2019-07-04 | 2019-07-04 | NA | NA | 2019-07-11 | 2019-11-06 | 2019-11-06 | 2019-11-06 | 2019-11-11 |  |  |  | 2019-11-11 | [9 empty] | 2019-11-13 |  | Pending HOC |  | 2019-12-15 | W3-Dec |  | Non-Private | Baladiya | AlAhsa Amana | NA | 0 | 0 | GF | Priv. Contract Not Issued From TAWAL | Above | Salah | بانتظار اصدار العقد من الامانة
ZHF318 | Macro | Aspiration | Eastern | Hofof | 2020 Scope | أمانة الإحساء | 25.3161 | 49.5927 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-07-24 | 2019-07-25 | Approved | 2019-07-20 13:32 | 2019-07-21 13:32 | IGATE | 22/07/2019 13:31:47 | SNR1011414 | SNR_O | Technical Procurement Section Manager | 2019-07-28 | 2019-07-28 | 2019-07-28 | 2019-08-05 | NA | NA | 2019-08-05 | 2019-10-10 | 2019-10-10 | 2019-10-13 | 2019-10-14 |  | NA | NA | 2019-10-15 | [9 empty] | 2019-10-21 | 2019-10-21 | FBP Not submitted |  | 2019-12-12 | W2-Dec | W3-Oct | Non-Private | Baladiya | AlAhsa Amana | NA | 0 | 0 | GF | FBP Not Issued | Above | Salah | تم تسليم الموقع بدون رخصة كما تم الاتفاق مع توال
ZJB157 | Macro | Aspiration | Eastern | Jubail | 2020 Scope | الهيئة الملكية بالجبيل | 27.1063 | 49.5101 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-05-15 | 2019-05-16 | Approved | 2019-07-23 14:55 | 2019-07-24 14:55 | IGATE | 29/10/2019 13:10:52 | SNR1012246 | SNR_D | Vendor SA | 2019-05-19 | 2019-07-04 | 2019-07-28 | 2019-08-05 | NA | NA | 2019-05-07 | [19 empty] | Pending HOC | 2019-11-15 | 2019-12-05 | W1-Dec |  | Non-Private | Gov | RC | NA | 0 | 0 | GF | IBP Not Issued | Below BM | Faris | بانتظار ارسال موافقة للهيئة الملكية
ZRR028 | Macro | Aspiration | Northern | Arrar | 2020 Scope | ملك خاص | 31.0038 | 41.0675 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-14 | 2019-03-15 | Approved | 2019-05-02 15:46 | 2019-05-03 15:46 | IGATE | 04/05/2019 15:45:36 | SNR1010049 | NOBODY | ACCEPTED | 2019-03-18 | 2019-04-10 | 2019-04-10 | 2019-04-14 | 2019-05-13 | 2019-06-20 | NA | NA | NA | NA | NA | NA | 2019-06-20 | 2019-06-30 | 2019-07-01 | 2019-07-15 | 2019-06-25 | 31.0033 | 41.0657 | 2019-06-30 | 2019-07-09 | ZRRA005 |  |  | 2019-07-18 | 2019-07-16 | No Dependency | 2019-11-15 | Done | HOC Done |  | Private | Private | جعيف العنزي | 0503382000 | 30,000.00 | 20*20 | GF | HO to CW Done | HO Done | Sultan | تم تسليم الموقع
ZRR029 | Macro | Aspiration | Northern | Arrar | 2020 Scope | جامعة الحدود الشمالية | 30.8422 | 41.1933 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-04-27 | 2019-04-28 | Approved | 2019-06-23 17:47 | 2019-06-24 17:47 | IGATE | 25/06/2019 17:46:41 | SNR1010830 | NOBODY | ACCEPTED | 2019-05-01 | 2019-05-19 | 2019-05-25 | 2019-05-29 | NA | NA | 2019-04-22 | 2019-05-13 | 2019-05-29 | 2019-06-13 | 2019-07-11 | 2019-07-21 | NA | NA | 2019-07-11 | 2019-07-17 | 2019-06-24 | 30.846601° | 41.18995° | 2019-06-25 | 2019-07-11 | ZRRA978 |  |  | 2019-07-18 | 2019-07-29 | FDED Not Approved | 2019-10-15 | Done | HOC Done |  | Non-Private | Gov | Northern borders university | NA | 20,000.00 | 15x15 | GF | HO to CW Done | HO Done | Sultan | تم تسليم الموقع
ZJB170 | Macro | Aspiration | Eastern | Jubail | 2020 Scope | الهيئة الملكية بالجبيل | 27.0962 | 49.5205 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-03-08 | 2019-03-09 | Approved | 2019-08-03 18:18 | 2019-08-04 18:18 | IGATE | 05/08/2019 18:17:30 | SNR1011585 | SNR_I | District Support | 2019-03-12 | 2019-04-10 | 2019-04-10 | 2019-05-01 | NA | NA | 2019-05-07 | [19 empty] | Pending HOC | 2019-11-15 | 2019-12-05 | W1-Dec |  | Non-Private | Gov | RC | NA | 0 | 0 | GF | IBP Not Issued | Below BM | Faris | تم رفض المواقع المقترحة من الهيئة الملكية
ZRR032 | Macro | Aspiration | Northern | Arrar | 2020 Scope | ملك خاص | 31.0089 | 41.0833 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-17 | 2019-03-18 | Approved | 2019-05-12 17:36 | 2019-05-13 17:36 | IGATE | 14/05/2019 17:36:27 | SNR1010247 | NOBODY | ACCEPTED | 2019-03-21 | 2019-04-10 | 2019-04-10 | 2019-04-14 | 2019-05-14 | 2019-06-20 | NA | NA | NA | NA | NA | NA | 2019-06-20 | 2019-06-30 | 2019-07-01 | 2019-07-15 | 2019-06-25 | 31.009525° | 41.08133° | 2019-07-01 | 2019-07-17 | 413-00-000 |  |  | 2019-07-16 | 2019-07-29 | No Dependency | 2019-10-15 | Done | HOC Done |  | Private | Private | جعيف العنزي | 0503382000 | 30,000.00 | 20x20 m | GF | HO to CW Done | HO Done | Sultan | تم تسليم الموقع
ZRS005 | Macro | Aspiration | Central | Riyadh District | 2020 Scope | روضة سدير | 25.6499 | 45.5544 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-06 | 2019-03-07 | Approved | 2019-05-13 15:43 | 2019-05-14 15:43 | IGATE | 15/05/2019 15:43:23 | SNR1010269 | NOBODY | ACCEPTED | 2019-03-10 | 2019-04-10 | 2019-04-10 | 2019-04-10 | NA | NA | 2019-04-14 | 2019-06-13 | 2019-04-24 | 2019-04-24 | 2019-06-20 | 2019-06-30 | NA | NA | 2019-06-20 | 2019-07-08 | 2019-06-22 | 25.649788° | 45.554983° | 2019-06-25 | 2019-07-10 | FRB05 |  | 15X15 | 2019-07-10 | 2019-07-11 | FDED Not Approved | 2019-09-15 | Done | HOC Done |  | Non-Private | Baladiya | Baladiya Rodet Sder | NA | 33,750.00 | 15*15 | GF | HO to CW Done | HO Done | Ghamdi | تم تسليم الموقع
ZSK100 | Macro | Aspiration | Northern | Arrar | 2020 Scope | مستشفى الملك عبدالعزيز التخصصي | 29.939 | 40.1884 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-10 | 2019-03-11 | Approved | 2019-07-28 16:29 | 2019-07-29 16:29 | IGATE | 30/07/2019 16:29:14 | SNR1011512 | NOBODY | ACCEPTED | 2019-03-14 | 2019-04-10 | 2019-05-25 | 2019-08-05 | NA | NA | NA | NA | NA | NA | NA | NA | 2019-09-15 | 2019-09-23 | 2019-09-23 | 2019-09-23 | 2019-09-09 | 29.942904° | 40.183968° | 2019-09-11 | 2019-09-19 | ZSKA005 |  |  | 2019-09-23 | 2019-10-10 | Pending HOC | 2019-12-15 | Done | HOC Done |  | Private | Private | عبدالله سعد | 0505391500 | 30,000.00 | 20X20 | GF | HO to CW Done | Below BM | Sultan | تم تسليم الموقع
ZSK117 | Macro | Aspiration | Northern | Arrar | 2020 Scope | الجوف | 29.9847 | 40.2279 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-10 | 2019-03-11 | Approved | 2019-05-02 15:54 | 2019-05-03 15:54 | IGATE | 10/11/2019 16:44:33 | SNR1012328 | SNR_B | RF Team Leader | 2019-03-14 | 2019-04-10 | 2019-04-10 |  | NA | NA | 2019-05-02 | [19 empty] | Pending HOC | 2019-09-15 | 2019-12-15 | W3-Dec |  | Non-Private | Baladiya | Amanah Jouf | 0 | 0 | 0 | GF | IBP Not Issued | Below BM | Sultan | تم رفع الاقرار المساحي وبانتظار العقد من البلدية
ZSS002 | Macro | Aspiration | Central | Qassim | 2020 Scope | الشماسية | 26.3195 | 44.239 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-04-06 | 2019-04-07 | Approved | 2019-05-13 14:16 | 2019-05-14 14:16 | IGATE | 15/05/2019 14:15:50 | SNR1010265 | NOBODY | ACCEPTED | 2019-04-10 | 2019-04-10 | 2019-04-10 | 2019-04-10 | 2019-04-23 | 2019-06-20 | NA | NA | NA | NA | NA | NA | 2019-06-20 | 2019-07-02 | 2019-07-02 | 2019-08-21 | 2019-06-25 | 26.319420° | 44.238820° | 2019-06-24 | 2019-07-29 | FRB11 |  |  | 2019-08-21 | 2019-08-21 | Pending HOC | 2019-09-15 | Done | HOC Done |  | Private | Private | عمر عبدالرحمن صالح | 564336999 | 25,000.00 | 20*20 | GF | HO to CW Done | HO Done | A Sughair | تم تسليم الموقع
ZJB175 | Macro | Aspiration | Eastern | Jubail | 2020 Scope | الهيئة الملكية بالجبيل | 27.105 | 49.529 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-05-15 | 2019-05-16 | Approved | 2019-07-05 18:29 | 2019-07-06 18:29 | IGATE | 07/07/2019 18:29:19 | SNR1011113 | SNR_F | District Director | 2019-05-19 | 2019-07-04 | 2019-07-04 | 2019-07-04 | NA | NA | 2019-05-07 | [19 empty] | Pending HOC | 2019-11-15 | 2019-12-05 | W1-Dec |  | Non-Private | Gov | RC | NA | 0 | 0 | GF | IBP Not Issued | Below BM | Faris | تم رفض المواقع المقترحة من الهيئة الملكية
ZTD003 | Macro | Aspiration | Central | Riyadh District | 2020 Scope | ثادق | 25.2549 | 45.8654 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-06 | 2019-03-07 | Approved | 2019-05-13 14:42 | 2019-05-14 14:42 | IGATE | 15/05/2019 14:42:26 | SNR1010266 | NOBODY | ACCEPTED | 2019-03-10 | 2019-04-10 | 2019-04-10 | 2019-04-10 | NA | NA | 2019-04-14 | 2019-04-25 | 2019-04-29 | 2019-05-27 | 2019-06-20 | 2019-06-30 | NA | NA | 2019-06-20 | 2019-10-28 | 2019-06-22 | 25.254255° | 45.866773° | 2019-06-25 | 2019-09-19 | 686-21-000 |  |  | 2019-10-20 | 2019-10-20 | Pending HOC | 2019-11-15 | 2019-10-16 | W2-Oct | W3-Oct | Non-Private | Baladiya | Baladiya Thadig | NA | 27,000.00 | 15*15 | GF | HO to CW Done | Below BM | Ghamdi | تم تسليم الموقع بدون رخصة كما تم الاتفاق مع توال
ZTR015 | Macro | Aspiration | Northern | Northern Border | 2020 Scope | هيئة مدن | 31.6524 | 38.8633 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-06-16 | 2019-06-17 | Approved | 2019-07-08 17:20 | 2019-07-09 17:20 | IGATE | 10/07/2019 17:19:33 | SNR1011224 | SNR_I | District Support | 2019-06-20 | 2019-07-04 | 2019-07-04 | 2019-07-04 | NA | NA | 2019-06-19 | [19 empty] | Pending HOC | 2019-11-15 | 2019-12-05 | W1-Dec |  | Non-Private | Gov | Modon | 0504866803 | 0 | 0 | GF | IBP Not Issued | Above | M. Ramadan | New Location received from MODON, under RF to check
ZTR026 | Macro | Aspiration | Northern | Northern Border | 2020 Scope | هيئة مدن | 31.6622 | 38.9521 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-06-16 | 2019-06-17 | Approved | 2019-07-05 18:11 | 2019-07-06 18:11 | IGATE | 07/07/2019 18:10:32 | SNR1011108 | SNR_I | District Support | 2019-06-20 | 2019-07-04 | 2019-07-04 | 2019-07-04 | NA | NA | 2019-06-19 | [19 empty] | Pending HOC | 2019-12-09 | 2019-12-05 | W1-Dec |  | Non-Private | Gov | Modon | NA | 0 | 0 | GF | IBP Not Issued | Above | M. Ramadan | New Location received from MODON, under RF to check
ZTR037 | Macro | Aspiration | Northern | Northern Border | 2020 Scope | هيئة مدن | 31.7435 | 38.977 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-06-16 | 2019-06-17 | Approved | 2019-07-23 15:22 | 2019-07-24 15:22 | IGATE | 25/07/2019 15:21:40 | SNR1011470 | SNR_I | District Support | 2019-06-20 | 2019-07-04 | 2019-07-28 | 2019-08-05 | NA | NA | 2019-06-19 | [19 empty] | Pending HOC | 2019-12-09 | 2019-12-05 | W1-Dec |  | Non-Private | Gov | Modon | NA | 0 | 0 | GF | IBP Not Issued | Above | M. Ramadan | New Location received from MODON, under RF to check
ZTR040 | Macro | Aspiration | Northern | Northern Border | 2020 Scope | هيئة مدن | 31.7416 | 39.0196 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-06-30 | 2019-07-01 | Approved | 2019-07-23 15:32 | 2019-07-24 15:32 | IGATE | 25/07/2019 15:32:23 | SNR1011471 | SNR_I | District Support | 2019-07-04 | 2019-07-04 | 2019-07-28 | 2019-08-05 | NA | NA | 2019-06-19 | [19 empty] | Pending HOC | 2019-12-09 | 2019-12-05 | W1-Dec |  | Non-Private | Gov | Modon | NA | 0 | 0 | GF | IBP Not Issued | Above | M. Ramadan | New Location received from MODON, under RF to check
ZTR043 | Macro | Aspiration | Northern | Northern Border | 2020 Scope | هيئة مدن | 31.7276 | 38.9535 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-06-16 | 2019-06-17 | Approved | 2019-07-05 18:17 | 2019-07-06 18:17 | IGATE | 07/07/2019 18:17:20 | SNR1011110 | SNR_I | District Support | 2019-06-20 | 2019-07-04 | 2019-07-04 | 2019-07-04 | NA | NA | 2019-06-19 | [19 empty] | Pending HOC | 2019-12-09 | 2019-12-05 | W1-Dec |  | Non-Private | Gov | Modon | NA | 0 | 0 | GF | IBP Not Issued | Above | M. Ramadan | New Location received from MODON, under RF to check
ZTR045 | Macro | Aspiration | Northern | Northern Border | 2020 Scope | هيئة مدن | 31.7758 | 39.0199 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-06-16 | 2019-06-17 | Approved | 2019-07-23 15:48 | 2019-07-24 15:48 | IGATE | 25/07/2019 15:48:03 | SNR1011474 | SNR_I | District Support | 2019-06-20 | 2019-07-04 | 2019-07-28 | 2019-08-05 | NA | NA | 2019-06-19 | [19 empty] | Pending HOC | 2019-12-09 | 2019-12-05 | W1-Dec |  | Non-Private | Gov | Modon | NA | 0 | 0 | GF | IBP Not Issued | Above | M. Ramadan | New Location received from MODON, under RF to check
ZTR047 | Macro | Aspiration | Northern | Northern Border | 2020 Scope | هيئة مدن | 31.7937 | 39.0211 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-06-16 | 2019-06-17 | Approved | 2019-07-23 15:37 | 2019-07-24 15:37 | IGATE | 25/07/2019 15:36:49 | SNR1011472 | SNR_I | District Support | 2019-06-20 | 2019-07-04 | 2019-07-28 | 2019-08-05 | NA | NA | 2019-06-19 | [19 empty] | Pending HOC | 2019-12-09 | 2019-12-05 | W1-Dec |  | Non-Private | Gov | Modon | NA | 0 | 0 | GF | IBP Not Issued | Above | M. Ramadan | New Location received from MODON, under RF to check
ZTR048 | Macro | Aspiration | Northern | Northern Border | 2020 Scope | هيئة مدن | 31.8328 | 39.0376 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-06-16 | 2019-06-17 | Approved | 2019-07-23 15:40 | 2019-07-24 15:40 | IGATE | 25/07/2019 15:39:39 | SNR1011473 | SNR_I | District Support | 2019-06-20 | 2019-07-04 | 2019-07-28 | 2019-08-05 | NA | NA | 2019-06-19 | [19 empty] | Pending HOC | 2019-12-09 | 2019-12-05 | W1-Dec |  | Non-Private | Gov | Modon | NA | 0 | 0 | GF | IBP Not Issued | Above | M. Ramadan | New Location received from MODON, under RF to check
ZTR053 | Macro | Aspiration | Northern | Northern Border | 2020 Scope | هيئة مدن | 31.6594 | 38.8759 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-06-16 | 2019-06-17 | Approved | 2019-07-08 17:16 | 2019-07-09 17:16 | IGATE | 10/07/2019 17:15:42 | SNR1011223 | SNR_I | District Support | 2019-06-20 | 2019-07-04 | 2019-07-04 | 2019-07-04 | NA | NA | 2019-06-19 | [19 empty] | Pending HOC | 2019-12-09 | 2019-12-05 | W1-Dec |  | Non-Private | Gov | Modon | 0504866803 | 0 | 0 | GF | IBP Not Issued | Above | M. Ramadan | New Location received from MODON, under RF to check
ZTR055 | Macro | Aspiration | Northern | Northern Border | 2020 Scope | هيئة مدن | 31.7562 | 38.9029 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-06-16 | 2019-06-17 | Approved | 2019-07-05 18:14 | 2019-07-06 18:14 | IGATE | 07/07/2019 18:13:57 | SNR1011109 | SNR_I | District Support | 2019-06-20 | 2019-07-04 | 2019-07-04 | 2019-07-04 | NA | NA | 2019-06-19 | [19 empty] | Pending HOC | 2019-12-09 | 2019-12-05 | W1-Dec |  | Non-Private | Gov | Modon | NA | 0 | 0 | GF | IBP Not Issued | Above | M. Ramadan | New Location received from MODON, under RF to check
ZTR088 | Macro | Aspiration | Northern | Northern Border | 2020 Scope | طريف | 31.6541 | 38.632 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-17 | 2019-03-18 | Approved | 2019-05-20 12:04 | 2019-05-21 12:04 | IGATE | 22/05/2019 12:03:32 | SNR1010360 | SNR_Q | GM Technical Procurement | 2019-03-21 | 2019-04-10 | 2019-04-10 | 2019-04-14 | NA | NA | 2019-04-23 | 2019-05-28 | 2019-05-28 | 2019-05-28 | 2019-10-06 | 2019-10-14 | NA | NA | 2019-10-06 | 2019-10-21 | 2019-08-28 | 31.6541 | 38.6321 | 2019-09-09 | 2019-09-02 | ZTRA001 |  |  | 2019-10-17 | 2019-10-17 | Pending HOC | 2019-10-15 | 2019-10-16 | W2-Oct | W2-Oct | Non-Private | Baladiya | Baladiya Tref | NA | 30,000.00 | 15*15 | GF | HO to CW Done | Below BM | Sultan | تم تسليم الموقع
ZUL030 | Macro | Aspiration | Northern | Tabuk | 2020 Scope | الكلية التقنية العالمية بأملج | 25.1757 | 37.276 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-03-17 | 2019-03-18 | Approved | 2019-05-20 14:20 | 2019-05-21 14:20 | IGATE | 22/05/2019 14:19:34 | SNR1010361 | SNR_I | District Support | 2019-03-21 | 2019-04-10 | 2019-05-19 | 2019-05-23 | NA | NA | 2019-04-18 | [19 empty] | Pending HOC | 2019-10-15 | 2019-11-10 | W2-Nov |  | Non-Private | Gov | Technical College in Umluj | NA | 0 | 0 | GF | IBP Not Issued | Above | Hatem | مدن بانتظار الاجتماع - تم اعادة تقديم الطلب بالنظام وتحتاج دراسة سيتم تحديد الاجتماع بعد انتهاء الدراسة
ZWJ018 | Macro | Aspiration | Northern | Tabuk | 2020 Scope | الوجه | 26.2558 | 36.4701 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-17 | 2019-03-18 | Approved | 2019-05-12 17:20 | 2019-05-13 17:20 | IGATE | 14/05/2019 17:20:19 | SNR1010245 | NOBODY | ACCEPTED | 2019-03-21 | 2019-04-10 | 2019-05-19 | 2019-05-23 | NA | NA | 2019-04-15 | 2019-05-09 | 2019-05-09 | 2019-06-18 | 2019-06-20 | 2019-06-30 | NA | NA | 2019-06-20 | 2019-07-17 | 2019-06-25 | 26.2573 | 36.4699 | 2019-06-30 | 2019-07-09 | 407-00-000 |  |  | 2019-07-18 | 2019-07-29 | FDED Not Approved | 2019-12-15 | Done | HOC Done |  | Non-Private | Baladiya | Baladiyah Wajh | NA | 30,000.00 | 15*15 | GF | HO to CW Done | HO Done | Hatem | تم تسليم الموقع
ZWJ020 | Macro | Aspiration | Northern | Tabuk | 2020 Scope | الوجه | 26.2648 | 36.4649 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-17 | 2019-03-18 | Approved | 2019-05-12 17:24 | 2019-05-13 17:24 | IGATE | 14/05/2019 17:24:25 | SNR1010246 | NOBODY | ACCEPTED | 2019-03-21 | 2019-04-10 | 2019-05-19 | 2019-05-23 | NA | NA | 2019-04-15 | 2019-05-09 | 2019-05-09 | 2019-06-18 | 2019-06-20 | 2019-06-30 | NA | NA | 2019-07-01 | 2019-07-17 | 2019-06-25 | 26.2666 | 36.4652 | 2019-06-30 | 2019-07-09 | 407-00-000 |  |  | 2019-07-18 | 2019-07-23 | No Dependency | 2019-12-15 | Done | HOC Done |  | Non-Private | Baladiya | Baladiyah Wajh | NA | 30,000.00 | 15*15 | GF | HO to CW Done | HO Done | Hatem | تم تسليم الموقع
ZTY009 | Macro | Aspiration | Northern | Tabuk | 2020 Scope | تيماء | 27.6203 | 38.5069 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-17 | 2019-03-18 | Approved | 2019-05-02 16:36 | 2019-05-03 16:36 | IGATE | 04/05/2019 16:36:21 | SNR1010054 | SNR_I | District Support | 2019-03-21 | 2019-04-10 | 2019-04-10 | 2019-04-14 | NA | NA | 2019-05-06 | [19 empty] | Pending HOC | 2019-10-15 | 2019-12-05 | W1-Dec |  | Non-Private | Baladiya | Baladiya Tayma | NA | 0 | 0 | GF | IBP Not Issued | Above | Hatem | تم الاجتماع مع الامانة وتم الاتفاق لاصدار العقود خلال اسبوعين
ZSK122 | Macro/Replacement | Aspiration | Northern | Arrar | 2020 Scope-Replacement | الجوف | 29.8214 | 40.1955 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-04-10 | 2019-04-11 | Approved | 2019-07-23 14:17 | 2019-07-24 14:17 | IGATE | 25/07/2019 14:17:21 | SNR1011462 | SNR_Q | GM Technical Procurement | 2019-04-14 | 2019-04-14 | 2019-05-25 | 2019-08-05 | 2019-09-11 | 2019-09-11 | NA | NA | NA | NA | NA | NA | 2019-09-26 | 2019-10-02 | 2019-09-11 | 2019-11-03 | 2019-09-03 | 29.8243 | 40.1919 | 2019-09-04 | 2019-10-09 | 419-00-000 |  |  | 2019-10-17 | 2019-10-17 | Pending HOC | 2019-12-15 | 2019-10-21 | W3-Oct | W2-Oct | Private | Private | احمد الدلبة | 0505415666‬ | 30,000.00 | 20X20 | GF | HO to CW Done | Below BM | Sultan | تم تسليم الموقع بدون رخصة كما تم الاتفاق مع توال
ZTB125 | Macro | Aspiration | Northern | Tabuk | 2019 Scope | تبوك | 28.3598 | 36.5428 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-07-31 | 2019-08-01 | Approved | 2019-07-28 16:57 | 2019-07-29 16:57 | IGATE | 30/07/2019 16:56:37 | SNR1011513 | SNR_I | District Support | 2019-08-04 | 2019-08-04 | 2019-08-04 | 2019-08-05 | 2019-08-26 | 2019-08-26 | NA | NA | NA | NA | NA | NA | [14 empty] | Pending HOC | 2019-12-31 | 2019-10-28 | W4-Oct |  | Private | Private | Private | NA | 20,000.00 | 20x20 | GF | Priv. Contract Not Issued From TAWAL | Below BM | Hatem | منطقة سكنية بانتظار موافقة البلدية على الرخصة
ZBR182 | Macro | Aspiration | Central | Qassim | 2020 Scope | ملك خاص | 26.424 | 43.8896 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-06-30 | 2019-07-01 | Approved | 2019-07-23 15:51 | 2019-07-24 15:51 | IGATE | 21/10/2019 11:59:08 | SNR1012153 | SNR_L | Real Estate Evaluator | 2019-07-04 | 2019-07-04 | 2019-07-28 | 2019-08-05 |  |  | NA | NA | NA | NA | NA | NA | [14 empty] | FBP Not submitted |  | 2019-11-18 | W3-Nov |  | Private | Private | Private | 0505559571 | 0 | 0 | GF | Priv. Contract Not Issued From TAWAL | Below BM | A Sughair | يحتاج اعادة تفاوض مع الملاك
ZBD024 | Macro | Aspiration | Central | Qassim | 2019 Scope | البدايع | 26.055090 | 43.784810 | Huawei | Critical Site | New Location | SHARING/MOBILY | GF | Macro | Doable |  | Approved | 2019-06-15 | 2019-06-16 | Approved | 2019-06-20 14:48 | 2019-06-21 14:48 | IGATE | 22/06/2019 14:48:04 | SNR1010727 | NOBODY | ACCEPTED | 2019-06-19 | 2019-06-19 | 2019-06-23 | 2019-06-27 | 2019-06-26 | 2019-08-05 | NA | NA | NA | NA | NA | NA | 2019-07-11 | 2019-08-20 | 2019-09-04 | 2019-09-15 | 2019-07-13 | 26.054354° | 43.784412° | 2019-07-17 | 2019-09-15 | 603-00-000 |  |  | 2019-09-15 | 2019-09-16 | No Dependency |  | Done | HOC Done |  | Private | Private | محمد الحبردي | 0595515555 | 25,000.00 | 20X20 | GF | HO to CW Done | HO Done | A Sughair | تم تسليم الموقع
ZBK039 | Macro | Aspiration | Central | Qassim | 2019 Scope | بكيرية | 26.1577 | 43.6895 | Huawei | Critical Site | To Remove as SAFE | SHARING/MOBILY | GF | Macro | Doable |  | Approved | 2019-06-15 | 2019-06-16 | Approved | 2019-06-20 15:10 | 2019-06-21 15:10 | IGATE | 22/06/2019 15:10:26 | SNR1010728 | NOBODY | ACCEPTED | 2019-06-19 | 2019-06-19 | 2019-06-23 | 2019-06-27 | 2019-06-26 | 2019-08-05 | NA | NA | NA | NA | NA | NA | 2019-07-11 | 2019-07-18 | 2019-07-18 | 2019-08-05 | 2019-07-15 | 26.157575° | 43.690266° | 2019-07-17 | 2019-08-06 | 606-00-000 |  |  | 2019-08-21 | 2019-08-07 | FBP Not submitted |  | Done | HOC Done |  | Private | Private | عبدالله محمد الحديثي / محمد عبدالرحمن العيد | 0505146485 | 35,000.00 | 20X20 | GF | HO to CW Done | HO Done | A Sughair | تم تسليم الموقع
ZBK041 | Macro | Aspiration | Central | Qassim | 2019 Scope | بكيرية | 26.132 | 43.6703 | Huawei | Critical Site | To Remove as SAFE | SHARING/MOBILY | GF | Macro | Doable |  | Approved | 2019-06-15 | 2019-06-16 | Approved | 2019-06-20 15:18 | 2019-06-21 15:18 | IGATE | 22/06/2019 15:17:50 | SNR1010729 | REQUESTER | REQUESTER | 2019-06-19 | 2019-06-19 | 2019-06-23 | 2019-06-27 | 2019-06-26 |  | NA | NA | NA | NA | NA | NA | 2019-07-18 | 2019-10-20 | 2019-10-20 | [11 empty] | Contract Not Signed |  | 2019-11-14 | W2-Nov |  | Private | Private | عبدالرحمن صالح التركي | 0505146882 | 0 | 20X20 | GF | FBP Not Issued |  | A Sughair
ZBR184 | Macro | Aspiration | Central | Qassim | 2019 Scope | بريدة | 26.341020 | 44.039010 | Huawei | Critical Site | New Location | SHARING/MOBILY | GF | Macro | Doable |  | Approved | 2019-06-16 | 2019-06-17 | Approved | 2019-06-17 18:06 | 2019-06-18 18:06 | IGATE | 19/06/2019 18:06:20 | SNR1010703 | SNR_I | District Support | 2019-06-20 | 2019-06-20 | 2019-06-24 | 2019-06-28 |  |  | NA | NA | NA | NA | NA | NA | [14 empty] | No Dependency |  | 2019-12-26 | W4-Dec |  | Private | Private | عبدالله البديوي | 597277000 | 0 | 0 | GF | Priv. Contract Not Issued From TAWAL |  | A Sughair
ZBR185 | Macro | Aspiration | Central | Qassim | 2019 Scope | صرف الصحي | 26.3928 | 44.0138 | Huawei | Critical Site | To Remove as SAFE | SHARING/MOBILY | GF | Macro | Doable |  | Approved | 2019-06-30 | 2019-07-01 | Approved | 2019-07-09 10:46 | 2019-07-10 10:46 | IGATE | 11/07/2019 10:46:26 | SNR1011249 | SNR_I | District Support | 2019-07-04 | 2019-07-04 | 2019-07-04 | 2019-07-04 | NA | NA | 2019-06-26 | [19 empty] | FBP Not submitted |  | 2019-12-12 | W2-Dec |  | Non-Private | Gov | الصرف الصحي | NA | 0 | 0 | GF | IBP Not Issued |  | A Sughair
ZBR186 | Macro | Aspiration | Central | Qassim | 2019 Scope | بريدة | 26.3218 | 43.7869 | Huawei | Critical Site | To Remove as SAFE | SHARING/MOBILY | GF | Macro | Doable |  | Approved | 2019-06-12 | 2019-06-13 | Rejected |  |  | IGATE | #N/A | #N/A | #N/A | #N/A | 2019-06-16 | 2019-06-16 |  |  |  |  | NA | NA | NA | NA | NA | NA | [14 empty] | No Dependency |  | 2019-12-26 | W4-Dec |  | Private | Private | غانم هلال الشلاحي المطيري | NA | NA | NA | RT | ,ISR IN GAT |  | A Sughair
ZBR188 | Macro | Aspiration | Central | Qassim | 2019 Scope | بريدة | 26.291000 | 43.975300 | Huawei | Critical Site | New Location | SHARING/MOBILY | GF | Macro | Doable |  | Approved | 2019-06-12 | 2019-06-13 | Approved | 2019-06-16 10:39 | 2019-06-17 10:39 | IGATE | 18/06/2019 10:38:51 | SNR1010648 | NOBODY | ACCEPTED | 2019-06-16 | 2019-06-16 | 2019-06-20 | 2019-06-24 | 2019-07-03 | 2019-08-05 | NA | NA | NA | NA | NA | NA | 2019-07-11 | 2019-07-18 | 2019-07-18 |  | 2019-07-13 | 26.291000° | 43.975710° | 2019-07-17 | NA | NA |  |  |  |  | No Dependency |  | 2019-12-26 | W4-Dec |  | Private | Private | عبدالكريم محمد الحجيلان | 503139042 | 30,000.00 | 20X20 | GF | FBP Not Issued |  | A Sughair
ZBR191 | Macro | Aspiration | Central | Qassim | 2019 Scope | بريدة | 26.3115 | 43.999 | Huawei | Critical Site | To Remove as SAFE | SHARING/MOBILY | GF | Macro | Doable |  | Approved | 2019-06-13 | 2019-06-14 | Approved | 2019-06-17 18:18 | 2019-06-18 18:18 | IGATE | 19/06/2019 18:17:44 | SNR1010705 | NOBODY | ACCEPTED | 2019-06-17 | 2019-06-17 | 2019-06-21 | 2019-06-25 | 2019-06-26 | 2019-08-05 | NA | NA | NA | NA | NA | NA | 2019-07-11 | 2019-07-18 | 2019-07-18 |  | 2019-07-13 | 26.310921° | 43.998153° | 2019-07-17 | NA | NA |  |  |  |  | FBP Not Approved |  | 2019-12-26 | W4-Dec |  | Private | Private | عثمان احمد الفايز | 0509996564 | 20,000.00 | 20X20 | GF | FBP Not Issued |  | A Sughair
ZDB149 | Macro | Aspiration | Northern | Tabuk | 2019 Scope | ضبا | 27.2792 | 35.7731 | Huawei | Critical Site | To Remove as SAFE | SHARING/MOBILY | GF | Macro | Doable |  | Approved | 2019-06-12 | 2019-06-13 | Approved | 2019-06-15 10:45 | 2019-06-16 10:45 | IGATE | 17/06/2019 10:44:49 | SNR1010558 | SNR_I | District Support | 2019-06-16 | 2019-06-16 | 2019-06-20 | 2019-06-20 | NA | NA | 2019-07-11 | [19 empty] | FBP Not submitted |  | 2019-12-26 | W4-Dec |  | Non-Private | Baladiya | Baladyah Diba | NA | 0 | 0 | GF | IBP Not Issued |  | Hatem
ZDB150 | Macro | Aspiration | Northern | Tabuk | 2019 Scope | ضبا | 27.372500 | 35.659400 | Huawei | Critical Site | New Location | SHARING/MOBILY | GF | Macro | Doable |  | Approved | 2019-06-12 | 2019-06-13 | Approved | 2019-06-15 10:54 | 2019-06-16 10:54 | IGATE | 17/06/2019 10:54:20 | SNR1010559 | SNR_I | District Support | 2019-06-16 | 2019-06-16 | 2019-06-20 | 2019-06-24 | NA | NA | 2019-06-26 | [19 empty] | FBP Not submitted |  | 2019-12-26 | W4-Dec |  | Non-Private | Baladiya | Baladyah Diba | NA | 0 | 0 | GF | IBP Not Issued |  | Hatem
ZHQ037 | Macro | Aspiration | Northern | Tabuk | 2019 Scope | حقل | 29.273580 | 34.940210 | Huawei | Critical Site | New Location | SHARING/MOBILY | GF | Macro | Doable |  | Approved | 2019-06-14 | 2019-06-15 | Approved | 2019-06-17 19:05 | 2019-06-18 19:05 | IGATE | 19/06/2019 19:04:32 | SNR1010709 | SNR_Q | GM Technical Procurement | 2019-06-18 | 2019-06-18 | 2019-06-22 | 2019-06-26 | 2019-08-27 | 2019-08-27 | NA | NA | NA | NA | NA | NA | 2019-09-29 | 2019-10-27 | 2019-10-27 | 2019-11-09 |  |  |  | 2019-10-20 |  |  |  |  | 2019-11-10 |  | No Dependency |  | 2019-10-31 | W4-Oct |  | Private | Private | أحمد الحبشي / سالم ابو احمد / فؤاد الغريض | 0506602510 | 30,000.00 | 20*20 | GF | HO Not Done |  | Hatem | تم تسليم الموقع
ZHA554 | Macro | Aspiration | Central | Hail | 2019 Scope | حائل | 27.4542 | 41.6316 | Huawei | Critical Site | To Remove as SAFE | SHARING/MOBILY | GF | Macro | Doable |  | Approved | 2019-06-28 | 2019-06-29 | Approved | 2019-06-30 11:37 | 2019-07-01 11:37 | IGATE | 02/07/2019 11:36:55 | SNR1010924 | NOBODY | REJECTED | 2019-07-02 | 2019-07-02 | 2019-07-02 | 2019-07-02 | NA | NA | 2019-07-11 | 2019-09-02 | 2019-09-02 | 2019-09-05 | 2019-10-17 |  | NA | NA | [12 empty] | No Dependency |  | 2019-10-31 | W4-Oct |  | Non-Private | Baladiya | Amanh Hail | NA | 30,000.00 | 4*14 | GF | FBP Not Applied |  | Abdulaziz | تم توقيع العقد من المشتريات وانتظار التوقيع من الأمانة
ZHA555 | Macro | Aspiration | Central | Hail | 2019 Scope | حائل | 27.501020 | 41.674070 | Huawei | Critical Site | New Location | SHARING/MOBILY | GF | Macro | Doable |  | Approved | 2019-06-09 | 2019-06-10 | Approved | 2019-06-15 11:43 | 2019-06-16 11:43 | IGATE | 17/06/2019 11:43:03 | SNR1010564 | SNR_I | District Support | 2019-06-13 | 2019-06-13 | 2019-06-17 | 2019-06-21 | NA | NA | 2019-06-26 | [19 empty] | No Dependency |  | 2019-12-26 | W4-Dec |  | Non-Private | Baladiya | Amanh Hail | NA | 0 | 0 | GF | IBP Not Issued |  | Abdulaziz
ZHA556 | Macro | Aspiration | Central | Hail | 2019 Scope | حائل | 27.4246 | 41.74 | Huawei | Critical Site | To Remove as SAFE | SHARING/MOBILY | GF | Macro | Doable |  | Approved | 2019-06-09 | 2019-06-10 | Approved | 2019-06-16 11:57 | 2019-06-17 11:57 | IGATE | 18/06/2019 11:56:31 | SNR1010666 | SNR_I | District Support | 2019-06-13 | 2019-06-13 | 2019-06-17 | 2019-06-21 | NA | NA | 2019-06-26 | [19 empty] | No Dependency |  | 2019-12-26 | W4-Dec |  | Non-Private | Baladiya | Amanh Hail | NA | 0 | 0 | GF | IBP Not Issued |  | Abdulaziz
ZJB222 | Macro | Aspiration | Eastern | Jubail | 2020 Scope | قاعدة الملك عبدالعزيز البحرية بالجبيل | 27.0031 | 49.3948 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-04-06 | 2019-04-07 | Approved | 2019-07-09 15:44 | 2019-07-10 15:44 | IGATE | 11/07/2019 15:44:18 | SNR1011273 | SNR_I | District Support | 2019-04-10 | 2019-07-04 | 2019-07-04 | 2019-07-04 | NA | NA | 2019-04-15 | [19 empty] | Pending HOC | 2019-12-29 | 2019-11-20 | W3-Nov |  | Non-Private | Gov | NB (Navel Base) | NA | 0 | 0 | GF | IBP Not Issued | Above | Faris | بانتظار العقد من البحرية - (الموقع يحتاج موافقة الهيئة الملكية ورافضه تقديمها للبحرية )
ZJB223 | Macro | Aspiration | Eastern | Jubail | 2020 Scope | ملك خاص | 26.8821 | 49.4669 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-04-06 | 2019-04-07 | Approved | 2019-05-19 17:09 | 2019-05-20 17:09 | IGATE | 21/05/2019 17:08:45 | SNR1010313 | NOBODY | ACCEPTED | 2019-04-10 | 2019-04-10 | 2019-04-23 | 2019-06-17 | 2019-07-11 | 2019-08-26 | NA | NA | NA | NA | NA | NA | 2019-09-04 | 2019-09-11 | 2019-09-11 | 2019-10-31 | 2019-09-07 | 26.8814 | 49.4645 | 2019-09-09 | 2019-10-11 | ZJB987 |  |  | 2019-10-17 | 2019-10-17 | Pending HOC | 2019-12-29 | 2019-10-20 | W3-Oct | W2-Oct | Private | Private | حسن راشد حسن الخاطر / نبأ القحطاني | 0555901239 | 25,000.00 | 20 * 20 | GF | HO to CW Done | Below BM | Faris | تم تسليم الموقع بدون رخصة كما تم الاتفاق مع توال
ZJB229 | Macro | Aspiration | Eastern | Jubail | 2020 Scope | ارامكو بالمنطقة الشرقية | 27.1068 | 49.0316 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-03-16 | 2019-03-17 | Approved | 2019-05-23 14:53 | 2019-05-24 14:53 | IGATE | 25/05/2019 14:53:08 | SNR1010383 | SNR_I | District Support | 2019-03-20 | 2019-04-10 | 2019-04-10 | 2019-05-01 | NA | NA | 2019-06-18 | [19 empty] | Pending HOC | 2019-11-15 | 2019-11-10 | W2-Nov |  | Non-Private | Gov | Aramco | NA | 0 | 0 | GF | IBP Not Issued | Above | Ali | تم تقديم خطاب رد لارامكو - بانتظار اصدار العقد من ارامكو
ZJB234 | Macro | Aspiration | Eastern | Jubail | 2020 Scope | ارامكو بالمنطقة الشرقية | 27.0918 | 49.0887 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-03-16 | 2019-03-17 | Approved | 2019-05-25 11:37 | 2019-05-26 11:37 | IGATE | 27/05/2019 11:37:17 | SNR1010414 | SNR_I | District Support | 2019-03-20 | 2019-04-10 | 2019-04-10 | 2019-05-01 | NA | NA | 2019-06-18 | [19 empty] | Pending HOC | 2019-11-15 | 2019-11-10 | W2-Nov |  | Non-Private | Gov | Aramco | NA | 0 | 0 | GF | IBP Not Issued | Above | Ali | تم تقديم خطاب رد لارامكو - بانتظار اصدار العقد من ارامكو
ZJB210 | Macro | Aspiration | Eastern | Jubail | 2020 Scope | الجبيل | 26.8621 | 49.7774 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-17 | 2019-03-18 | Approved | 2019-05-19 19:23 | 2019-05-20 19:23 | IGATE | 21/05/2019 19:23:27 | SNR1010322 | SNR_I | District Support | 2019-03-21 | 2019-04-10 | 2019-04-10 | 2019-04-10 | NA | NA | 2019-04-14 | [12 empty] | 2019-10-20 | [6 empty] | Pending HOC | 2019-09-15 | 2019-11-28 | W4-Nov |  | Non-Private | Baladiya | Baladiya Jubail | NA | 0 | 0 | GF | IBP Not Issued | Above | Faris | بانتظار توقيع المالية على محضر التقدير - واصدار العقد
ZKF067 | Macro | Aspiration | Eastern | Jubail | 2020 Scope | الخفجي | 28.3868 | 48.4504 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-10 | 2019-03-11 | Approved | 2019-05-03 11:00 | 2019-05-04 11:00 | IGATE | 05/05/2019 10:59:45 | SNR1010059 | SNR_O | Technical Procurement Section Manager | 2019-03-14 | 2019-04-10 | 2019-04-10 | 2019-04-14 | NA | NA | 2019-04-15 | 2019-10-09 | 2019-10-09 | 2019-10-15 | 2019-10-17 |  | NA | NA | [10 empty] | 2019-10-22 | 2019-10-22 | Pending HOC | 2019-09-15 | 2019-11-17 | W3-Nov |  | Non-Private | Baladiya | Baladiya Khafji | NA | 0 | 0 | GF | FBP Not Applied | Above | Faris | تم تسليم الموقع بدون رخصة كما تم الاتفاق مع توال
ZKF072 | Macro | Aspiration | Eastern | Jubail | 2020 Scope | الخفجي | 28.3936 | 48.4566 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-10 | 2019-03-11 | Approved | 2019-05-03 11:30 | 2019-05-04 11:30 | IGATE | 05/05/2019 11:30:16 | SNR1010061 | SNR_I | District Support | 2019-03-14 | 2019-04-10 | 2019-04-10 | 2019-04-14 | NA | NA | 2019-05-13 | 2019-10-09 | 2019-10-09 | [17 empty] | Pending HOC | 2019-12-29 | 2019-11-17 | W3-Nov |  | Non-Private | Baladiya | Baladiya Khafji | NA | 0 | 0 | GF | Contract Not Submitted to TAWAL | Above | Faris | بانتظار العقود من البلدية
ZKF078 | Macro | Aspiration | Eastern | Jubail | 2020 Scope | الخفجي | 28.4856 | 48.4799 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-03-10 | 2019-03-11 | Approved | 2019-05-25 15:45 | 2019-05-26 15:45 | IGATE | 27/05/2019 15:44:38 | SNR1010426 | SNR_O | Technical Procurement Section Manager | 2019-03-14 | 2019-04-10 | 2019-04-10 | 2019-04-10 | NA | NA | 2019-04-15 | 2019-10-09 | 2019-10-09 | 2019-10-15 | 2019-10-17 |  | NA | NA | [10 empty] | 2019-10-22 | 2019-10-22 | Pending HOC | 2019-09-15 | 2019-11-17 | W3-Nov |  | Non-Private | Baladiya | Baladiya Khafji | NA | 0 | 0 | GF | FBP Not Applied | Above | Faris | تم تسليم الموقع بدون رخصة كما تم الاتفاق مع توال
ZJB101 | Macro | Aspiration | Eastern | Jubail | 2020 Scope | الهيئة الملكية بالجبيل | 27.1482 | 49.5352 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-03-05 | 2019-03-06 | Approved | 2019-05-02 15:19 | 2019-05-03 15:19 | IGATE | 04/05/2019 15:18:59 | SNR1010046 | SNR_F | District Director | 2019-03-09 | 2019-04-10 | 2019-04-10 | 2019-04-14 | NA | NA | 2019-05-07 | [19 empty] | Pending HOC | 2019-11-15 | 2019-12-05 | W1-Dec |  | Non-Private | Gov | RC | NA | 0 | 0 | GF | IBP Not Issued | Below BM | Faris | تم رفض المواقع المقترحة من الهيئة الملكية
ZJB107 | Macro | Aspiration | Eastern | Jubail | 2020 Scope | الهيئة الملكية بالجبيل | 27.1677 | 49.5168 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-03-05 | 2019-03-06 | Approved | 2019-05-23 14:45 | 2019-05-24 14:45 | IGATE | 25/05/2019 14:49:01 | SNR1010382 | REQUESTER | REQUESTER | 2019-03-09 | 2019-04-10 | 2019-05-25 | 2019-06-17 | NA | NA | 2019-05-07 | [19 empty] | Pending HOC | 2019-11-15 | 2019-12-05 | W1-Dec |  | Non-Private | Gov | RC | 0 | 0 | 0 | GF | IBP Not Issued | Below BM | Faris | تم رفض المواقع المقترحة من الهيئة الملكية
ZJB108 | Macro | Aspiration | Eastern | Jubail | 2020 Scope | الهيئة الملكية بالجبيل | 27.173 | 49.5237 | Huawei | New Site | New Location | NA | NA | Macro | Long process |  | Approved | 2019-03-05 | 2019-03-06 | Approved | 2019-05-02 15:37 | 2019-05-03 15:37 | IGATE | 29/10/2019 17:13:39 | SNR1012255 | SNR_D | Vendor SA | 2019-03-09 | 2019-04-10 | 2019-04-10 | 2019-04-14 | NA | NA | 2019-05-07 | [19 empty] | Pending HOC | 2019-11-15 | 2019-12-05 | W1-Dec |  | Non-Private | Gov | RC | NA | 0 | 0 | GF | IBP Not Issued | Below BM | Faris | تم رفض المواقع المقترحة من الهيئة الملكية
ZJB805 | Macro | Aspiration | Eastern | Jubail | 2019 Scope | الهيئة الملكية | 27.1678 | 49.5406 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-06-30 | 2019-07-01 | Approved | 2019-08-05 12:39 | 2019-08-06 12:39 | IGATE | 07/08/2019 12:39:15 | SNR1011603 | SNR_I | District Support | 2019-07-04 | 2019-07-04 | 2019-09-03 | 2019-09-03 | NA | NA | 2019-08-05 | [19 empty] | Pending HOC |  | 2019-12-20 | W3-Dec |  | Non-Private | Gov | RC | NA | 0 | 0 | GF | IBP Not Issued | Below BM | Faris | تم رفض المواقع المقترحة من الهيئة الملكية
ZJB854 | Macro | Aspiration | Eastern | Jubail | 2019 Scope | ملك خاص | 26.9763 | 49.6622 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-08-03 | 2019-08-04 | Approved | 2019-08-05 13:29 | 2019-08-06 13:29 | IGATE | 07/08/2019 13:28:49 | SNR1011607 | SNR_I | District Support | 2019-08-07 | 2019-08-07 | 2019-08-07 | 2019-09-03 |  |  | NA | NA | NA | NA | NA | NA | [14 empty] | Pending HOC |  | 2019-12-25 | W4-Dec |  | Private | Private | مجمع قرية الجود(حمدي يونس) | 0113641115/0133641676 | 0 | 0 | GF | Priv. Contract Not Issued From TAWAL | Below BM | Faris | تم رفض التاجير من مجمع الجود (سيتم اعادة التفاوض معهم او الحصول على رفض بخطاب رسمي )
ZJB861 | Macro | Aspiration | Eastern | Jubail | 2019 Scope | الهيئة الملكية | 27.1373 | 49.5364 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-07-24 | 2019-07-25 | Approved | 2019-07-23 15:10 | 2019-07-24 15:10 | IGATE | 25/07/2019 15:10:02 | SNR1011469 | SNR_I | District Support | 2019-07-28 | 2019-07-28 | 2019-07-28 | 2019-08-05 | NA | NA | 2019-08-05 | [19 empty] | Pending HOC |  | 2019-12-25 | W4-Dec |  | Non-Private | Gov | RC | NA | 0 | 0 | GF | IBP Not Issued | Below BM | Faris | تم رفض المواقع المقترحة من الهيئة الملكية
ZBH661 | Macro | Aspiration | Southern | Baha | 2020 Scope | العقيق | 20.2448 | 41.6821 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-06-20 | 2019-06-21 | Approved | 2019-07-20 14:09 | 2019-07-21 14:09 | IGATE | 22/07/2019 14:09:10 | SNR1011417 | REQUESTER | REQUESTER | 2019-06-24 | 2019-06-24 |  |  | NA | NA | 2019-07-11 | 2019-07-11 | [18 empty] | Pending HOC |  | 2019-11-14 | W2-Nov |  | Non-Private | Baladiya | Al Aqeq Baladiyah | 0 | 0 | 0 | GF | ISR Not Approved By RF | Above | Ali Asiri | no deed, Searching for Private can issue FBP
ZJZ172 | Macro | Aspiration | Southern | Jizan | 2019 Scope | جازان | 16.9509 | 42.5619 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-06-20 | 2019-06-21 | Approved | 2019-07-01 10:56 | 2019-07-02 10:56 | IGATE | 03/07/2019 10:56:03 | SNR1010972 | SNR_O | Technical Procurement Section Manager | 2019-06-24 | 2019-06-24 | 2019-06-24 | 2019-06-24 | NA | NA | 2019-06-09 | 2019-09-23 | 2019-09-23 | 2019-10-30 | 2019-10-30 | [5 empty] | 2019-10-08 | 16.9508 | 42.5618 | 2019-10-20 | 2019-10-22 | ZJZA001 |  |  | 2019-10-30 | 2019-11-03 | FDED Not Approved |  | 2019-11-14 | W2-Nov |  | Non-Private | Baladiya | Jazan Amanah | NA | 0 | 17*17 | GF | Priv. Contract Not Issued From TAWAL | Above | Fahad Allam | تم تسليم الموقع بدون رخصة كما تم الاتفاق مع توال
ZJZ376 | Macro | Aspiration | Southern | Jizan | 2019 Scope | أماننة جازان | 17.7205 | 42.2534 | Huawei | New Site | New Location | NA | NA | Macro | Doable | On Hold by STC RF | Approved | 2019-06-30 | 2019-07-01 | Approved | 2019-08-04 19:33 | 2019-08-05 19:33 | IGATE | 06/08/2019 19:33:21 | SNR1011598 | SNR_I | District Support | 2019-07-04 | 2019-07-04 | 2019-09-03 | 2019-09-03 |  |  | 2019-08-01 | [19 empty] | FDED Not Approved |  | 2019-11-14 | W2-Nov |  | Non-Private | Baladiya | Jazan Amanah | 0504577009 | 0 | 0 | GF | IBP Not Issued | Above | Fahad Allam | no deed
ZTB437 | Macro/Replacement | Aspiration | Northern | Tabuk | 2019 Scope-Replacement | تبوك | 28.3864 | 36.534 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-07-31 | 2019-08-01 | Approved | 2019-07-01 11:28 | 2019-07-02 11:28 | IGATE | 03/07/2019 11:27:51 | SNR1010981 | SNR_O | Technical Procurement Section Manager | 2019-08-04 | 2019-08-04 | 2019-08-04 | 2019-08-04 | 2019-08-26 | 2019-08-26 | NA | NA | NA | NA | NA | NA | 2019-10-30 | 2019-11-07 | 2019-10-30 | 2019-11-07 | [8 empty] | 2019-10-30 | 2019-11-03 | Pending HOC |  | 2019-10-21 | W3-Oct |  | Private | Private | Private | 0505372647 | 40,000.00 | سطح مبنى | GF | HO to CW Done | Below BM | Hatem | تم تسليم الموقع بدون رخصة كما تم الاتفاق مع توال
ZUZ060 | Macro | Aspiration | Central | Qassim | 2019 Scope | وزارة الاسكان | 26.0592 | 44.0949 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-06-27 | 2019-06-28 | Approved | 2019-06-23 18:10 | 2019-06-24 18:10 | IGATE | 25/06/2019 18:09:37 | SNR1010831 | SNR_I | District Support | 2019-07-01 | 2019-07-01 | 2019-07-01 | 2019-07-01 | NA | NA | 2019-07-02 | [19 empty] | Pending HOC |  | 2019-11-28 | W4-Nov |  | Non-Private | Gov | MOH | NA | 0 | 0 | GF | IBP Not Issued | Above | A Sughair | بانتظار رد من وزارة الاسكان
CWH076 | Macro | Aspiration | COW | COW | 2020 Scope | COW | 26.385 | 50.1285 | Huawei | COW newly Added | New Location |  |  | COW | Doable |  | Approved | 2019-06-30 | 2019-07-01 | Approved | 2019-07-05 18:23 | 2019-07-01 | Non IGATE | NA | NA | NA | NA | 2019-07-04 | 2019-07-04 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | NA | NA | 2019-07-08 | 2019-07-08 |  |  |  | 2019-07-08 |  |  |  |  | 2019-07-08 | 2019-07-08 | FDED Not Approved |  | Done | HOC Done |  | Non-Private | COW |  | NA | NA | NA | COW | HO to CW Done | HO Done | Done | تم تسليم الموقع
CWH077 | Macro | Aspiration | COW | COW | 2020 Scope | COW | 26.385 | 50.1285 | Huawei | COW newly Added | New Location |  |  | COW | Doable |  | Approved | 2019-06-30 | 2019-07-01 | Approved | 2019-07-05 18:23 | 2019-07-01 | Non IGATE | NA | NA | NA | NA | 2019-07-04 | 2019-07-04 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | NA | NA | 2019-07-08 | 2019-07-08 |  |  |  | 2019-07-08 |  |  |  |  | 2019-07-08 | 2019-07-08 | FDED Not Approved |  | Done | HOC Done |  | Non-Private | COW |  | NA | NA | NA | COW | HO to CW Done | HO Done | Done | تم تسليم الموقع
CWH078 | Macro | Aspiration | COW | COW | 2020 Scope | COW | 26.385 | 50.1285 | Huawei | COW newly Added | New Location |  |  | COW | Doable |  | Approved | 2019-06-30 | 2019-07-01 | Approved | 2019-07-05 18:23 | 2019-07-01 | Non IGATE | NA | NA | NA | NA | 2019-07-04 | 2019-07-04 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | NA | NA | 2019-07-08 | 2019-07-08 |  |  |  | 2019-07-08 |  |  |  |  | 2019-07-08 | 2019-07-08 | No Dependency |  | Done | HOC Done |  | Non-Private | COW |  | NA | NA | NA | COW | HO to CW Done | HO Done | Done | تم تسليم الموقع
CWH079 | Macro | Aspiration | COW | COW | 2020 Scope | COW | 26.385 | 50.1285 | Huawei | COW newly Added | New Location |  |  | COW | Doable |  | Approved | 2019-06-30 | 2019-07-01 | Approved | 2019-07-05 18:23 | 2019-07-01 | Non IGATE | NA | NA | NA | NA | 2019-07-04 | 2019-07-04 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | NA | NA | 2019-07-08 | 2019-07-08 |  |  |  | 2019-07-08 |  |  |  |  | 2019-07-08 | 2019-07-08 | FDED Not Approved |  | Done | HOC Done |  | Non-Private | COW |  | NA | NA | NA | COW | HO to CW Done | HO Done | Done | تم تسليم الموقع
CWH080 | Macro | Aspiration | COW | COW | 2020 Scope | COW | 26.385 | 50.1285 | Huawei | COW newly Added | New Location |  |  | COW | Doable |  | Approved | 2019-06-30 | 2019-07-01 | Approved | 2019-06-30 | 2019-07-01 | Non IGATE | NA | NA | NA | NA | 2019-07-04 | 2019-07-04 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | NA | NA | 2019-07-08 | 2019-07-08 |  |  |  | 2019-07-08 |  |  |  |  | 2019-07-08 | 2019-07-08 | No Dependency |  | Done | HOC Done |  | Non-Private | COW |  | NA | NA | NA | COW | HO to CW Done | HO Done | Done | تم تسليم الموقع
CWH081 | Macro | Aspiration | COW | COW | 2020 Scope | COW | 26.385 | 50.1285 | Huawei | COW newly Added | New Location |  |  | COW | Doable |  | Approved | 2019-06-30 | 2019-07-01 | Approved | 2019-07-05 18:23 | 2019-07-01 | Non IGATE | NA | NA | NA | NA | 2019-07-04 | 2019-07-04 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | NA | NA | 2019-07-08 | 2019-07-08 |  |  |  | 2019-07-08 |  |  |  |  | 2019-07-08 | 2019-07-08 | FDED Not Approved |  | Done | HOC Done |  | Non-Private | COW |  | NA | NA | NA | COW | HO to CW Done | HO Done | Done | تم تسليم الموقع
CWH082 | Macro | Aspiration | COW | COW | 2020 Scope | COW | 26.385 | 50.1285 | Huawei | COW newly Added | New Location |  |  | COW | Doable |  | Approved | 2019-06-30 | 2019-07-01 | Approved | 2019-07-05 18:23 | 2019-07-01 | Non IGATE | NA | NA | NA | NA | 2019-07-04 | 2019-07-04 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | NA | NA | 2019-07-08 | 2019-07-08 |  |  |  | 2019-07-08 |  |  |  |  | 2019-07-08 | 2019-07-08 | FDED Not Approved |  | Done | HOC Done |  | Non-Private | COW |  | NA | NA | NA | COW | HO to CW Done | HO Done | Done | تم تسليم الموقع
CWH083 | Macro | Aspiration | COW | COW | 2020 Scope | COW | 26.385 | 50.1285 | Huawei | COW newly Added | New Location |  |  | COW | Doable |  | Approved | 2019-06-30 | 2019-07-01 | Approved | 2019-07-05 18:23 | 2019-07-01 | Non IGATE | NA | NA | NA | NA | 2019-07-04 | 2019-07-04 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | NA | NA | 2019-07-08 | 2019-07-08 |  |  |  | 2019-07-08 |  |  |  |  | 2019-07-08 | 2019-07-08 | No Dependency |  | Done | HOC Done |  | Non-Private | COW |  | NA | NA | NA | COW | HO to CW Done | HO Done | Done | تم تسليم الموقع
CWH084 | Macro | Aspiration | COW | COW | 2020 Scope | COW | 26.385 | 50.1285 | Huawei | COW newly Added | New Location |  |  | COW | Doable |  | Approved | 2019-06-30 | 2019-07-01 | Approved | 2019-07-05 18:23 | 2019-07-01 | Non IGATE | NA | NA | NA | NA | 2019-07-04 | 2019-07-04 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | NA | NA | 2019-07-08 | 2019-07-08 |  |  |  | 2019-07-08 |  |  |  |  | 2019-07-08 | 2019-07-08 | FDED Not Approved |  | Done | HOC Done |  | Non-Private | COW |  | NA | NA | NA | COW | HO to CW Done | HO Done | Done | تم تسليم الموقع
CWH085 | Macro | Aspiration | COW | COW | 2020 Scope | COW | 26.385 | 50.1285 | Huawei | COW newly Added | New Location |  |  | COW | Doable |  | Approved | 2019-06-30 | 2019-07-01 | Approved | 2019-07-05 18:23 | 2019-07-01 | Non IGATE | NA | NA | NA | NA | 2019-07-04 | 2019-07-04 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | NA | NA | 2019-07-08 | 2019-07-08 |  |  |  | 2019-07-08 |  |  |  |  | 2019-07-08 | 2019-07-08 | FDED Not Approved |  | Done | HOC Done |  | Non-Private | COW |  | NA | NA | NA | COW | HO to CW Done | HO Done | Done | تم تسليم الموقع
CWH086 | Macro | Aspiration | COW | COW | 2020 Scope | COW | 26.385 | 50.1285 | Huawei | COW newly Added | New Location |  |  | COW | Doable |  | Approved | 2019-06-30 | 2019-07-01 | Approved | 2019-07-05 18:23 | 2019-07-01 | Non IGATE | NA | NA | NA | NA | 2019-07-04 | 2019-07-04 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | NA | NA | 2019-07-08 | 2019-07-08 |  |  |  | 2019-07-08 |  |  |  |  | 2019-07-08 | 2019-07-08 | FDED Not Approved |  | Done | HOC Done |  | Non-Private | COW |  | NA | NA | NA | COW | HO to CW Done | HO Done | Done | تم تسليم الموقع
CWH087 | Macro | Aspiration | COW | COW | 2020 Scope | COW | 26.385 | 50.1285 | Huawei | COW newly Added | New Location |  |  | COW | Doable |  | Approved | 2019-06-30 | 2019-07-01 | Approved | 2019-07-05 18:23 | 2019-07-01 | Non IGATE | NA | NA | NA | NA | 2019-07-04 | 2019-07-04 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | NA | NA | 2019-07-08 | 2019-07-08 |  |  |  | 2019-07-08 |  |  |  |  | 2019-07-08 | 2019-07-08 | FDED Not Approved |  | Done | HOC Done |  | Non-Private | COW |  | NA | NA | NA | COW | HO to CW Done | HO Done | Done | تم تسليم الموقع
CWH088 | Macro | Aspiration | COW | COW | 2020 Scope | COW | 26.385 | 50.1285 | Huawei | COW newly Added | New Location |  |  | COW | Doable |  | Approved | 2019-06-30 | 2019-07-01 | Approved | 2019-07-05 18:23 | 2019-07-01 | Non IGATE | NA | NA | NA | NA | 2019-07-04 | 2019-07-04 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | NA | NA | 2019-07-08 | 2019-07-08 |  |  |  | 2019-07-08 |  |  |  |  | 2019-07-08 | 2019-07-08 | No Dependency |  | Done | HOC Done |  | Non-Private | COW |  | NA | NA | NA | COW | HO to CW Done | HO Done | Done | تم تسليم الموقع
CWH089 | Macro | Aspiration | COW | COW | 2020 Scope | COW | 26.385 | 50.1285 | Huawei | COW newly Added | New Location |  |  | COW | Doable |  | Approved | 2019-06-30 | 2019-07-01 | Approved | 2019-07-05 18:23 | 2019-07-01 | Non IGATE | NA | NA | NA | NA | 2019-07-04 | 2019-07-04 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | NA | NA | 2019-07-08 | 2019-07-08 |  |  |  | 2019-07-08 |  |  |  |  | 2019-07-08 | 2019-07-08 | No Dependency |  | Done | HOC Done |  | Non-Private | COW |  | NA | NA | NA | COW | HO to CW Done | HO Done | Done | تم تسليم الموقع
CWH090 | Macro | Aspiration | COW | COW | 2020 Scope | COW | 26.385 | 50.1285 | Huawei | COW newly Added | New Location |  |  | COW | Doable |  | Approved | 2019-06-30 | 2019-07-01 | Approved | 2019-07-05 18:23 | 2019-07-01 | Non IGATE | NA | NA | NA | NA | 2019-07-04 | 2019-07-04 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | NA | NA | 2019-07-08 | 2019-07-08 |  |  |  | 2019-07-08 |  |  |  |  | 2019-07-08 | 2019-07-08 | FDED Not Approved |  | Done | HOC Done |  | Non-Private | COW |  | NA | NA | NA | COW | HO to CW Done | HO Done | Done | تم تسليم الموقع
CWH091 | Macro | Aspiration | COW | COW | 2020 Scope | COW | 26.385 | 50.1285 | Huawei | COW newly Added | New Location |  |  | COW | Doable |  | Approved | 2019-06-30 | 2019-07-01 | Approved | 2019-07-05 18:23 | 2019-07-01 | Non IGATE | NA | NA | NA | NA | 2019-07-04 | 2019-07-04 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | NA | NA | 2019-07-08 | 2019-07-08 |  |  |  | 2019-07-08 |  |  |  |  | 2019-07-08 | 2019-07-08 | FDED Not Approved |  | Done | HOC Done |  | Non-Private | COW |  | NA | NA | NA | COW | HO to CW Done | HO Done | Done | تم تسليم الموقع
CWH092 | Macro | Aspiration | COW | COW | 2020 Scope | COW | 26.385 | 50.1285 | Huawei | COW newly Added | New Location |  |  | COW | Doable |  | Approved | 2019-06-30 | 2019-07-01 | Approved | 2019-07-05 18:23 | 2019-07-01 | Non IGATE | NA | NA | NA | NA | 2019-07-04 | 2019-07-04 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | NA | NA | 2019-07-08 | 2019-07-08 |  |  |  | 2019-07-08 |  |  |  |  | 2019-07-08 | 2019-07-08 | FDED Not Approved |  | Done | HOC Done |  | Non-Private | COW |  | NA | NA | NA | COW | HO to CW Done | HO Done | Done | تم تسليم الموقع
CWH093 | Macro | Aspiration | COW | COW | 2020 Scope | COW | 26.385 | 50.1285 | Huawei | COW newly Added | New Location |  |  | COW | Doable |  | Approved | 2019-06-30 | 2019-07-01 | Approved | 2019-07-05 18:23 | 2019-07-01 | Non IGATE | NA | NA | NA | NA | 2019-07-04 | 2019-07-04 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | NA | NA | 2019-07-08 | 2019-07-08 |  |  |  | 2019-07-08 |  |  |  |  | 2019-07-08 | 2019-07-08 | FDED Not Approved |  | Done | HOC Done |  | Non-Private | COW |  | NA | NA | NA | COW | HO to CW Done | HO Done | Done | تم تسليم الموقع
CWH094 | Macro | Aspiration | COW | COW | 2020 Scope | COW | 26.385 | 50.1285 | Huawei | COW newly Added | New Location |  |  | COW | Doable |  | Approved | 2019-06-30 | 2019-07-01 | Approved | 2019-06-30 | 2019-07-01 | Non IGATE | NA | NA | NA | NA | 2019-07-04 | 2019-07-04 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | NA | NA | 2019-07-08 | 2019-07-08 |  |  |  | 2019-07-08 |  |  |  |  | 2019-07-08 | 2019-07-08 | FDED Not Approved |  | Done | HOC Done |  | Non-Private | COW |  | NA | NA | NA | COW | HO to CW Done | HO Done | Done | تم تسليم الموقع
CWH095 | Macro | Aspiration | COW | COW | 2020 Scope | COW | 26.385 | 50.1285 | Huawei | COW newly Added | New Location |  |  | COW | Doable |  | Approved | 2019-06-30 | 2019-07-01 | Approved | 2019-07-05 18:23 | 2019-07-01 | Non IGATE | NA | NA | NA | NA | 2019-07-04 | 2019-07-04 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | 2019-07-08 | NA | NA | 2019-07-08 | 2019-07-08 |  |  |  | 2019-07-08 |  |  |  |  | 2019-07-08 | 2019-07-08 | FDED Not Approved |  | Done | HOC Done |  | Non-Private | COW |  | NA | NA | NA | COW | HO to CW Done | HO Done | Done | تم تسليم الموقع
PKU138 | Macro/Replacement | Aspiration | Eastern | Dammam | 2020 Scope | الدمام | 26.3978 | 50.0266 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-06-30 | 2019-07-01 | Approved | 2019-08-05 13:43 | 2019-08-06 13:43 | IGATE | 07/08/2019 13:42:36 | SNR1011609 | SNR_I | District Support | 2019-07-04 | 2019-07-04 | 2019-09-03 | 2019-09-03 |  |  | 2019-09-04 | [19 empty] | Pending HOC |  | 2019-11-10 | W2-Nov |  | Non-Private | Baladiya | Western Dammam | NA | 0 | 0 | GF | IBP Not Issued | Above | Ali | بانتظار العقد من البلدية - يحتاج اسبوع
ZJB279 | Macro/Replacement | Aspiration | Eastern | Jubail | 2019 Scope-Replacement | الهيئة الملكية | 27.499 | 49.192 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-06-27 | 2019-06-28 | Approved | 2019-06-24 18:37 | 2019-06-25 18:37 | IGATE | 26/06/2019 18:36:49 | SNR1010857 | SNR_I | District Support | 2019-07-01 | 2019-07-01 | 2019-07-01 | 2019-07-01 | NA | NA | 2019-07-04 | [12 empty] | 2019-10-20 | [6 empty] | Pending HOC |  | 2019-12-25 | W4-Dec |  | Non-Private | Gov | RC | NA | 0 | 0 | GF | IBP Not Issued | Below BM | Faris | عقد الموقع المتواجد ينتهي ب 2020
ZJZ061 | Macro/Replacement | Aspiration | Southern | Jizan | 2019 Scope-Replacement | ملك خاص | 17.3727 | 42.5342 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-06-30 | 2019-07-01 | Approved | 2019-08-05 15:10 | 2019-08-06 15:10 | IGATE | 07/08/2019 15:10:07 | SNR1011611 | SNR_O | Technical Procurement Section Manager | 2019-07-04 | 2019-07-04 |  |  |  |  | NA | NA | NA | NA | NA | NA | 2019-11-06 | 2019-11-06 | 2019-10-23 | 2019-10-24 | 2019-10-17 | 17.3729 | 42.5333 | 2019-10-17 | 2019-10-20 | 707-00-000 |  |  | 2019-11-06 |  | FDED Not Approved |  | 2019-11-14 | W2-Nov |  | Private | Private | Private | 0 | 0 | 0 | GF | ISR Not Approved By RF | Below BM | Fahad Allam | تم تسليم الموقع
ZDB151 | Macro | Aspiration | Northern | Tabuk | 2020 Scope | مطار خليج نيوم | 27.9177 | 35.2912 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-06-30 | 2019-07-01 | Approved | 2019-07-14 14:36 | 2019-07-15 14:36 | IGATE | 16/07/2019 14:35:44 | SNR1011355 | SNR_O | Technical Procurement Section Manager | 2019-07-04 | 2019-07-04 | 2019-07-04 | 2019-08-05 | NA | NA | 2019-08-05 | 2019-10-01 | 2019-10-01 | 2019-10-01 | [9 empty] | 2019-10-20 | [6 empty] | FBP Not submitted |  | 2019-10-28 | W4-Oct |  | Non-Private | Gov | Neum Airport | NA | 65,000.00 | 10*10 | GF | Contract Not Signed by TAWAL | Above | Hatem | بانتظار توقيع العقد من المشتريات - وسيتم ارسال ايميل بالملاحظات بالعقد لهيئة الطيران المدني
ZDM194 | Macro/Replacement | Aspiration | Eastern | Dammam | 2020 Scope-Replacement | ملك خاص | 26.5914 | 41.74 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-07-21 | 2019-07-22 | Approved | 2019-08-22 | 2019-10-02 | IGATE | 29/10/2019 17:26:16 | SNR1012258 | SNR_F | District Director | 2019-07-25 | [5 empty] | 2019-09-04 | 2019-11-10 | 2019-11-10 | 2019-11-14 | 2019-11-14 |  | NA | NA | 2019-11-17 | [9 empty] | 2019-11-14 |  | FBP Not submitted |  | 2019-11-15 | W2-Nov |  | Non-Private | Baladiya | Qateef Baladiyah | NA | NA | NA | GF | ISR Not Sub to RF | Below BM | Ali | انتظار العقد من البلدية للعربة المتحركة
ZJZ173 | Macro | Aspiration | Southern | Jizan | 2019 Scope | وزارة الصحة | 16.8054 | 42.6548 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-07-24 | 2019-07-25 | Approved | 2019-08-05 15:36 | 2019-08-06 15:36 | IGATE | 07/08/2019 15:35:32 | SNR1011613 | SNR_I | District Support | 2019-07-28 | 2019-08-07 | 2019-08-22 | 2019-09-03 |  |  | 2019-08-01 | [19 empty] | FDED Not Approved |  | 2019-11-28 | W4-Nov |  | Non-Private | Gov | Ministry of health | NA | 0 | 0 | GF | IBP Not Issued | Below BM | Fahad Allam | بانتظار العقد لدى البلدية لتخفيض العقد | Fahad to provide Feedback
ZJB782 | Macro | Aspiration | GRD | Jubail | 2019 Scope | GRD | 26.863608 | 49.454874 | Huawei | Critical Site | New Location | COW | GRD | GRD |  |  | Approved | Done | Done | Approved | Done | Done | Non IGATE | NA | NA | NA | NA | [26 empty] | FDED Not Approved |  | 2019-12-26 | W4-Dec |  | Non-Private | GRD |  | NA | NA | NA | GRD | ISR Not Sub to RF |  | Faris
ZDM007 | Macro | Aspiration | GRD | Dammam | 2019 Scope | GRD | 26.332571 | 50.165691 | Huawei | Critical Site | New Location | COW | GRD | GRD |  |  | Approved | Done | Done | Approved | Done | Done | Non IGATE | NA | NA | NA | NA | [26 empty] | FDED Not Approved |  | 2019-11-28 | W4-Nov |  | Non-Private | GRD |  | NA | NA | NA | GRD | ISR Not Sub to RF |  | Ali
ZBR193 | Macro/Replacement | Aspiration | Central | Qassim | 2020 Scope-Replacement | بريدة | 26.342 | 44.0026 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-08-07 | 2019-08-07 | Approved | 2019-08-07 | 2019-08-18 | IGATE | 07/08/2019 17:58:12 | SNR1011616 | SNR_I | District Support | 2019-08-20 | 2019-08-20 | 2019-08-20 | 2019-09-03 |  |  | 2019-08-01 | [19 empty] | FBP Not submitted |  | 2019-11-25 | Out |  | Non-Private | Baladiya | Qassem Amanah | NA | 0 | 0 | GF | IBP Not Issued | Above | A Sughair | تم احاله المعاملة من الاراضي الى ادارة الحدائق بالامانة
ZJZ057 | Macro | Aspiration | Southern | Jizan | Removed | جازان | 17.762 | 42.4004 | Huawei | Removed from Scope | New Location |  |  | Macro | Cancelled |  | Approved | 2019-08-03 | 2019-08-04 | Approved | 2019-08-05 15:25 | 2019-08-06 15:25 | IGATE | 07/08/2019 15:24:39 | SNR1011612 | REQUESTER | REQUESTER | 2019-08-07 | [27 empty] | Out | Out |  | Non-Private | Baladiya |  | 0 | 0 | 0 | GF | ISR Not Sub to RF |  | Fahad Allam | Out
COW303 | COW | Aspiration | COW | COW | Same Location | COW | 27.559497 | 47.710185 | Huawei | Critical Site | Same Location | COW | COW | COW | Doable |  | Approved | 2019-07-09 | 2019-07-10 | Approved | 2019-07-09 | 2019-07-10 | Non IGATE | NA | NA | NA | NA | 2019-07-13 | 2019-07-13 | 2019-07-13 | 2019-07-13 | NA | NA | 2019-07-13 | 2019-07-13 | 2019-07-13 | 2019-07-13 | 2019-07-13 | 2019-07-13 | NA | NA | 2019-07-13 | 2019-07-13 | [6 empty] | 2019-07-13 | 2019-07-13 | 2019-07-13 | 2019-07-11 | No Dependency |  | Done | HOC Done |  | Non-Private | COW | COW | NA | NA | NA | COW | HO to CW Done | HO Done | Done | تم تسليم الموقع
CWN985 | COW | Aspiration | COW | COW | Same Location | COW | 17.386220 | 42.379530 | Huawei | Critical Site | Same Location | COW | COW | COW | Doable |  | Approved | 2019-07-09 | 2019-07-10 | Approved | 2019-07-05 18:23 | 2019-07-10 | Non IGATE | NA | NA | NA | NA | 2019-07-13 | 2019-07-13 | 2019-07-13 | 2019-07-13 | NA | NA | 2019-07-13 | 2019-07-13 | 2019-07-13 | 2019-07-13 | 2019-07-13 | 2019-07-13 | NA | NA | 2019-07-13 | 2019-07-13 | [6 empty] | 2019-07-13 | 2019-07-13 | 2019-07-13 | 2019-07-11 | No Dependency |  | Done | HOC Done |  | Non-Private | COW | COW | NA | NA | NA | COW | HO to CW Done | HO Done | Done | تم تسليم الموقع
CWN925 | COW | Aspiration | COW | COW | Same Location | COW | 16.920632 | 42.549327 | Huawei | Critical Site | Same Location | COW | COW | COW | Doable |  | Approved | 2019-07-09 | 2019-07-10 | Approved | 2019-07-05 18:23 | 2019-07-10 | Non IGATE | NA | NA | NA | NA | 2019-07-13 | 2019-07-13 | 2019-07-13 | 2019-07-13 | NA | NA | 2019-07-13 | 2019-07-13 | 2019-07-13 | 2019-07-13 | 2019-07-13 | 2019-07-13 | NA | NA | 2019-07-13 | 2019-07-13 | [6 empty] | 2019-07-13 | 2019-07-13 | 2019-07-13 | 2019-07-11 | No Dependency |  | Done | HOC Done |  | Non-Private | COW | COW | NA | NA | NA | COW | HO to CW Done | HO Done | Done | تم تسليم الموقع
CWS810 | COW | Aspiration | COW | COW | Same Location | COW | 28.432764 | 36.575677 | Huawei | Critical Site | Same Location | COW | COW | COW | Doable |  | Approved | 2019-07-09 | 2019-07-10 | Approved | 2019-07-05 18:23 | 2019-07-10 | Non IGATE | NA | NA | NA | NA | 2019-07-13 | 2019-07-13 | 2019-07-13 | 2019-07-13 | NA | NA | 2019-07-13 | 2019-07-13 | 2019-07-13 | 2019-07-13 | 2019-07-13 | 2019-07-13 | NA | NA | 2019-07-13 | 2019-07-13 | [6 empty] | 2019-07-13 | 2019-07-13 | 2019-07-13 | 2019-07-11 | No Dependency |  | Done | HOC Done |  | Non-Private | COW | COW | NA | NA | NA | COW | HO to CW Done | HO Done | Done | تم تسليم الموقع
COW305 | COW | Aspiration | COW | COW | Same Location | COW | 28.123086 | 45.672542 | Huawei | Critical Site | Same Location | COW | COW | COW | Doable |  | Approved | 2019-07-09 | 2019-07-10 | Approved | 2019-07-05 18:23 | 2019-07-10 | Non IGATE | NA | NA | NA | NA | 2019-07-13 | 2019-07-13 | 2019-07-13 | 2019-07-13 | NA | NA | 2019-07-13 | 2019-07-13 | 2019-07-13 | 2019-07-13 | 2019-07-13 | 2019-07-13 | NA | NA | 2019-07-13 | 2019-07-13 | [6 empty] | 2019-07-13 | 2019-07-13 | 2019-07-13 | 2019-07-11 | No Dependency |  | Done | HOC Done |  | Non-Private | COW | COW | NA | NA | NA | COW | HO to CW Done | HO Done | Done | تم تسليم الموقع
CWS821 | COW | Aspiration | COW | COW | Same Location | COW | 26.902278 | 49.485427 | Huawei | Critical Site | Same Location | COW | COW | COW | Doable |  | Approved | 2019-07-09 | 2019-07-10 | Approved | 2019-07-05 18:23 | 2019-07-10 | Non IGATE | NA | NA | NA | NA | 2019-07-13 | 2019-07-13 | 2019-07-13 | 2019-07-13 | NA | NA | 2019-07-13 | 2019-07-13 | 2019-07-13 | 2019-07-13 | 2019-07-13 | 2019-07-13 | NA | NA | 2019-07-13 | 2019-07-13 | [6 empty] | 2019-07-13 | 2019-07-13 | 2019-07-13 | 2019-07-11 | No Dependency |  | Done | HOC Done |  | Non-Private | COW | COW | NA | NA | NA | COW | HO to CW Done | HO Done | Done | تم تسليم الموقع
COW306 | COW | Aspiration | COW | COW | Same Location | COW | 26.472800 | 50.029570 | Huawei | Critical Site | Same Location | COW | COW | COW | Doable |  | Approved | 2019-07-09 | 2019-07-10 | Approved | 2019-07-05 18:23 | 2019-07-10 | Non IGATE | NA | NA | NA | NA | 2019-07-13 | 2019-07-13 | 2019-07-13 | 2019-07-13 | NA | NA | 2019-07-13 | 2019-07-13 | 2019-07-13 | 2019-07-13 | 2019-07-13 | 2019-07-13 | NA | NA | 2019-07-13 | 2019-07-13 | [6 empty] | 2019-07-13 | 2019-07-13 | 2019-07-13 | 2019-07-11 | No Dependency |  | Done | HOC Done |  | Non-Private | COW | COW | NA | NA | NA | COW | HO to CW Done | HO Done | Done | تم تسليم الموقع
CWN904 | COW | Aspiration | COW | COW | Same Location | COW | 16.975067 | 42.556888 | Huawei | Critical Site | Same Location | COW | COW | COW | Doable |  | Approved | 2019-07-09 | 2019-07-10 | Approved | 2019-07-05 18:23 | 2019-07-10 | Non IGATE | NA | NA | NA | NA | 2019-07-13 | 2019-07-13 | 2019-07-13 | 2019-07-13 | NA | NA | 2019-07-13 | 2019-07-13 | 2019-07-13 | 2019-07-13 | 2019-07-13 | 2019-07-13 | NA | NA | 2019-07-13 | 2019-07-13 | [6 empty] | 2019-07-13 | 2019-07-13 | 2019-07-13 | 2019-07-11 | No Dependency |  | Done | HOC Done |  | Non-Private | COW | COW | NA | NA | NA | COW | HO to CW Done | HO Done | Done | تم تسليم الموقع
CWN911 | Macro | Aspiration | COW | COW | Same Location | COW | 19.815960 | 42.615530 | Huawei | Critical Site | Same Location | COW | COW | COW | Doable |  | Approved | Done | Done | Approved | Done | Done | Non IGATE | NA | NA | NA | NA | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | NA | NA | Done | Done | [6 empty] | Done | Done | 2019-07-24 |  | No Dependency |  | Done | HOC Done |  | Non-Private | COW |  | NA | NA | NA | COW | HO Not Done | HO Done | Done | تم تسليم الموقع
CWS813 | Macro | Aspiration | COW | COW | Same Location | COW | 27.600390 | 46.310030 | Huawei | Critical Site | Same Location | COW | COW | COW | Doable |  | Approved | Done | Done | Approved | Done | Done | Non IGATE | NA | NA | NA | NA | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | NA | NA | Done | Done | [6 empty] | Done | Done | 2019-07-24 |  | No Dependency |  | Done | HOC Done |  | Non-Private | COW |  | NA | NA | NA | COW | HO Not Done | HO Done | Done | تم تسليم الموقع
COW629 | Macro | Aspiration | COW | COW | Same Location | COW | 24.582100 | 47.988840 | Huawei | Critical Site | Same Location | COW | COW | COW | Doable |  | Approved | Done | Done | Approved | Done | Done | Non IGATE | NA | NA | NA | NA | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | NA | NA | Done | Done | [6 empty] | Done | Done | 2019-07-24 |  | No Dependency |  | Done | HOC Done |  | Non-Private | COW |  | NA | NA | NA | COW | HO Not Done | HO Done | Done | تم تسليم الموقع
COW618 | Macro | Aspiration | COW | COW | Same Location | COW | 26.422798 | 49.977105 | Huawei | Critical Site | Same Location | COW | COW | COW | Doable |  | Approved | Done | Done | Approved | Done | Done | Non IGATE | NA | NA | NA | NA | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | NA | NA | Done | Done | [6 empty] | Done | Done | 2019-07-24 |  | No Dependency |  | Done | HOC Done |  | Non-Private | COW |  | NA | NA | NA | COW | HO Not Done | HO Done | Done | تم تسليم الموقع
ZBR977 | Macro | Aspiration | RT | Qassim | Same Location | RT | 26.369146 | 43.959432 | Huawei | Critical Site | Same Location | RT | RT | RT | Doable |  | Approved | Done | Done | Approved | Done | Done | Non IGATE | NA | NA | NA | NA | Done | Done | Done | Done | Done | Done | NA | NA | NA | NA | NA | NA | Done | Done | Done | Done | [6 empty] | Done | Done | 2019-07-24 |  | No Dependency |  | Done | HOC Done |  | Private | RT |  | NA | NA | NA | RT | HO Not Done | HO Done | Done | تم تسليم الموقع
CWS804 | Macro | Aspiration | COW | COW | Same Location | COW | 27.115830 | 49.286620 | Huawei | Critical Site | Same Location | COW | COW | COW | Doable |  | Approved | Done | Done | Approved | Done | Done | Non IGATE | NA | NA | NA | NA | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | NA | NA | Done | Done | [6 empty] | Done | Done | 2019-07-24 |  | No Dependency |  | Done | HOC Done |  | Non-Private | COW |  | NA | NA | NA | COW | HO Not Done | HO Done | Done | تم تسليم الموقع
COW545 | Macro | Aspiration | COW | COW | Same Location | COW | 27.355738 | 49.219924 | Huawei | Critical Site | Same Location | COW | COW | COW | Doable |  | Approved | Done | Done | Approved | Done | Done | Non IGATE | NA | NA | NA | NA | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | NA | NA | Done | Done | [6 empty] | Done | Done | 2019-07-24 |  | No Dependency |  | Done | HOC Done |  | Non-Private | COW |  | NA | NA | NA | COW | HO Not Done | HO Done | Done | تم تسليم الموقع
CWS835 | Macro | Aspiration | COW | COW | Same Location | COW | 28.402500 | 45.938800 | Huawei | Critical Site | Same Location | COW | COW | COW | Doable |  | Approved | Done | Done | Approved | Done | Done | Non IGATE | NA | NA | NA | NA | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | NA | NA | Done | Done | [6 empty] | Done | Done | 2019-07-24 |  | No Dependency |  | Done | HOC Done |  | Non-Private | COW |  | NA | NA | NA | COW | HO Not Done | HO Done | Done | تم تسليم الموقع
CWS819 | Macro | Aspiration | COW | COW | Same Location | COW | 27.474450 | 49.194850 | Huawei | Critical Site | Same Location | COW | COW | COW | Doable |  | Approved | Done | Done | Approved | Done | Done | Non IGATE | NA | NA | NA | NA | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | NA | NA | Done | Done | [6 empty] | Done | Done | 2019-07-24 |  | No Dependency |  | Done | HOC Done |  | Non-Private | COW |  | NA | NA | NA | COW | HO Not Done | HO Done | Done | تم تسليم الموقع
CWS818 | Macro | Aspiration | COW | COW | Same Location | COW | 27.537300 | 49.117178 | Huawei | Critical Site | Same Location | COW | COW | COW | Doable |  | Approved | Done | Done | Approved | Done | Done | Non IGATE | NA | NA | NA | NA | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | NA | NA | Done | Done | [6 empty] | Done | Done | 2019-07-24 |  | No Dependency |  | Done | HOC Done |  | Non-Private | COW |  | NA | NA | NA | COW | HO Not Done | HO Done | Done | تم تسليم الموقع
CWS832 | Macro | Aspiration | COW | COW | Same Location | COW | 27.122144 | 49.551362 | Huawei | Critical Site | Same Location | COW | COW | COW | Doable |  | Approved | Done | Done | Approved | Done | Done | Non IGATE | NA | NA | NA | NA | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | NA | NA | Done | Done | [6 empty] | Done | Done | 2019-07-24 |  | No Dependency |  | Done | HOC Done |  | Non-Private | COW |  | NA | NA | NA | COW | HO Not Done | HO Done | Done | تم تسليم الموقع
COW551 | Macro | Aspiration | COW | COW | Same Location | COW | 25.475355 | 49.510221 | Huawei | Critical Site | Same Location | COW | COW | COW | Doable |  | Approved | Done | Done | Approved | Done | Done | Non IGATE | NA | NA | NA | NA | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | NA | NA | Done | Done | [6 empty] | Done | Done | 2019-07-24 |  | No Dependency |  | Done | HOC Done |  | Non-Private | COW |  | NA | NA | NA | COW | HO Not Done | HO Done | Done | تم تسليم الموقع
CWS836 | Macro | Aspiration | COW | COW | Same Location | COW | 31.757854 | 39.014080 | Huawei | Critical Site | Same Location | COW | COW | COW | Doable |  | Approved | Done | Done | Approved | Done | Done | Non IGATE | NA | NA | NA | NA | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | NA | NA | Done | Done | [6 empty] | Done | Done | 2019-07-24 |  | No Dependency |  | Done | HOC Done |  | Non-Private | COW |  | NA | NA | NA | COW | HO Not Done | HO Done | Done | تم تسليم الموقع
CWS808 | Macro | Aspiration | COW | COW | Same Location | COW | 27.466080 | 48.625570 | Huawei | Critical Site | Same Location | COW | COW | COW | Doable |  | Approved | Done | Done | Approved | Done | Done | Non IGATE | NA | NA | NA | NA | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | NA | NA | Done | Done | [6 empty] | Done | Done | 2019-07-24 |  | No Dependency |  | Done | HOC Done |  | Non-Private | COW |  | NA | NA | NA | COW | HO Not Done | HO Done | Done | تم تسليم الموقع
ZND810 | Macro | Aspiration | RT | Dammam | Same Location | RT | 26.377870 | 50.187760 | Huawei | Critical Site | Same Location | RT | RT | RT | Doable |  | Approved | Done | Done | Approved | Done | Done | Non IGATE | NA | NA | NA | NA | Done | Done | Done | Done | Done | Done | NA | NA | NA | NA | NA | NA | Done | Done | Done | Done | [6 empty] | Done | Done | 2019-07-24 |  | No Dependency |  | Done | HOC Done |  | Private | RT |  | NA | NA | NA | RT | HO Not Done | HO Done | Done | تم تسليم الموقع
COW652 | Macro | Aspiration | COW | COW | Same Location | COW | 26.342600 | 50.134500 | Huawei | Critical Site | Same Location | COW | COW | COW | Doable |  | Approved | Done | Done | Approved | Done | Done | Non IGATE | NA | NA | NA | NA | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | NA | NA | Done | Done | [6 empty] | Done | Done | 2019-07-24 |  | No Dependency |  | Done | HOC Done |  | Non-Private | COW |  | NA | NA | NA | COW | HO Not Done | HO Done | Done | تم تسليم الموقع
COW659 | Macro | Aspiration | COW | COW | Same Location | COW | 26.487380 | 50.120354 | Huawei | Critical Site | Same Location | COW | COW | COW | Doable |  | Approved | Done | Done | Approved | Done | Done | Non IGATE | NA | NA | NA | NA | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | NA | NA | Done | Done | [6 empty] | Done | Done | 2019-07-24 |  | No Dependency |  | Done | HOC Done |  | Non-Private | COW |  | NA | NA | NA | COW | HO Not Done | HO Done | Done | تم تسليم الموقع
ZHF050 | Macro | Aspiration | RT | Hofof | Same Location | RT | 22.510606 | 53.952473 | Huawei | Critical Site | Same Location | RT | RT | RT | Doable |  | Approved | Done | Done | Approved | Done | Done | Non IGATE | NA | NA | NA | NA | Done | Done | Done | Done | Done | Done | NA | NA | NA | NA | NA | NA | Done | Done | Done | Done | [6 empty] | Done | Done | 2019-07-24 |  | No Dependency |  | Done | HOC Done |  | Private | RT |  | NA | NA | NA | RT | HO Not Done | HO Done | Done | تم تسليم الموقع
CWN900 | COW | Aspiration | COW | COW | Same Location | COW | 16.755750 | 43.125830 | Huawei | Critical Site | Same Location | COW | COW | COW | Doable |  | Approved | Done | Done | Approved | Done | Done | Non IGATE | NA | NA | NA | NA | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | NA | NA | Done | Done | [6 empty] | Done | Done | 2019-07-31 |  | No Dependency |  | Done | HOC Done |  | Non-Private | COW |  | NA | NA | NA | COW | HO Not Done | HO Done | Done | تم تسليم الموقع
CWN910 | COW | Aspiration | COW | COW | Same Location | COW | 17.711588 | 42.215851 | Huawei | Critical Site | Same Location | COW | COW | COW | Doable |  | Approved | Done | Done | Approved | Done | Done | Non IGATE | NA | NA | NA | NA | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | NA | NA | Done | Done | [6 empty] | Done | Done | 2019-07-31 |  | No Dependency |  | Done | HOC Done |  | Non-Private | COW |  | NA | NA | NA | COW | HO Not Done | HO Done | Done | تم تسليم الموقع
CWS834 | COW | Aspiration | COW | COW | Same Location | COW | 28.438170 | 45.954590 | Huawei | Critical Site | Same Location | COW | COW | COW | Doable |  | Approved | Done | Done | Approved | Done | Done | Non IGATE | NA | NA | NA | NA | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | NA | NA | Done | Done | [6 empty] | Done | Done | 2019-07-31 |  | No Dependency |  | Done | HOC Done |  | Non-Private | COW |  | NA | NA | NA | COW | HO Not Done | HO Done | Done | تم تسليم الموقع
ZBR136 | Macro | Aspiration | Central | Qassim | 2020 Scope | بريدة | 26.2708 | 44.0342 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-09-01 | 2019-09-01 | Approved | 2019-09-03 | 2019-10-02 | IGATE | 29/10/2019 17:31:10 | SNR1012259 | SNR_K | Procurement Department Employee | [6 empty] | NA | NA | NA | NA | NA | NA | [14 empty] | FDED Not Approved |  | 2019-11-28 | W4-Nov |  | Non-Private | Gov | Hospital | NA | NA | NA | GF | ISR Not Sub to RF | Below BM | A Sughair | بانتظار موافقة RF على موقع المستشفى FOC
ZDH028 | Macro/Replacement | Aspiration | Eastern | Dammam | 2019 Scope-Replacement | Aramco | 26.2502 | 50.0478 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-10-07 | 2019-10-13 |  |  |  | IGATE | 10/11/2019 17:33:29 | SNR1012330 | SNR_B | RF Team Leader | [26 empty] | Pending HOC |  | 2019-12-25 | W4-Dec |  | Non-Private | Gov | Aramco | NA | NA | NA | GF | ,ISR IN GAT | Below BM | NA | تمت اضافته جديد تم مسح مبدئي -الموقع غير قابل للحيازة لا نستطيع استخراج رخصة
ZJB280 | Macro | Aspiration | Eastern | Jubail |  | GRD | 26.953392 | 49.351409 | Huawei | Critical Site | New Location | COW | GF | GRD | Doable |  | Approved | 2019-10-07 | 2019-10-13 | Approved | 2019-10-13 | 2019-10-13 | IGATE | 25/07/2019 15:04:28 | SNR1011468 | SNR_I | District Support | [26 empty] | FDED Not Approved |  | 2019-12-26 | W4-Dec |  |  |  |  | NA | NA | NA | GRD | ISR Not Sub to RF |  | NA
ZND529 | Macro | Aspiration | Eastern | Dammam |  | GRD | 26.396290 | 50.142700 | Huawei | Critical Site | New Location | COW | GRD | GRD | Doable |  | Approved | 2019-10-07 | 2019-10-13 |  |  |  | IGATE | #N/A | #N/A | #N/A | #N/A | [26 empty] | FDED Not Approved |  | 2019-12-26 | W4-Dec |  |  |  |  | NA | NA | NA | GRD | ,ISR IN GAT |  | NA
ZTB423 | Macro | Aspiration | Northern | Tabuk |  | GRD | 28.790529 | 36.447902 | Huawei | Critical Site | New Location | COW | GRD | GRD | Doable |  | Approved | 2019-10-07 | 2019-10-13 | Approved | 2019-10-13 | 2019-10-13 | IGATE | #N/A | #N/A | #N/A | #N/A | [26 empty] | FBP Not submitted |  | 2019-12-26 | W4-Dec |  |  |  |  | NA | NA | NA | GRD | #N/A |  | NA
ZTR018 | Macro | Aspiration | Northern | Northern Border |  | GRD | 31.374400 | 37.298200 | Huawei | Critical Site | New Location | COW | GRD | GRD | Doable |  | Approved | 2019-10-07 | 2019-10-13 |  |  |  | IGATE | #N/A | #N/A | #N/A | #N/A | [26 empty] | FBP Not submitted |  | 2019-12-26 | W4-Dec |  |  |  |  | NA | NA | NA | GRD | ,ISR IN GAT |  | NA
ZTB385 | Macro | Aspiration | Northern | Tabuk | 2019 Scope | تبوك | 28.4195 | 36.4698 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-10-27 | 2019-10-28 | Approved | 2019-11-05 | 2019-11-05 | IGATE | 07/11/2019 12:23:41 | SNR1012321 | SNR_F | District Director | Done | Done | Done | Done | Done | Done | 2019-11-09 | NA | [18 empty] | Pending HOC |  | 2019-12-26 | W4-Dec |  | Private | Private | [5 empty] | Contract Not Issued
ZHF284 | Macro | Aspiration | Eastern | Hofof | 2019 Scope | الهفوف | 25.3885 | 49.5452 | Huawei | New Site | New Location | NA | NA | Macro | Doable |  | Approved | 2019-10-27 | 2019-10-28 |  |  |  | IGATE | 10/11/2019 16:53:35 | SNR1012329 | SNR_B | RF Team Leader | [26 empty] | Pending HOC |  | 2019-12-26 | W4-Dec |  | Non-Private | Baladiya | Al Ahsa Amanah |  |  |  |  | ,ISR IN GAT | Above
COW302 | Macro | Aspiration | COW | COW | Same Location | COW | 26.313300 | 50.226570 | Huawei | Critical Site | Same Location | COW | COW | COW | Doable |  | Approved | Done | Done | Approved | Done | Done | Non IGATE | NA | NA | NA | NA | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | NA | NA | Done | Done | [6 empty] | Done | Done | 2019-07-24 |  | No Dependency |  | Done | HOC Done |  | Non-Private | COW |  | NA | NA | NA | COW | HO Not Done | HO Done | Done | تم تسليم الموقع
COW304 | Macro | Aspiration | COW | COW | Same Location | COW | 0 | 0 | Huawei | Critical Site | Same Location | COW | COW | COW | Doable |  | Approved | Done | Done | Approved | Done | Done | Non IGATE | NA | NA | NA | NA | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | NA | NA | Done | Done | [6 empty] | Done | Done | 2019-07-24 |  | No Dependency |  | Done | HOC Done |  | Non-Private | COW |  | NA | NA | NA | COW | HO Not Done | HO Done | Done | تم تسليم الموقع
COW547 | Macro | Aspiration | COW | COW | Same Location | COW | 25.630113 | 46.818825 | Huawei | Critical Site | Same Location | COW | COW | COW | Doable |  | Approved | Done | Done | Approved | Done | Done | Non IGATE | NA | NA | NA | NA | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | NA | NA | Done | Done | [6 empty] | Done | Done | 2019-07-24 |  | No Dependency |  | Done | HOC Done |  | Non-Private | COW |  | NA | NA | NA | COW | HO Not Done | HO Done | Done | تم تسليم الموقع
COW636 | Macro | Aspiration | COW | COW | Same Location | COW | 28.453600 | 46.023570 | Huawei | Critical Site | Same Location | COW | COW | COW | Doable |  | Approved | Done | Done | Approved | Done | Done | Non IGATE | NA | NA | NA | NA | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | NA | NA | Done | Done | [6 empty] | Done | Done | 2019-07-24 |  | No Dependency |  | Done | HOC Done |  | Non-Private | COW |  | NA | NA | NA | COW | HO Not Done | HO Done | Done | تم تسليم الموقع
COW657 | Macro | Aspiration | COW | COW | Same Location | COW | 26.367213 | 50.137514 | Huawei | Critical Site | Same Location | COW | COW | COW | Doable |  | Approved | Done | Done | Approved | Done | Done | Non IGATE | NA | NA | NA | NA | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | NA | NA | Done | Done | [6 empty] | Done | Done | 2019-07-24 |  | No Dependency |  | Done | HOC Done |  | Non-Private | COW |  | NA | NA | NA | COW | HO Not Done | HO Done | Done | تم تسليم الموقع
CWN918 | Macro | Aspiration | COW | COW | Same Location | COW | 0 | 0 | Huawei | Critical Site | Same Location | COW | COW | COW | Doable |  | Approved | Done | Done | Approved | Done | Done | Non IGATE | NA | NA | NA | NA | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | NA | NA | Done | Done | [6 empty] | Done | Done | 2019-07-24 |  | No Dependency |  | Done | HOC Done |  | Non-Private | COW |  | NA | NA | NA | COW | HO Not Done | HO Done | Done | تم تسليم الموقع
CWS800 | Macro | Aspiration | COW | COW | Same Location | COW | 0 | 0 | Huawei | Critical Site | Same Location | COW | COW | COW | Doable |  | Approved | Done | Done | Approved | Done | Done | Non IGATE | NA | NA | NA | NA | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | NA | NA | Done | Done | [6 empty] | Done | Done | 2019-07-24 |  | No Dependency |  | Done | HOC Done |  | Non-Private | COW |  | NA | NA | NA | COW | HO Not Done | HO Done | Done | تم تسليم الموقع
ZDH010 | Macro | Aspiration | GF-Palm Tree | GF-Palm Tree | Same Location | GF-Palm Tree | 26.400920 | 49.886430 | Huawei | Critical Site | Same Location | GF-Palm Tree | GF-Palm Tree | GF-Palm Tree | Doable |  | Approved | Done | Done | Approved | Done | Done | Non IGATE | NA | NA | NA | NA | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | NA | NA | Done | Done | [6 empty] | Done | Done | 2019-07-24 |  | No Dependency |  | Done | HOC Done |  | Non-Private | COW |  | NA | NA | NA | COW | HO Not Done | HO Done | Done | تم تسليم الموقع
ZHF774 | Macro | Aspiration | GF-Palm Tree | GF-Palm Tree | Same Location | GF-Palm Tree | 25.343900 | 49.595100 | Huawei | Critical Site | Same Location | GF-Palm Tree | GF-Palm Tree | GF-Palm Tree | Doable |  | Approved | Done | Done | Approved | Done | Done | Non IGATE | NA | NA | NA | NA | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | NA | NA | Done | Done | [6 empty] | Done | Done | 2019-07-24 |  |  |  | Done | HOC Done |  | Non-Private | COW |  | NA | NA | NA | COW | HO Not Done | HO Done | Done | تم تسليم الموقع
ZHF871 | Macro | Aspiration | GF-Palm Tree | GF-Palm Tree | Same Location | GF-Palm Tree | 25.455240 | 49.517980 | Huawei | Critical Site | Same Location | GF-Palm Tree | GF-Palm Tree | GF-Palm Tree | Doable |  | Approved | Done | Done | Approved | Done | Done | Non IGATE | NA | NA | NA | NA | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | NA | NA | Done | Done | [6 empty] | Done | Done | 2019-07-24 |  |  |  | Done | HOC Done |  | Non-Private | COW |  | NA | NA | NA | COW | HO Not Done | HO Done | Done | تم تسليم الموقع
ZND743 | Macro | Aspiration | GF-Palm Tree | GF-Palm Tree | Same Location | GF-Palm Tree | 26.377870 | 50.187760 | Huawei | Critical Site | Same Location | GF-Palm Tree | GF-Palm Tree | GF-Palm Tree | Doable |  | Approved | Done | Done | Approved | Done | Done | Non IGATE | NA | NA | NA | NA | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done | NA | NA | Done | Done | [6 empty] | Done | Done | 2019-07-24 |  | No Dependency |  | Done | HOC Done |  | Non-Private | COW |  | NA | NA | NA | COW | HO Not Done | HO Done | Done | تم تسليم الموقع
Formulas:
ADHOC = VLOOKUP(A:A,'[1]NPTS-Export'!$C:$K,9,0)

## Sheet8 (hidden)
Scope Status | (Multiple Items)
Row Labels | Count of Site ID | Count of HO Submission date
Arrar | 9 | 7
Baladiya | 1
Gov | 3 | 2
Private | 5 | 5
Baha | 14 | 8
Baladiya | 7 | 6
Gov | 2
Private | 5 | 2
COW | 20 | 20
COW | 20 | 20
Dammam | 25 | 12
Baladiya | 13 | 11
Gov | 9
Private | 3 | 1
Hafr Batin | 16 | 11
Baladiya | 10 | 5
Private | 6 | 6
Hail | 14 | 11
Baladiya | 9 | 7
Gov | 2 | 1
Private | 3 | 3
Hofof | 19 | 5
Baladiya | 13 | 4
Gov | 5
Private | 1 | 1
Jizan | 15 | 5
Baladiya | 7 | 3
Gov | 7 | 1
Private | 1 | 1
Jubail | 18 | 3
Baladiya | 4 | 2
Gov | 12
Private | 2 | 1
Najran | 13 | 8
Baladiya | 7 | 5
Gov | 1
Private | 5 | 3
Northern Border | 16 | 4
Baladiya | 3 | 1
Gov | 10
Private | 3 | 3
Qassim | 24 | 13
Baladiya | 6 | 2
Gov | 4 | 1
Private | 14 | 10
Riyadh District | 16 | 12
Baladiya | 9 | 8
Gov | 3
Private | 4 | 4
Tabuk | 26 | 11
Baladiya | 9 | 2
Gov | 10 | 5
Private | 7 | 4
Grand Total | 245 | 130

## NovDec plan
Milestone | Total Scope | HO | Not HO | Owner type |  | Nov-Wk1 | Nov-Wk2 | Nov-Wk3 | Nov-Wk4 | Dec-Wk1 | Dec-Wk2 | Dec-Wk3 | Dec-Wk4
Nov / Dec Plan | 245 | 138 | 107 | Private | Plan | 1 | 4 | 2 | 3 | 1 | 2 | 1 | 2
|  |  |  | 13 | Actual | Nov-Wk1: 1; Nov-Wk2: 2; Nov-Wk3: 0
|  |  |  | Gov | Plan | 3 | 3 | 7 | 5 | 10 | 10 | 9 | 11
|  |  |  | 58 | Actual | Nov-Wk1: 0; Nov-Wk2: 0; Nov-Wk3: 0
|  |  |  | Baladiyah | Plan | 3 | 2 | 4 | 3 | 7 | 4 | 10 | 9
|  |  |  | 38 | Actual | Nov-Wk1: 3; Nov-Wk2: 5; Nov-Wk3: 0
Grand Total | 245 | 138 | 107 | 11 | Plan | 7 | 9 | 13 | 11 | 18 | 16 | 20 | 22
[5 empty] | Actual | 4 | 7 | 0 | 0 | 0 | 0 | 0 | 0

## New Tree
Total Scope | 256 | Total Scope 256
Not in Scope | 11 | Not in Scope 11
Gov. | 58 | Gov. 58
Within BM | 21 | Within BM 21
Above BM | 37 | Above BM 37
Contract Issued Under TAWAL Signature | 1 | Contract Issued Under TAWAL Signature 1
Under contract issuance | 36 | Under contract issuance 36
BP Sites | 187 | BP Sites 187
Handed Over | 138 | Handed Over 138
BP Submitted | 47 | BP Submitted 47
FBP Submitted | 5 | FBP Submitted 5
Under Contract Stage | 42 | Under Contract Stage 42
Contract issued under TAWAL signature | 7 | Contract issued under TAWAL signature 7
Under contract issuance | 35 | Under contract issuance 35
BP not submitted | 2 | BP not submitted 2
Above BM | 2 | Above BM 2
Within BM | 0 | Within BM 0
Total Scope 256
Gov. 58
Within BM 21
Above BM 37
Contract Issued Under TAWAL Signature 1
Under contract issuance 36
Not in Scope 11
BP Sites 187
Handed Over 138
BP Submitted 47
FBP Submitted 5
Under Contract Stage 42
Contract issued under TAWAL signature 7
Under contract issuance 35
BP not submitted 2
Above BM 2
Within BM 0

## Sheet6 (hidden)
Site ID | Gov Name | HO Submission date | HO Submission date | (blank)
ZDM080 | General Investigation
ZDM139 | Seaport |  | Row Labels | Count of Site ID
ZAQ013 | Aramco |  | Airport | 1
ZDH002 | Aramco |  | Aramco | 6 | -1
ZDH003 | Aramco |  | Camel Club | 3
ZDM033 | NG |  | General Investigation | 1
ZND791 | NG |  | MO Health | 2
ZDM013 | Modon |  | Modon | 11
ZTB402 | MOI |  | MOH | 3
ZHF279 | NG |  | MOI | 4
ZHF294 | NG |  | NG | 9
ZRN026 | Camel Club |  | RC JAZAN | 5
ZRN027 | Camel Club |  | RC Jubail | 9
ZNM043 | MOA |  | Seaport | 1
ZRN028 | Camel Club |  | Technical College | 2
ZHF296 | NG |  | MOA | 1
ZBH587 | MOI |  | Grand Total | 58
ZJZ068 | MOI | 2019-07-03
ZJZ170 | RC JAZAN
ZJZ221 | RC JAZAN
ZJZ356 | RC JAZAN
ZJZ530 | RC JAZAN
ZJZ531 | RC JAZAN
ZRR027 | MOI | 2019-09-16
ZBR149 | MOI | 2019-06-30
ZBR178 | NG
ZTB430 | MOH
ZHA330 | MOH
ZNN676 | NG
ZHF202 | NG
ZHF203 | NG
ZTB128 | MOI | 2019-07-03
ZTB135 | MOI | 2019-07-10
ZTB036 | Uni. | 2019-10-30
ZTB111 | Uni. | 2019-10-30
ZTB872 | MOI
ZTB384 | Uni. | 2019-10-30
ZRR031 | Technical College
ZHA904 | Uni. | 2019-10-24
ZJB157 | RC Jubail
ZRR029 | Uni. | 2019-07-18
ZJB170 | RC Jubail
ZJB175 | RC Jubail
ZTR015 | Modon
ZTR026 | Modon
ZTR037 | Modon
ZTR040 | Modon
ZTR043 | Modon
ZTR045 | Modon
ZTR047 | Modon
ZTR048 | Modon
ZTR053 | Modon
ZTR055 | Modon
ZUL030 | Technical College
ZJB222 | MOI
ZJB229 | Aramco
ZJB234 | Aramco
ZJB101 | RC Jubail
ZJB107 | RC Jubail
ZJB108 | RC Jubail
ZJB805 | RC Jubail
ZJB861 | RC Jubail
ZUZ060 | MOH
ZJB279 | RC Jubail
ZDB151 | Airport
ZJZ173 | MO Health
ZBR136 | MO Health
ZDH028 | Aramco

## Sheet5 (hidden)
Site ID | District | Owner Type | Contract submitted | HOC submitted | Invoice submitted | ملاحظات المشتريات | Remark | IBP | FBP
ZAB391 | Baha | Non-Private | yes |  | 0 | محضر استلام وفاتورة سداد | 2 | Yes
ZAB444 | Baha | Non-Private | yes |  | Yes | محضر استلام وفاتورة سداد | يحتاج تعديل الفاتورة | Yes
ZBH590 | Baha | Non-Private | yes |  | Yes | #N/A | لا يوجد فترة سماح بالعقد | Yes
ZBH640 | Baha | Non-Private | yes |  | Yes | #N/A |  | Yes
ZBS115 | Baha | Non-Private | Submitted |  | Submitted | #N/A |  | Submitted
ZBS341 | Baha | Non-Private | Submitted |  | Submitted | #N/A |  | Submitted | Submitted
ZBS186 | Baha | Private | Submitted | Yes | NA | #N/A |  | NA
ZNN721 | Najran | Private | Submitted | Yes | NA | #N/A |  | NA
ZNN668 | Najran | Private | Submitted | Yes | NA | #N/A |  | NA
ZNN700 | Najran | Private | Submitted | 0 | NA | #N/A |  | NA
ZBS340 | Baha | Private | Submitted | 0 | NA | #N/A |  | NA
ZJZ068 | Jizan | Non-Private | Submitted |  | Submitted | #N/A |  | NA
ZNN665 | Najran | Non-Private | yes |  | Yes | محضر استلام | تم تقديم المحضر | Yes
ZNN741 | Najran | Non-Private | yes |  | Yes | محضر استلام وفاتورة سداد لم يخصم منها فترة السماح | يحتاج محضر وخصم الفاتورة | 0
ZNN763 | Najran | Non-Private | yes |  | Yes | محضر استلام وفاتورة سداد لم يخصم منها فترة السماح | يحتاج محضر وخصم الفاتورة | 0
ZSR042 | Najran | Non-Private | yes |  | Yes | محضر الاستلام | يحتاج تعديل الفاتورة | Yes
ZSR045 | Najran | Non-Private | yes |  | Yes | محضر الاستلام | يحتاج تعديل الفاتورة | Yes

## Sheet4 (hidden)
Scope Status | New Site
Owner's Type (Gov/Amanah/Private) | (Multiple Items)
Count of Site ID | FC Week
District | HOC Done | Out | W3-Oct | W4-Oct | W1-Nov | W2-Nov | W3-Nov | W4-Nov | W1-Dec | W2-Dec | W2-Oct | W3-Dec | W4-Dec | Grand Total
Arrar | 4 |  | 1 | [8 empty] | 1 |  | 6
Baha | 5 |  | 2 | 1 |  | 2 |  |  |  |  | 1 |  |  | 11
Dammam | 1 |  | 3 | 9 |  | 2 |  |  | 1 |  |  |  |  | 16
Hafr Batin | 3 |  |  | 5 | 1 |  | 4 | 1 | 1 |  |  | 1 |  | 16
Hail | 2 |  | 1 | 7 |  |  |  | 2 | [5 empty] | 12
Hofof |  |  | 1 | [6 empty] | 4 |  | 8 |  | 13
Jizan | [5 empty] | 7 |  | 1 | [5 empty] | 8
Jubail |  |  | 1 |  |  |  | 3 | 1 |  |  |  |  | 1 | 6
Najran | 3 |  | 2 | 2 | [5 empty] | 4 | 1 |  |  | 12
Northern Border | 2 | [7 empty] | 3 |  | 1 |  |  | 6
Qassim | 9 | 1 | 3 | 1 | 2 | 2 | 1 | 1 | [5 empty] | 20
Riyadh District | 11 |  |  |  |  | 1 |  |  |  |  | 1 |  |  | 13
Tabuk | 5 |  | 1 | 1 |  |  |  |  | 1 | 1 |  | 6 |  | 15
Grand Total | 45 | 1 | 15 | 26 | 3 | 14 | 8 | 6 | 6 | 9 | 4 | 16 | 1 | 154

## SAQ GAP
New Sites - SAQ GAP
Deliverable | New Sites |  |  | Critical Sites | [5 empty] | Total GAP | Responsibility | FC date | 275
|  |  |  | Same Site ID |  |  | New Sites
| Plan | Actual | GAP | Scope | Actual | GAP | Plan | Actual | GAP
Design
Scope | 256 | 245 | 11 | 40 | 40 | 0 | 22 | 22 | 0 | 11 | STC WND | 12 New Sites For Future Replacement Site |  | 176 | 34 | 142
JISOW | 245 | 245 | 0 | 40 | 40 | 0 | 22 | 22 | 0 | 0 | STC WND
SSO Submitted | 245 | 245 | 0 | 40 | 40 | 0 | 22 | 22 | 0 | 0 | Vendor RF
SSO Approved | 245 | 245 | 0 | 40 | 40 | 0 | 22 | 22 | 0 | 0 | STC WND
ISR Submitted | 245 | 243 | 2 | 40 | 40 | 0 | 22 | 20 | 2 | 4 | Vendor RF
ISR Approved | 243 | 242 | 1 | 40 | 40 | 0 | 20 | 20 | 0 | 1 | STC WND | 03 New Sites ZNB017-Will remove from Scope ZDM194-area under planning, no available location ZBR136-ISR Submitted under STC RF Approval 01 Critical Sites 1 Rejected under Discussion
Submitted In IGATE | 242 | 241 | 1 | 40 | 40 | 0 | 20 | 19 | 1 | 2 | Vendor RF | 02 New Sites ZJZ531-uploaded under STC not TAWAL ZBR082-Residintial Area & no Baladiyah land 02 Under upload
Approved in IGATE RF | 241 | 231 | 10 | 40 | 40 | 0 | 19 | 17 | 2 | 12 | STC WND | 11 New Sites 8 Sites-Under Requester ZJB108-Rejected 2 Sites-Under RF Team leader 6 Critical Site 6 Under Approving
Approved in IGATE SAQ | 231 | 228 | 3 | 40 | 40 | 0 | 17 | 17 | 0 | 3 | Vendor SA | ZMC554-Under uploading more ISR
Private Sites
MOU Signed | 56 | 56 | 0 | 3 | 3 | 0 | 17 | 4 | 13 | 13 | Vendor SA | 6 Critical Sites 6 under uploading
MOU Submitted To TAWAL | 56 | 52 | 4 | 3 | 3 | 0 | 4 | 3 | 1 | 5 | Vendor SA | 10 New Sites 5 Sites-Under District Director & SA team leader 5 Sites-Under District Support | 75
Contract Draft | 52 | 46 | 6 | 3 | 3 | 0 | 3 | 3 | 0 | 6 | TAWAL Site Lease | 2 New Sites ZUZ039-Need to remove from Scope ZSK122-Waiting Contract from TAWAL | 58
Private Contract Singed by Tawal | 46 | 46 | 0 | 3 | 3 | 0 | 3 | 3 | 0 | 0 | TAWAL Site Lease
Private Contract Signed BY Owner | 46 | 45 | 1 | 3 | 3 | 0 | 3 | 3 | 0 | 1 | Vendor SA | 1 New Sites ZSR045-Owner refused to sign, under prepare Baladiyah Candidate 3 Critical Sites 2 under Owners Signature 1 Need modify the Location as agreed with Owner |  | 37
None Private Sites
Letter submitted to None Private | 171 | 171 | 0 | 37 | 37 | 0 | 12 | 12 | 0 | 0 | Vendor SA
Letter Approved by None Private | 171 | 171 | 0 | 37 | 37 | 0 | 12 | 12 | 0 | 0 | Vendor SA
None Private Contract Issued | 171 | 20 | 151 | 40 | 40 | 0 | 12 | 1 | 11 | 162 |  | 6 Tathmeen Issued 4 under issue the Contract & 2 Under Reduce Price |  | 10
None Private Contract Submitted to TAWAL | 171 | 94 | 77 | 37 | 37 | 0 | 12 | 1 | 11 | 88 | Vendor SA | 133 New Sites 4 Under Baladiyah to Modify as TAWAL Request 134 Under Process 22 Critical Sites 4 On Hold 18 Under Process
None Private Contract Singed by TAWAL | 94 | 92 | 2 | 37 | 37 | 0 | 1 | 0 | 1 | 3 | TAWAL Site Lease | 11 New Sites 6 Under TAWAL Signature 3 Baladiyah Rejected to reduce the Price 2 Under Reduce Price
Contract Signed by None Private | 92 | 55 | 37 | 37 | 37 | 0 | 0 | 0 | 0 | 37 | Vendor SA
Permits & HOC
BP Submitted | 100 | 103 | -3 | 40 | 40 | 0 | 3 | 2 | 1 | -2 | Vendor SA
FBP Received | 103 | 102 | 1 | 40 | 40 | 0 | 2 | 2 | 0 | 1 | Vendor SA
HO to CW | 102 | 138 | -36 | 40 | 40 | 0 | 2 | 2 | 0 | -36 | TAWAL SA
Total HO To CW Sites | [7 empty] | 160 |  |  | +20 COW Handed over

## Critical Sites GAP (hidden)
Aspiration Project
Deliverable | Critical Sites | [9 empty] | Responsibility Project
| Actual | Dammam | Arrar | Qassim | Hail | Jubail | Tabuk | Hofof | Hafr Batin | Northen Border
Design
Scope | 108 | 46 | 2 | 19 | 6 | 5 | 6 | 14 | 9 | 1 | STC WND
Approved in IGATE RF | 96 | 41 | 2 | 18 | 6 | 4 | 5 | 12 | 8 | 0 | STC WND
Approved in IGATE Vendor SAQ | 96 | 41 | 2 | 18 | 6 | 4 | 5 | 12 | 8 | 0 | Vendor SA
Private Sites
MOU Signed | 32 | 6 | 2 | 12 | 2 | 0 | 2 | 5 | 3 | 0 | Vendor SA
MOU Submitted To TAWAL | 32 | 6 | 2 | 12 | 2 | 0 | 2 | 5 | 3 | 0 | Vendor SA
Contract Draft | 28 | 6 | 2 | 11 | 2 | 0 | 2 | 4 | 1 | 0 | TAWAL Site Lease
Private Contract Singed by Owner | 26 | 6 | 2 | 9 | 2 | 0 | 2 | 4 | 1 | 0 | Vendor SA
Private Contract Signed BY TAWAL | 28 | 6 | 2 | 11 | 2 | 0 | 2 | 4 | 1 | 0 | TAWAL Site Lease
None Private Sites
Letter submitted to None Private | 28 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Vendor SA
Letter Approved by None Private | 28 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Vendor SA
None Private Contract Singed by TAWAL | 28 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TAWAL Site Lease
Contract Signed by None Private | 28 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Vendor SA
Permits & HOC
BP Submitted | 54 | 34 | 2 | 9 | 2 | 0 | 2 | 4 | 1 | 0 | Vendor SA
FBP Received | 49 | 34 | 2 | 4 | 2 | 0 | 2 | 4 | 1 | 0 | Vendor SA
HO to CW | 49 | 34 | 2 | 4 | 2 | 0 | 2 | 4 | 1 | 0 | TAWAL SA

## Weekly Report (hidden)
New Sites
Work Type | Scope | Milestone | Actual | Status | 2019-04-19 | 2019-05-19 | 2019-06-19 | 2019-07-19 | 2019-08-19 | 2019-09-19 |  |  |  | 2019-10-19 | 2019-11-19 | 2019-12-19 | 2019-01-20 | 2019-02-20 | 2019-03-20 | 2019-04-20
[10 empty] | W1 | W2 | W3 | W4
New Site | 244 | BP Approved | 102 | Plan |  |  | 5 | 40 | 75 | 80 | 85 | 95 | 115 | 170 | 215 | 244
|  |  |  | Actual |  |  | 5 | 102 | 102
|  | HO | 138 | Plan |  |  | 5 | 40 | 75 |  |  |  | 115 | 170 | 215 | 244
|  |  |  | Actual |  |  | 5 | 138 | 138
[8 empty] | 35 | 35 |  |  |  | 40 | 55 | 45 | 29
Critical Sites
Work Type | Scope | Milestone | Actual | Status | 2019-04-19 | 2019-05-19 | 2019-06-19 | 2019-07-19 | 2019-08-19 |  |  |  | 2019-09-19 | 2019-10-19 | 2019-11-19 | 2019-12-19 | 2019-01-20 | 2019-02-20 | 2019-03-20 | 2019-04-20
New Site | 107 | BP Approved | 9 | Plan |  |  | 0 | 20 | 50 |  |  |  | 80 | 95 | 107
|  |  |  | Actual |  |  | 0 | 43 | 43
|  | HO | 9 | Plan |  |  | 0 | 20 | 50 |  |  |  | 80 | 95 | 107
|  |  |  | Actual |  |  | 0 | 43 | 43
[8 empty] | 20 | 30 |  |  |  | 30 | 15 | 12
[9 empty] | 125 |  |  |  | 195
107
18

## Sep target (hidden)
Sep Plan
91 | 91 | 91 | 91 | 91 | 85
Site ID | Region | Work Type | Comments | Owner | FD/FBP
ZBH631 | South | New | Alaqeq Baladih/FBP | Fahad | 2019-09-10
ZNN665 | South | New | Habona Baladih/FBP | Nawaf | 2019-09-10
ZBS340 | South | New | beasha Baladiah/Price issue | Need district support/Faisal
ZBS341 | South | New | beasha Baladiah/Price issue | Need district support/Faisal
ZBS115 | South | New | thania tbalah Baladiah/Price issue | Need district support/Faisal
ZSR042 | South | New | Shrora Baladih/Price issue | Abu Islam | 2019-09-27
ZJZ167 | South | New | Jazan Amanh/Tathmeen | Fahad | 2019-09-12
ZJZ169 | South | New | Jazan Amanh/Tathmeen | Fahad | 2019-09-12
ZJZ172 | South | New | Jazan Amanh/Tathmeen | Fahad | 2019-09-12
ZAB444 | South | New | Belgarn Baladih/Tathmeen | Fahad | 2019-09-17
ZAB391 | South | New | Rejal almaa/Contract | Fahad | 2019-09-16
ZBH587 | South | New | Militery/Contract | Fahad | 2019-09-20
ZNN676 | South | New | Militery BG/Contract | Nawaf | 2019-09-20
ZNN741 | South | New | Najran Amanh/Contract | Nawaf | 2019-09-12
ZNN763 | South | New | Najran Amanh/Contract | Nawaf | 2019-09-12
ZNM043 | South | New | MOA/Contract | Fahad | 2019-09-10
ZDM101 | East | New | contract under TAWAL to sign | Ali | 2019-09-10
ZDM107 | East | New | contract under TAWAL to sign | Ali | 2019-09-10
ZDM109 | East | New | under tathmeen / contract | ALI | 2019-09-17
ZDM119 | East | New | will transfer to tathmeen / contract | ALI | 2019-09-26
ZDM121 | East | New | under tathmeen / contract | ALI | 2019-09-17
ZDM136 | East | New | under tathmeen / contract | ALI | 2019-09-17
ZDM139 | East | New | need TAWAL approval the prices and RF approval the locatiopn | Ali | 2019-09-17
ZND196 | East | New | under tathmeen / contract | ALI | 2019-09-17
ZND271 | East | New | contract under TAWAL to sign | Ali | 2019-09-10
ZND370 | East | New | under tathmeen / contract | ALI | 2019-09-17
ZJB222 | East | New | contract | Faris | 2019-09-12
ZJB223 | East | New | contract under issued from TAWAL | Faris | 2019-09-30
ZHF292 | East | New | will transfer to tathmeen / contract | Salah | 2019-09-30
ZHF293 | East | New | will transfer to tathmeen / contract | Salah | 2019-09-30
ZND791 | East | New | contract / NG | Salah | 2019-09-25
ZHB031 | East | New | ( waiting Amanah Approval )will transfer to tathmeen / contract | Al hmidi | 2019-09-28
ZHB037 | East | New | will transfer to tathmeen / contract ( need RF approval ) | Al hmidi | 2019-09-28
ZHB043 | East | New | ( waiting Amanah Approval )will transfer to tathmeen / contract | Al hmidi | 2019-09-28
ZJB210 | East | New | under tathmeen / contract | Faris | 2019-09-15
ZHB055 | East | New | will transfer to tathmeen / contract | Al hmidi | 2019-09-28
ZHB899 | East | New | will transfer to tathmeen / contract | Al hmidi | 2019-09-28
ZHB936 | East | New | under tathmeen / contract | Al hmidi | 2019-09-28
ZND017 | East | New | under tathmeen / contract | ALI | 2019-09-28
ZND237 | East | New | under tathmeen / contract | ALI | 2019-09-28
ZHB027 | East | New | waiting letter from TAWAL | Al hmidi | 2019-09-17
ZHB028 | East | New | will transfer to tathmeen / contract | Al hmidi | 2019-09-25
ZNR028 | East | New | contract | Salah | 2019-09-18
ZNR029 | East | New | contract | Salah | 2019-09-18
ZHF245 | East | New | will transfer to tathmeen / contract | Salah | 2019-09-30
ZHF303 | East | New | will transfer to tathmeen / contract | Salah | 2019-09-30
ZHF342 | East | New | will transfer to tathmeen / contract | Salah | 2019-09-30
ZHF350 | East | New | will transfer to tathmeen / contract | Salah | 2019-09-30
ZKF067 | East | New | contract | Faris | 2019-09-25
ZKF072 | East | New | contract | Faris | 2019-09-25
ZKF078 | East | New | contract | Faris | 2019-09-25
ZTD003 | Central | New | 5% need add in contract , under Baladiyah | Algamdi | 2019-09-12
ZBK030 | Central | New | Edit Thmeen to 30K | Suliman | 2019-09-05
ZAZ028 | Central | New | Contract under Tawal signature | Algamdi | 2019-09-01
ZBR146 | Central | New | Contract High price 65K need Tawal reduce price | Ahmed Sughair | 2019-09-19
ZBR120 | Central | New | Contract High price 70K need Tawal reduce price | Ahmed Sughair | 2019-09-19
ZAZ013 | Central | New | Letter under Riyadh الخدمات المساندة | Algamdi | 2019-09-18
ZUZ039 | Central | New | ISR for praivte and MOU | Suliman | 2019-09-04
ZRN026 | Central | New | Contract under Tawal negotiation | Algamdi | 2019-09-11
ZRN027 | Central | New | Contract under Tawal negotiation | Algamdi | 2019-09-11
ZRN028 | Central | New | Contract under Tawal negotiation | Algamdi | 2019-09-11
ZQU032 | North | New | Contract under Tawal /Site apply for FBP | Sultan | 2019-09-04
ZQU037 | North | New | Contract under Baladiyah | Sultan | 2019-09-17
ZQU970 | North | New | Contract under Baladiyah | Sultan | 2019-09-17
ZTB036 | North | New | Contract under Uni | Hatim | 2019-09-04
ZTB111 | North | New | Contract under Uni | Hatim | 2019-09-04
ZTB384 | North | New | Contract under Uni | Hatim | 2019-09-04
ZQU041 | North | New | Contract under Tawal /Site apply for FBP | Sultan | 2019-09-04
ZSK117 | North | New | Contract under Baladiyah | Sultan | 2019-09-11
ZRR027 | North | New | Contract under reduce price | Sultan | 2019-09-05
ZTB402 | North | New | Contract under NB | Hatim | 2019-09-10
ZRR031 | North | New | Contract under Uni | Sultan | 2019-09-12
ZTR088 | North | New | Contract under Tawal signature | Sultan | 2019-09-04
ZSK122 | North | New | Need Contract from Tawal | Sultan | 2019-09-09
ZTB132 | North | New | Need Contract from Tawal | Hatim | 2019-09-19
ZTB399 | North | New | Contract under Baladiyah / Tabouk Ammanh issue | Hatim | 2019-09-19
ZTB400 | North | New | Contract under Baladiyah / Tabouk Ammanh issue | Hatim | 2019-09-19
ZTB431 | North | New | Contract under Baladiyah / Tabouk Ammanh issue | Hatim | 2019-09-19
ZTB433 | North | New | Contract under Baladiyah / Tabouk Ammanh issue | Hatim | 2019-09-19
ZDB084 | North | New | Contract under Baladiyah / Tabouk Ammanh issue | Hatim | 2019-09-19
ZTY009 | North | New | Contract under Baladiyah / Tabouk Ammanh issue | Hatim | 2019-09-19
ZHA489 | North | New | Contract under Baladiyah | Abdulaziz | 2019-09-04
ZHA348 | North | New | Contract under Baladiyah | Abdulaziz | 2019-09-04
ZHA324 | North | New | Contract under Baladiyah | Abdulaziz | 2019-09-04
ZHA308 | North | New | Contract under Baladiyah | Abdulaziz | 2019-09-04
ZHA270 | North | New | Contract under Baladiyah | Abdulaziz | 2019-09-04
ZHA475 | North | New | Contract under Baladiyah | Abdulaziz | 2019-09-04
ZHA926 | North | New | Contract under Baladiyah | Abdulaziz | 2019-09-04
ZHA320 | North | New | Contract under Baladiyah | Abdulaziz | 2019-09-11
ZHA330 | North | New | Contract under Baladiyah | Abdulaziz | 2019-09-11
ZHA904 | North | New | Contract under Uni | Abdulaziz | 2019-09-11
ZTB437 | North | New |  | Hatim | 2019-09-01
ZHQ037 | North | New |  | Hatim | 2019-09-01
ZQW937 |  |  |  |  | 2019-09-01
ZAR022 |  |  |  |  | 2019-09-01
ZTB134 |  |  |  |  | 2019-09-01
ZTB390 |  |  |  |  | 2019-09-01
ZSK100

## Sheet3 (hidden)
Deliverable |  | Design | Scope | JISOW | SSO Submitted | SSO Approved | ISR Submitted | ISR Approved | Submitted In IGATE | Approved in IGATE RF | Approved in IGATE SAQ | Private Sites | MOU Signed | MOU Submitted To TAWAL | Contract Draft | Private Contract Singed by Owner | Private Contract Signed BY TAWAL | None Private Sites | Letter submitted to None Private | Letter Approved by None Private Received by Tawal | None Private Contract Issued | None Private Contract Submitted to TAWAL | None Private Contract Singed by TAWAL | None Private Contract Signed by None Private | Permits & HOC | BP Submitted | FBP Received | HO to CW
New 222 Sites | Plan |  | 256 | 243 | 243 | 243 | 241 | 241 | 190 | 187 | 157 |  | 34 | 34 | 27 | 24 | 24 |  | 123 | 123 | 123 | #REF! | 39 | 45 |  | 54 | 54 | 29
| Actual |  | 243 | 243 | 243 | 241 | 241 | 190 | 187 | 157 | 157 |  | 34 | 27 | 24 | 22 | 24 |  | 123 | 123 | #REF! | 42 | 32 | 39 |  | 54 | 29 | 28
| GAP |  | 13 | 0 | 0 | 2 | 0 | 51 | 3 | 30 | 0 |  | 0 | 7 | 3 | 2 | 0 |  | 0 | 0 | #REF! | #REF! | 7 | 6 |  | 0 | 25 | 1
| District | Design | Scope | JISOW | SSO Submitted | SSO Approved | ISR Submitted | ISR Approved | Submitted In IGATE | Approved in IGATE RF | Approved in IGATE SAQ | Private Sites | MOU Signed | MOU Submitted To TAWAL | Contract Draft | Private Contract Singed by Owner | Private Contract Signed BY TAWAL | None Private Sites | Letter submitted to None Private | Letter Approved by None Private Received by Tawal | None Private Contract Issued | None Private Contract Submitted to TAWAL | None Private Contract Singed by TAWAL | None Private Contract Signed by None Private | Permits & HOC | BP Submitted | FBP Received | HO to CW
Dammam
Qassim
Hail
Jubail
Tabuk
Hofof
Hafr Batin
Arrar
Riyadh District
Northern Border
Najran
Baha
Jizan
Total
Critical 106 Sites | Plan |  | 106 | 103 | 62 | 62 | 62 | 55 | 50 | 41 | 36 |  | 16 | 9 | 9 | 0 | 0 |  | 19 | 19 | 19 | 0 | 0 | 0 |  | 0 | 0 | 0
| Actual |  | 103 | 62 | 62 | 62 | 55 | 50 | 41 | 36 | 35 |  | 9 | 9 | 0 | 0 | 0 |  | 19 | 19 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
| GAP |  | 3 | 41 | 0 | 0 | 7 | 5 | 9 | 5 | 1 |  | 7 | 0 | 9 | 0 | 0 |  | 0 | 0 | 19 | 0 | 0 | 0 |  | 0 | 0 | 0
Total | Gap |  | 16 | 41 | 0 | 2 | 7 | 56 | 12 | 35 | 1 |  | 7 | 7 | 12 | 2 | 0 |  | 0 | 0 | #REF! | #REF! | 7 | 6 |  | 0 | 25 | 1
Responsibility |  |  | STC WND | STC WND | Vendor RF | STC WND | Vendor RF | STC WND | Vendor RF | STC WND | Vendor SA |  | Vendor SA | Vendor SA | TAWAL Site Lease | Vendor SA | TAWAL Site Lease |  | Vendor SA | Vendor SA |  |  | TAWAL Site Lease | Vendor SA |  | Vendor SA | Vendor SA | TAWAL SA
FC date |  |  | 14 New Sites 1 Under CR to remove remaining for Future Replacement Site 3 Critical Sites remaining Under Design Confirmation | Critical Sites (41) 41 Under Final Solution & CR |  | New Sites (2) Hold By RF STC to remove from JISOW 11/7 | 07 New Sites 07 Newly Added to Scope, Under Survey 10/7 07 Critical Sites 07 GOV under Survey 10/7 | 51 New Sites 51 Submitted under Approval 11/7 05 Critical Sites 5 Submitted under Approval 11/7 | 3 New Sites 3 will be uploaded in 10/7 9 Critical Sites 9 COW Sites no need SAQ | 30 New Sites 29 under Approving 11/7 1 Cancelled need to Remove From JISOW 9/7 5 Critical Sites under Approving 11/7 |  |  | 7 Under MOU Signature 8/7 | 7 New Sites 5 Under District Director Approval 2 Under RF to approve the New Shifted Location by owner 9/7 | 13 Waiting Contract from Procurement | 1 Under Owner Signature 14/7 1 (ZBR893) Manual Contract Signed by tawal & RF Rejected after Approval |  |  |  | 31 IBP & Tathmeen Issued 20 COW no Need SAQ Documents | 6 Tathmeen Issued 4 under issue the Contract & 2 Under Reduce Price | 3 Under Reduce Price 11/7 | Under TAWAL Signature | 6 Tathmeen Issued 4 under issue the Contract & 2 Under Reduce Price |  |  | 25 FBP Under Process
Risk

## Sheet2 (hidden)
New Sites - SAQ GAP (Scope: 275+20 COW , HOC: 3 )
Deliverable | New 222 Sites |  |  | Critical 106 Sites |  |  | Total | Responsibility | FC date | Risk
| Plan | Actual | GAP | Plan | Actual | GAP | Gap
Design
Scope | 256 | 243 | 13 | 106 | 103 | 3 | 16 | STC WND | 14 New Sites 1 Under CR to remove remaining for Future Replacement Site 3 Critical Sites remaining Under Design Confirmation
JISOW | 243 | 243 | 0 | 103 | 62 | 41 | 41 | STC WND | Critical Sites (41) 41 Under Final Solution & CR
SSO Submitted | 243 | 243 | 0 | 62 | 62 | 0 | 0 | Vendor RF
SSO Approved | 243 | 241 | 2 | 62 | 62 | 0 | 2 | STC WND | New Sites (2) Hold By RF STC to remove from JISOW 11/7
ISR Submitted | 241 | 241 | 0 | 62 | 55 | 7 | 7 | Vendor RF | 07 New Sites 07 Newly Added to Scope, Under Survey 10/7 07 Critical Sites 07 GOV under Survey 10/7
ISR Approved | 241 | 190 | 51 | 55 | 50 | 5 | 56 | STC WND | 51 New Sites 51 Submitted under Approval 11/7 05 Critical Sites 5 Submitted under Approval 11/7
Submitted In IGATE | 190 | 187 | 3 | 50 | 41 | 9 | 12 | Vendor RF | 3 New Sites 3 will be uploaded in 10/7 9 Critical Sites 9 COW Sites no need SAQ
Approved in IGATE RF | 187 | 157 | 30 | 41 | 36 | 5 | 35 | STC WND | 30 New Sites 29 under Approving 11/7 1 Cancelled need to Remove From JISOW 9/7 5 Critical Sites under Approving 11/7
Approved in IGATE SAQ | 157 | 157 | 0 | 36 | 35 | 1 | 1 | Vendor SA
Private Sites
MOU Signed | 34 | 34 | 0 | 16 | 9 | 7 | 7 | Vendor SA | 7 Under MOU Signature 8/7
MOU Submitted To TAWAL | 34 | 27 | 7 | 9 | 9 | 0 | 7 | Vendor SA | 7 New Sites 5 Under District Director Approval 2 Under RF to approve the New Shifted Location by owner 9/7
Contract Draft | 27 | 24 | 3 | 9 | 0 | 9 | 12 | TAWAL Site Lease | 13 Waiting Contract from Procurement
Private Contract Singed by Owner | 24 | 22 | 2 | 0 | 0 | 0 | 2 | Vendor SA | 1 Under Owner Signature 14/7 1 (ZBR893) Manual Contract Signed by tawal & RF Rejected after Approval
Private Contract Signed BY TAWAL | 24 | 24 | 0 | 0 | 0 | 0 | 0 | TAWAL Site Lease
None Private Sites
Letter submitted to None Private | 123 | 123 | 0 | 19 | 19 | 0 | 0 | Vendor SA
Letter Approved by None Private Received by Tawal | 123 | 123 | 0 | 19 | 19 | 0 | 0 | Vendor SA | 31 IBP & Tathmeen Issued 20 COW no Need SAQ Documents
None Private Contract Issued | 123 | #REF! | #REF! | 19 | 0 | 19 | #REF! |  | 6 Tathmeen Issued 4 under issue the Contract & 2 Under Reduce Price
None Private Contract Submitted to TAWAL | #REF! | 42 | #REF! | 0 | 0 | 0 | #REF! |  | 3 Under Reduce Price 11/7
None Private Contract Singed by TAWAL | 39 | 32 | 7 | 0 | 0 | 0 | 7 | TAWAL Site Lease | Under TAWAL Signature
None Private Contract Signed by None Private | 45 | 39 | 6 | 0 | 0 | 0 | 6 | Vendor SA | 6 Tathmeen Issued 4 under issue the Contract & 2 Under Reduce Price
Permits & HOC
BP Submitted | 54 | 54 | 0 | 0 | 0 | 0 | 0 | Vendor SA
FBP Received | 54 | 29 | 25 | 0 | 0 | 0 | 25 | Vendor SA | 25 FBP Under Process
HO to CW | 29 | 28 | 1 | 0 | 0 | 0 | 1 | TAWAL SA

## Sheet1 (hidden)
Site ID |  | Site Owner | Clutter Type | Request Number | Email | Latitude | Longitude | Clutter Type |  |  | Site ID | Region | District | City | Latitude | Longitude | Scope Status | Optimization Feedback
ZAB391 | #REF! | شركة أبراج الاتصالات المحدودة | Rural | SNR1010041 | saqhua@stc.com.sa | 18.0735 | 42.2224 |  |  |  | ZAQ046 | Eastern | Dammam | أرامكو | 25.9396 | 49.6797 | Replacement for Critical Site ZAQ029 | ok
ZJB234 | #REF! | شركة أبراج الاتصالات المحدودة | Rural | SNR1010414 | saqhua@stc.com.sa | 27.0937 | 49.0888 |  |  |  | ZDH026 | Eastern | Dammam | أرامكو | 26.3119 | 50.1411 | Replacement for Critical Site ZDH010 | Inside the KFUPM and should not be any restriction there
ZTB402 | #REF! | شركة أبراج الاتصالات المحدودة | Rural | SNR1010511 | saqhua@stc.com.sa | 28.0282 | 34.6315 |  |  |  | ZDH027 | Eastern | Dammam | أرامكو | 26.3232 | 50.1094 | Replacement for Critical Site ZDH015 | Ok but it is better to the replacement will be very close to ZND586 and it is better to change the location
ZJB229 | #REF! | شركة أبراج الاتصالات المحدودة | Rural | SNR1010383 | saqhua@stc.com.sa | 27.1068 | 49.0316 |  | داخل الحي السكني | Urban | ZDM191 | Eastern | Dammam | حرس وطني | 26.3545 | 50.1773 | Replacement for Critical Site ZDM082 | ok
ZNN665 | #REF! | شركة أبراج الاتصالات المحدودة | Rural | SNR1010038 | saqhua@stc.com.sa | 17.83 | 44.0364 |  | في ضواحي المدن | Sub urban | ZKU061 | Eastern | Dammam | محطة الكهرباء | 25.831 | 50.1325 | Replacement for Critical Site ZHF089 | ok
ZAZ028 | #REF! | شركة أبراج الاتصالات المحدودة | Rural | SNR1010241 | saqhua@stc.com.sa | 26.3073 | 44.9166 |  | طرق الخارجيه بين المدن | Rural | ZDM080 | Eastern | Dammam | المباحث العامة | 26.3325 | 49.9605 | New Site | ok
ZKU046 | #N/A | شركة أبراج الاتصالات المحدودة | Rural | SNR1009792 | saqhua@stc.com.sa | 26.1486 | 50.1176 |  |  |  | ZDH002 | Eastern | Dammam | ارامكو بالمنطقة الشرقية | 26.2648 | 50.068 | New Site | ok
ZDM135 | #N/A | شركة أبراج الاتصالات المحدودة | Rural | SNR1009866 | saqhua@stc.com.sa | 26.3639 | 50.2286 |  |  |  | ZDM033 | Eastern | Dammam | الحرس الوطني | 26.3688 | 50.1598 | New Site | ok
ZBS323 | #N/A | شركة أبراج الاتصالات المحدودة | Rural | SNR1010284 | saqhua@stc.com.sa | 19.8574 | 42.4195 |  |  |  | ZND791 | Eastern | Dammam | المدينة السكنية بالحرس الوطني | 26.3681 | 50.169 | New Site | ok
ZJB210 | #REF! | شركة أبراج الاتصالات المحدودة | Rural | SNR1010322 | saqhua@stc.com.sa | 26.8621 | 49.7774 |  |  |  | ZHF341 | Eastern | Hofof | أرامكو | 24.0652 | 49.2012 | Replacement for Critical Site ZHF125 | ok
ZJZ068 | #REF! | شركة أبراج الاتصالات المحدودة | Rural | SNR1010222 | saqhua@stc.com.sa | 16.8139 | 42.9084 |  |  |  | ZHF345 | Eastern | Hofof | جامعة الملك فيصل | 25.3442 | 49.5948 | Replacement for Critical Site ZHF774 | There shouldn’t be any restriction
ZNM043 | #REF! | شركة أبراج الاتصالات المحدودة | Rural | SNR1010411 | saqhua@stc.com.sa | 19.2504 | 42.0697 |  |  |  | ZHF348 | Eastern | Hofof | حرس وطني | 25.4552 | 49.518 | Replacement for Critical Site ZHF871 | ok
ZRR031 | #REF! | شركة أبراج الاتصالات المحدودة | Rural | SNR1010416 | saqhua@stc.com.sa | 31.0264 | 40.9032 |  |  |  | ZHF279 | Eastern | Hofof | الحرس الوطني | 25.4751 | 49.51 | New Site | ok
ZRN027 | #REF! | شركة أبراج الاتصالات المحدودة | Rural | SNR1010393 | saqhua@stc.com.sa | 25.6438 | 46.8299 |  |  |  | ZHF294 | Eastern | Hofof | الحرس الوطني | 25.4535 | 49.5039 | New Site | ok
[11 empty] | ZHF296 | Eastern | Hofof | الحرس الوطني | 25.4666 | 49.5189 | New Site | ok
[11 empty] | ZHF203 | Eastern | Hofof | NG | 25.463 | 49.5071 | New Site | ok
[11 empty] | ZHF202 | Eastern | Hofof | NG | 25.435 | 49.511 | New Site | ok
[11 empty] | ZJB157 | Eastern | Jubail | الهيئة الملكية بالجبيل | 27.1063 | 49.5101 | New Site | There shouldn’t be any restriction
[11 empty] | ZJB175 | Eastern | Jubail | الهيئة الملكية بالجبيل | 27.105 | 49.529 | New Site | There shouldn’t be any restriction
[11 empty] | ZJB222 | Eastern | Jubail | قاعدة الملك عبدالعزيز البحرية بالجبيل | 27.0031 | 49.3948 | New Site | ok
[11 empty] | ZJB805 | Eastern | Jubail | RC | 27.1678 | 49.5406 | New Site | There shouldn’t be any restriction
[11 empty] | ZTR045 | Northern | Northern Border | هيئة مدن | 31.7758 | 39.0199 | New Site | ok
[11 empty] | ZTR053 | Northern | Northern Border | هيئة مدن | 31.6594 | 38.8759 | New Site | ok
[11 empty] | ZBR185 | Central | Qassim | صرف الصحي | 26.3928 | 44.0138 | Replacement for Critical Site ZBR042 | ok
[11 empty] | ZBR178 | Central | Qassim | الحرس الوطني | 26.3272 | 43.7781 | New Site | ok
[11 empty] | ZHA330 | Central | Hail | وزارة الاسكان بمنطفة حائل | 27.507 | 41.7666 | New Site | ok