## Slide 1
Weekly CFO Meeting
(Aspiration)

## Slide 2
Nokia Remaining Doable New site scope & Hand Over Forecast
Sites Scope Handover Timeline (Nokia) |  |  |  |  |  | 
Remaining New site scope | Total Scope 276 | Site Scope |  | Deadline | Revise Deadline | Remark
 |  | Remaining Sites 08 Sites | Old Scope 03 Sites | 15-Aug-20 | 29-Jul-21 | 01 MD Site, Under Evaluation from Amana. 01 MK-Rabigh Site, Under apply through New Baladi System. 01 Taif Site, Under Confirmation from Amana for MOT Approval
 |  |  | Rep. Newly Added 05 Sites | Added in 2021 | 29-Jul-21 | 01 Assir Site, Under LA issuance from Amana 01 MD Site, Newly Added, under Letter Submission to Amana 01 MK-Khulas Site, Under apply through New Baladi System. 02 Taif Sites, 01 Gov. Site, Waiting Feedback from University to issua LA or Apply Tender. 01 Newly Added, under Remove from Scope (LA Renewd of Existing Site)

## Slide 3
Aspiration SAQ Site list Details
Site ID | District | Sub-Scope | Owner's Name | Owner Type | Last Status | Category | Action Owner | JISOW Scope Date | Site Category
PMD892 | Madinah | Rep. | Municipality | Baladiya | The spatial approval of the construction agency has been approved, and the site evaluation is awaiting | Contract issuance and valuation | NOKIA | 3-Jul-19 | Old Scope 03 Sites
ZMK657 | MK-Rabigh | New | Obaid Al Yubi | Private | Waiting for the authorization of the engineering office on my new system by Tawal | FBP Issuance | TAWAL | 20-Sep-20 | 
ZTF438 | Taif | New | Municipality | Baladiya | Waiting for the final response from the municipality to need approval from the Ministry of Transportation | Preliminary approval | NOKIA | 31-Jan-19 | 
ZKH516 | Assir | New | Municipality | Baladiya | Waiting for the contracts to be issued by the municipality | Contract issuance and valuation | NOKIA | 12-Sep-21 | Rep. Newly Added 06 Sites
ZMM846 | Madinah | New | Municipality | Baladiya | Waiting for the letter to be received from Tawal to submit the signed request from the Secretariat | Contract issuance and valuation | TAWAL | 12-Sep-21 | 
ZKL011 | MK-Khulas | New | Sami Al Me’abed | Private | Waiting for the authorization of the engineering office on the new system by Tawal | FBP Issuance | TAWAL | 9-Feb-21 | 
ZTF501 | Taif | New | University | Gov | Waiting for the investment committee's response on the issuance of contracts or the launch of a new tender | Contract issuance and valuation | TAWAL | 5-Apr-21 | 
ZTF275 | Taif | Rep. | TBD | TBD | The contract with the previous owner has been renewed and the site is being taken out of the project | Remove from Project | TAWAL | 12-Sep-21 | 

## Slide 4
Makkah Aspiration SAQ Site list Details
Owner Type | High Category | Total
Private | Applied on FURAS System, Waiting SADAD Issuance | 4
Private Total |  | 4
Amana | FBP SADAD Done, Under FBP Issuance Manual | 3
 | Applied on FURAS System, under System Process | 9
Amana Total |  | 12
Grand Total |  | 16

## Slide 5
Makkah Aspiration SAQ Site list Details
Site ID | Owner Type | Owner Name | High Category | Site current stage | Daily update | Application Number | Update on system
ZMC513 | Private | Khaled Al Srihi | Private FBP under process | Payment of fees | The application submitted in system and is awaiting issuance of payment fees | CTL-21-09-000268 | Waiting for investigation
PMK488 | Private | Naser Alhibi | Private FBP under process | Payment of fees | The application submitted in system and is awaiting issuance of payment fees | CTL-21-09-000260 | Waiting for investigation
ZMC499 | Private | Nasem Sendi | Private FBP under process | Payment of fees | The application submitted in system and is awaiting issuance of payment fees | CTL-21-09-000264 | Waiting for investigation
ZMC500 | private | Jamil Sawat | Private FBP under process | Payment of fees | The application submitted in system and is awaiting issuance of payment fees | CTL-21-09-000288 | Waiting for investigation
ZMC686 | Amana | Municipality | Under FBP Signing | License approval | Manual issuance of the license is in progress | NA | NA
ZMC696 | Amana | Municipality | Under FBP Signing | License approval | Manual issuance of the license is in progress | NA | NA
ZMC541 | Amana | Municipality | Under FBP Signing | License approval | Manual issuance of the license is in progress | NA | NA
ZMC494 | Amana | Municipality | Under LA Issuance & Payment | Contract issuance and assignment | The contract requested in system, under follow-up | CTR-21-10-000456 | Under study by land official
ZMC497 | Amana | Municipality | Under LA Issuance & Payment | Contract issuance and assignment | The contract requested in system, under follow-up | CTR-21-10-000453 | Under study by land official
ZMC665 | Amana | Municipality | Under LA Issuance & Payment | Contract issuance and assignment | The contract requested in system, under follow-up | CTR-21-10-000451 | Under study by land official
ZMC325 | Amana | Municipality | Under LA Issuance & Payment | Contract issuance and assignment | The contract requested in system, under follow-up | CTR-21-10-000450 | Under study by land official
ZMC925 | Amana | Municipality | Under LA Issuance & Payment | Contract issuance and assignment | The contract requested in system, under follow-up | CTR-21-10-000454 | Under study by land official
ZMK569 | Amana | Municipality | Under LA Issuance & Payment | Contract issuance and assignment | The contract requested in system, under follow-up | CTR-21-10-000449 | Under study by land official
ZMC660 | Amana | Municipality | Under LA Issuance & Payment | Contract issuance and assignment | The contract requested in system, under follow-up | CTR-21-10-000452 | Under study by land official
ZMC544 | Amana | Municipality | Under LA Issuance & Payment | Contract issuance and assignment | The contract requested in system, under follow-up | CTR-21-10-000457 | Under study by land official
ZMC543 | Amana | Municipality | Under LA Issuance & Payment | Contract issuance and assignment | The contract requested in system, under follow-up | CTR-21-10-000455 | Under study by land official

## Slide 6
Thank
You