## sql_statement
42 | 42 | 42 | 42 | 42 | 42 | 42 | 1 | 42 | 42 | 12 | 42 | 11 | 37 | 20 | 38 | 28 | 5 | 23 | 42 | 31 | 10 | 15 | 17 | 42 | 42
Name | Nominal Long | Nominal Lat | District | Area | TL | Priority | Action done | Survey Date | Survey done | Comments | حالة الموقع | Remarks | Survey Date | Re Plan Survey | # Of Candidates | # of RT from Cand. | # of Sharing | # of GF | # Of SAR | SAR Submitted | Need Letter | Direction in Letter | Remark | Formula | Last Update
JED0972 | 21.5343 | 39.2184 | Jeddah | Jaddah | Fouad | P0 |  | 2021-04-10 | Done | Need Letter for NG | الحرس الوطني | Need Letter | 2021-04-10 |  | 3 | 1 |  | 2 | 3 | Yes |  | سعادة وكيل وزارة الحرس الوطني | SAR's Submitted | SAR Submitted | SAR Submitted waiting feedback
JED2085 | 21.613 | 39.197 | Jeddah | Jaddah | Fouad | Done | SAR received | Done Before | Done by other | [14 empty] | Done by other | Done by other
JED2170 | 21.3832 | 39.2913 | Jeddah | Jaddah | Fouad | Done | SAR received | Done Before | Done by other | [14 empty] | Done by other | Done by other
JED2171 | 21.4713 | 39.3729 | Jeddah | Jaddah | Fouad | Done | SAR received | Done Before | Done by other | [14 empty] | Done by other | Done by other
JED2172 | 21.455 | 39.3944 | Jeddah | Jaddah | Fouad | Done | SAR received | Done Before | Done by other | [14 empty] | Done by other | Done by other
JED2704 | 21.62 | 39.2032 | Jeddah | Jaddah | Fouad | P0 |  | 2021-04-11 | Access | Need Letter for Security Gard | قوى الامن | Need Letter | 2021-04-11 |  | 1 | 0 |  | 1 | 0 |  | Yes | سعادة مدير إسكان قوى الامن الداخلي بمدينة جدة |  | Letter under submitted | Letter Received under Submission
JED2184 | 21.574 | 39.1856 | Jeddah | Jaddah | Fouad | Done | SAR received | Done Before | Done by other | [14 empty] | Done by other | Done by other
JED2205 | 21.6089 | 39.2345 | Jeddah | Jaddah | Fouad | P2 |  | 2021-04-12 | Done | Need Authority Letter | ممكن حيازته |  | 2021-04-12 |  | 1 |  |  | 1 | 1 | Yes |  | مطلوب خطاب التفويض للموظف ليتم عمل مسح واخذ صور من الاسطح |  | SAR Submitted | SAR Submitted waiting feedback
JED2264 | 21.492 | 39.2596 | Jeddah | Jaddah | Fouad | P0 |  | 2021-04-11 | Access | Need Letter for Uni. | جامعة الملك عبدالعزيز | Need Letter | 2021-04-11 |  | 1 | 0 |  | 1 | 1 | Yes | Yes | السادة جامعة الملك عبد العزيز إدارة الاستثمار |  | SAR Submitted | SAR Submitted waiting feedback
JED2262 | 21.5433 | 39.1922 | Jeddah | Jaddah | Fouad | Done | SAR received | Done Before | Done by other | [14 empty] | Done by other | Done by other
JED2263 | 21.5535 | 39.2482 | Jeddah | Jaddah | Fouad | Done | SAR received | Done Before | Done by other | [14 empty] | Done by other | Done by other
JED2267 | 21.5903 | 39.2513 | Jeddah | Jaddah | Fouad | Done | SAR received | Done Before | Done by other | [14 empty] | Done by other | Done by other
JED2269 | 21.6234 | 39.1409 | Jeddah | Jaddah | Fouad | Done | SAR received | Done Before | Done by other | [14 empty] | Done by other | Done by other
JED2561 | 21.54 | 39.2933 | Jeddah | Jaddah | Fouad | Done | SAR received | Done Before | Done by other | [14 empty] | Done by other | Done by other
JED2083 | 21.5553 | 39.1512 | Jeddah | Jaddah | Fouad | P0-Onging | Ongoing, FCD 10/4 |  | Done by other | [14 empty] | Done by other | Done by other
JED2563 | 21.6119 | 39.2099 | Jeddah | Jaddah | Fouad | Done | SAR received | Done Before | Done by other | [14 empty] | Done by other | Done by other
JED2565 | 21.6645 | 39.1186 | Jeddah | Jaddah | Fouad | Done | SAR received | Done Before | Done by other | [14 empty] | Done by other | Done by other
JED2567 | 21.4683 | 39.2828 | Jeddah | Jaddah | Fouad | Done | SAR received | Done Before | Done by other | [14 empty] | Done by other | Done by other
JED2568 | 21.4561 | 39.2514 | Jeddah | Jaddah | Fouad | Done | SAR received | Done Before | Done by other | [14 empty] | Done by other | Done by other
JED2569 | 21.454 | 39.2554 | Jeddah | Jaddah | Fouad | Done | SAR received | Done Before | Done by other | [14 empty] | Done by other | Done by other
JED0991 | 21.2879 | 39.2711 | Jeddah | Jaddah | Fouad | P0-Onging | Ongoing, FCD 10/4 |  | Done by other | [14 empty] | Done by other | Done by other
JED2570 | 21.4644 | 39.2453 | Jeddah | Jaddah | Fouad | Done | SAR received | Done Before | Done by other | [14 empty] | Done by other | Done by other
JED2571 | 21.4844 | 39.268 | Jeddah | Jaddah | Fouad | Done | SAR received | Done Before | Done by other | [14 empty] | Done by other | Done by other
JED2572 | 21.4799 | 39.2739 | Jeddah | Jaddah | Fouad | Done | SAR received | Done Before | Done by other | [14 empty] | Done by other | Done by other
JED2662 | 21.4608 | 39.3534 | Jeddah | Jaddah | Fouad | P2-Ongoing | Ongoing, FCD 10/4 |  | Done by other | [14 empty] | Done by other | Done by other
JED2645 | 21.4687 | 39.3306 | Jeddah | Jaddah | Fouad | P2-Ongoing | Ongoing, FCD 10/4 |  | Done by other | [14 empty] | Done by other | Done by other
JED2686 | 21.7474 | 39.2073 | Jeddah | Jaddah | Fouad | JR | JR | 2021-04-18 | under Plan |  | ممكن حيازته |  | 2021-04-20 | 2021-04-20 | 2 |  |  | 2 | 2 | Yes |  | مطلوب خطاب التفويض للموظف ليتم عمل مسح واخذ صور من الاسطح |  | SAR Submitted | SAR Submitted waiting feedback
JED2680 | 21.4826 | 39.3747 | Jeddah | Jaddah | Fouad | P2-Ongoing | Ongoing, FCD 10/4 |  | Done by other | [14 empty] | Done by other | Done by other
JED2663 | 21.4687 | 39.3836 | Jeddah | Jaddah | Fouad | P2-Ongoing | Ongoing, FCD 10/4 |  | Done by other | [14 empty] | Done by other | Done by other
JED2573 | 21.486 | 39.3575 | Jeddah | Jaddah | Fouad | P2 |  | 2021-04-19 | under Plan |  | ممكن حيازته |  |  | 2021-04-22 | 1 |  |  | 1 | 1 | Yes |  |  | منطقة بدون صكوك | SAR Submitted | SAR Submitted waiting feedback
JED2666 | 21.4369 | 39.3995 | Jeddah | Jaddah | Fouad | P2 |  | 2021-04-17 | under Plan |  | ممكن حيازته |  | 2021-04-17 | 2021-04-20 | 0 | 0 |  |  | 0 |  |  |  | منطقة لا يمكن حيازتها، تابعة لوقف عين العزيزية ولا صكوك لها سيتم إعادة مسح المنطقة بعد اصدار التفويض | JTR shared (Waqf al aziziah Area ) | Waqf al aziziah, Waiting Zain Feedback
JED2787 | 21.4581 | 39.3999 | Jeddah | Jaddah | Fouad | P2 |  | 2021-04-17 | under Plan |  | ممكن حيازته |  | 2021-04-17 | 2021-04-20 | 0 | 0 |  |  | 0 |  |  |  | منطقة لا يمكن حيازتها، تابعة لوقف عين العزيزية ولا صكوك لها سيتم إعادة مسح المنطقة بعد اصدار التفويض | JTR shared (Waqf al aziziah Area ) | Waqf al aziziah, Waiting Zain Feedback
JED0932 | 21.4797 | 39.2937 | Jeddah | Jaddah | Fouad | P0 |  | 2021-04-12 | Done | Need Letter for Waqf | ممكن حيازته |  | 2021-04-12 | 2021-04-20 | 1 | 0 | 1 |  | 1 | Yes |  |  | منطقة لا يمكن حيازتها، تابعة لوقف عين العزيزية ولا صكوك لها سيتم إعادة مسح المنطقة بعد اصدار التفويض | SAR Submitted | SAR Submitted waiting feedback
JED2647 | 21.5095 | 39.3293 | Jeddah | Jaddah | Fouad | P2 |  | 2021-04-12 | Done | No Deed Area | ممكن حيازته |  | 2021-04-12 |  | 1 | 0 |  | 1 | 1 | Yes |  |  | منطقة بدون صكوك، جاري عمل JTR، مطلوب فورمة JTR زين | SAR Submitted | SAR Submitted waiting feedback
JED2702 | 21.5077 | 39.1827 | Jeddah | Jaddah | Fouad | Done | SAR received | Done Before | Done by other | [14 empty] | Done by other | Done by other
JED2684 | 21.8089 | 39.1312 | Jeddah | Jaddah | Fouad | P2 |  | 2021-04-18 | under Plan |  | ممكن حيازته |  | 2021-04-21 | 2021-04-21 | 3 | 2 |  | 1 | 2 | Yes |  |  | انتظار رد مالك مبنى ليتم تصوير السطح | SAR Submitted | SAR Submitted waiting feedback
JED2861 | 21.774 | 39.1769 | Jeddah | Jaddah | Fouad | P2 |  | 2021-04-18 | under Plan |  | ممكن حيازته |  | 2021-04-20 | 2021-04-19 | 3 | 2 |  | 1 | 3 | Yes |  | مطلوب خطاب التفويض للموظف ليتم عمل مسح واخذ صور من الاسطح |  | TSS JV Planed | TSS JV ongoing
JED2424 | 21.6152 | 39.2027 | Jeddah | Jaddah | Fouad | P0 |  | 2021-04-11 | Access | Need Letter for Security Gard | قوى الامن | Need Letter | 2021-04-11 |  | 1 | 0 |  |  | 0 |  | Yes | سعادة مدير إسكان قوى الامن الداخلي بمدينة جدة |  | Letter under submitted | Letter Received under Submission
JED2609 | 21.5343 | 39.2288 | Jeddah | Jaddah | Fouad | P0 |  | 2021-04-10 | Access | Need Letter for NG | الحرس الوطني | Need Letter | 2021-04-10 |  | 1 | 0 |  |  | 0 |  | Yes | سعادة وكيل وزارة الحرس الوطني |  | Letter under submitted | Letter Received under Submission
JED2717 | 21.5298 | 39.2236 | Jeddah | Jaddah | Fouad | P0 |  | 2021-04-10 | Access | Need Letter for NG | الحرس الوطني | Need Letter | 2021-04-10 |  | 1 | 0 |  |  | 0 |  | Yes | سعادة وكيل وزارة الحرس الوطني |  | Letter under submitted | Letter Received under Submission
JED2715 | 21.6692 | 39.1739 | Jeddah | Jaddah | Fouad | P0 |  | 2021-04-13 | under Plan |  | مطار جدة | Need Letter | 2021-04-13 |  | 1 | 0 |  |  | 0 |  | Yes | جاري الحصول على التوجيه |  | Waiting Letter for Jaddah Airport | Waiting Letter Stamp
JED2623 | 21.7464 | 39.1375 | Jeddah | Jaddah | Fouad | P0 |  | 2021-04-19 | under Plan |  | ممكن حيازته |  | 2021-04-12 | 2021-04-21 | 3 | 2 |  | 1 | 3 | Yes |  |  |  | SAR Submitted for new searching area | SAR Submitted Location Shifted
JED2788 | 21.721 | 39.1303 | Jeddah | Jaddah | Fouad | P0 |  | 2021-04-19 | under Plan |  | وزارة النقل |  | 2021-04-12 |  | 2 |  |  | 2 | 2 | Yes | Yes | امانة جدة |  | SAR Submitted | SAR Submitted waiting feedback
JED2602 | 21.7979 | 39.0708 | Jeddah | Jaddah | Fouad | P2 |  | 2021-04-13 | under Plan |  | ممكن حيازته |  | 2021-04-21 | 2021-04-21 | 3 | 2 |  | 1 | 3 | Yes |  |  |  | SAR Submitted | 2 SAR Private rejected, 1 SAR Amana waiting feedback
HAW2295 | 21.4549 | 40.5151 | Taif | Al Hawiah Taif | Fahad R. | P1 |  | 2021-04-11 | Rescheduled 13-Apr-21 |  | ممكن حيازته |  | 2021-04-13 |  | 3 | 2 |  | 1 | 3 | Yes |  |  | 2 خيارات ملاك سكني، جاري التأكد من إمكانية اصدار رخص لها | TSS JV Planed | TSS JV ongoing
MAK2128 | 21.4604 | 39.909 | Mekkah | Mekkah | Adnan | P1 |  | 2021-04-14 | under Plan |  | ممكن حيازته |  | 2021-04-18 | 2021-04-18 | 3 | 1 |  | 2 | 3 | Yes |  |  |  | SAR Submitted | SAR Submitted waiting feedback
TAF2288 | 21.23 | 40.4232 | Taif | Taif | Fahad R. | P1 |  | 2021-04-11 | Done | SAR Under Process, need Letter for Amana | حدبقة تابعة للامانة وممكن مشاركة مع STC | Need Letter | 2021-04-11 |  | 1 |  |  | 1 | 1 | Yes |  |  | SAR's Submitted | TSS JV Planed | TSS JV ongoing
MAK2247 | 21.4686 | 39.9299 | Mekkah | Mekkah | Adnan | P1 |  | 2021-04-14 | under Plan |  | ممكن حيازته |  | 2021-04-18 | 2021-04-18 | 2 | 1 |  | 1 | 2 | Yes |  |  |  | SAR Submitted | SAR Submitted waiting feedback
MAK2237 | 21.3743 | 39.7768 | Mekkah | Mekkah | Adnan | P1 |  | 2021-04-17 | under Plan |  | ممكن حيازته |  | 2021-04-17 |  | 2 | 1 |  | 1 | 2 | Yes |  |  |  | SAR Submitted for new searching area | SAR Submitted Location Shifted
MAK2558 | 21.3739 | 39.8271 | Mekkah | Mekkah | Adnan | P1 |  | 2021-04-15 | under Plan |  | ممكن حيازته |  |  | 2021-04-22 |  | 2 |  |  | 2 | Yes |  |  | منطقة كلها شقق تمليك | SAR Submitted | SAR Ongoing
MAK2511 | 21.3619 | 39.8873 | Mekkah | Mekkah | Adnan | P1 |  | 2021-04-15 | under Plan |  | ممكن حيازته |  | 2021-04-15 |  | 1 | 1 |  |  | 1 | Yes |  |  |  | SAR Approved | SAR Approved waiting final feedback
MAK2234 | 21.3438 | 39.9053 | Mekkah | Mekkah | Adnan | P1 |  | 2021-04-15 | under Plan |  | ممكن حيازته |  | 2021-04-15 |  | 1 | 1 |  |  | 1 | Yes |  |  |  | SAR Submitted | SAR Submitted waiting feedback
MAK2091 | 21.5005 | 39.9502 | Mekkah | Mekkah | Adnan | P1 |  | 2021-04-14 | under Plan |  | ممكن حيازته |  | 2021-04-18 | 2021-04-18 | 3 | 2 |  |  | 2 | Yes |  |  |  | SAR Submitted | SAR Submitted waiting feedback
BSA0413 | 19.9943 | 42.6168 | Assir | Bisha | Shehri | P0 |  | 2021-04-21 | Rescheduled 21-Apr-21 |  | مطار بيشة | Need Letter |  | 2021-04-21 |  |  |  |  | 0 |  | Yes | مدير عام مطار بيشة |  | Letter under submitted | Letter Received under Submission
ZHR0388 | 17.5679 | 43.4557 | Assir | Dahran Al Janoub | Shehri | P0 |  | 2021-04-14 | Rescheduled 14-Apr-21 |  | ممكن حيازته |  | 2021-04-14 |  | 2 |  | 1 | 1 | 0 |  | Yes | سعادة قائد القوات البرية بالمنطقة الجنوبية بمدينة الملك فيصل العسكرية | تم مسح الموقع من قبل زين سابقا | Letter under submitted | Letter Received under Submission
TLT0324 | 19.5217 | 43.5331 | Assir | Tathleeth | Shehri | P0 |  | 2021-04-11 | Done | SAR Under Process | ممكن حيازته |  | 2021-04-11 |  | 3 | 2 |  | 1 | 3 | Yes |  |  | SAR's Submitted | Re-survey ongoing | SAR Submitted Location Shifted
KAC0453 | 22.5125 | 39.0971 | Jeddah | مدينة الملك عبد الله الاقتصادية | Fouad | P0 |  | 2021-04-13 | under Plan |  | مدينة الملك عبد الله الاقتصادية |  | 2021-04-13 |  | 1 |  | 1 |  | 1 | Yes |  |  |  | TSS Done | Sharing Mobily,TSS JV Done,Submission TSS
WDA0368 | 16.9631 | 47.0179 | Najran | Al wadiiah Sharorah | TBD | P0 |  | 2021-04-20 | under Plan |  | قاعدة عسكرية | Need Letter | [6 empty] | 0 |  |  | الهيئه العامه للجمارك |  | Letter under submitted | Letter Received under Submission
NJR0371 | 17.4466 | 44.7196 | Najran | Najran | TBD | P0 |  | 2021-04-21 | under Plan |  | منفذ حدودي | Need Letter | [6 empty] | 0 |  |  |  |  | Letter under submitted | Waiting Letter Signature & Stamp
BLS0345 | 18.7836 | 42.2542 | Assir | Ballasmar | Shehri | P0 |  | 2021-04-10 | Done | Need Letter for Hospital | ممكن حيازته |  | 2021-04-10 |  | 2 |  |  | 2 | 2 | Yes |  |  | SAR's Submitted | SAR Submitted | SAR Submitted waiting feedback
KMS0313 | 18.2712 | 42.765 | Assir | Khamis Mushait | Shehri | P1 |  | 2021-04-14 | under Plan |  | ممكن حيازته |  | 2021-04-19 | 2021-04-19 | 1 |  |  | 1 | 1 | Yes | Yes | مدينة الملك فيصل العسكريه بخميس مشيط |  | Letter under submitted | SAR Submitted, requested more options, Letter Received under Submission
KMS0440 | 18.3524 | 42.7573 | Assir | Khamis Mushait | Shehri | P1 |  | 2021-04-14 | under Plan |  | ممكن حيازته |  | 2021-04-19 | 2021-04-19 | 3 | 2 | 1 |  | 3 | Yes |  |  | تم تسليم 3 خيارات برقم الموقع القديم | TSS JV Planed | Sharing Mobily,TSS JV ongoing
ABH0342 | 18.2839 | 42.602 | Assir | Abha | Shehri | P1 |  | 2021-04-20 | under Plan |  | ممكن حيازته |  | 2021-04-20 | 2021-04-20 | 2 |  |  | 2 | 2 | Yes |  |  |  | SAR Submitted | SAR Submitted waiting feedback
ABH0341 | 18.2668 | 42.6412 | Assir | Abha | Shehri | P1 |  | 2021-04-20 | under Plan |  | ممكن حيازته |  | 2021-04-20 | 2021-04-21 | 2 | 1 |  | 1 | 2 | Yes |  |  | منطقة سكنية جميعها ملاك | SAR & JTR Submitted | SAR & JTR Submitted
ULY0209 | 19.5663 | 41.9556 | Assir | Sabt Al Alaya | Shehri | P1 |  | 2021-04-15 | under Plan |  | ممكن حيازته |  | 2021-04-15 |  | 1 | 1 |  |  | 1 | Yes |  |  | SAR's Submitted تم الاتفاق على الموقع من قبل زين والتصميم | SAR & JTR Submitted | SAR Submitted, requested more 2 RT options, JTR Submitted
MHL0337 | 18.5437 | 42.0384 | Assir | Mahail | Shehri | P1 |  | 2021-04-18 | Rescheduled 18-Apr-21 |  | ممكن حيازته |  | 2021-04-18 | 2021-04-18 | 1 |  | 1 |  | 1 | Yes |  |  | Sharing with Mobily | TSS JV Planed | Sharing Mobily,TSS JV ongoing
MHL0339 | 18.5566 | 42.0422 | Assir | Mahail | Shehri | P1 |  | 2021-04-18 | Rescheduled 18-Apr-21 |  | ممكن حيازته |  | 2021-04-18 | 2021-04-18 | 2 | 2 |  |  | 2 | Yes |  |  |  | SAR Submitted | SAR Submitted waiting feedback

## Summary 1
Category | Total Sites | Action required | Owner
TSS JV Planed | 5 | Jv Planed on 2-May | Nokia / Zain
SAR Approved | 1 | waiting Planning feedback to proceed with TSS | Zain
SAR Submitted | 18 | waiting Planning feedback to proceed with TSS | Zain
SAR & JTR Submitted | 2 | waiting Planning feedback to proceed with TSS | Zain
SAR Submitted for new searching area | 2 | waiting Planning feedback to proceed with TSS | Zain
JTR shared (Waqf al aziziah Area ) | 2 | Waiting Zain SAQ feedback | Zain
Letter under submitted | 9 | Letter under submission in order to proceed with Survey | Nokia
Re-survey ongoing | 1 | On going Planed 2-May | Nokia
Waiting Letter for Jaddah Airport | 1 | Waiting for letter | Zain
TSS Done | 1 | waiting TX data | Zain
Grand Total | 42